## README
ENEC 2026 - Project 360 workbook (synthetic training data)
Synthetic data from Nuclear Enterprise 360 V2.2.
project_360 is built from the database view project_risk_360 joined with project attributes.
Sheet | Rows | What it contains
project_360 | 29 | MAIN VIEW: one row per project (29) with department, manager code, theme, dates, budget, completion, risk and action counts.
project_kpis | 336 | Monthly planned vs actual progress and cost per project (includes future-dated months).
risks | 423 | All project risks with probability, impact, exposure and mitigation plan.
actions | 807 | Mitigation actions with owner, priority, due date and status.
project_asset_links | 30 | Which assets each project covers (only a few projects have linked assets).
Suggested prompts for Copilot / ChatGPT / Colab
1. | Which projects are over budget or behind plan, and which have overdue actions?
2. | Rank projects by maximum_exposure and show the top 5 with their risk categories.
3. | Which risks have no mitigation action or an overdue action?
4. | Chart planned vs actual progress by month for the five largest-budget projects.
5. | Which projects are linked to assets, and what do their risks say about those assets?
Note | Only P-021, P-027 and P-029 link to assets. Questions that join projects to assets will mostly return empty results for other projects.
Note | project_kpis includes future-dated months. Training data only.

## project_360
project_id | project_name | department_name | project_manager_code | strategic_theme | start_date | planned_end_date | project_status | completion_pct | budget_usd | active_risks | maximum_exposure | active_actions | overdue_actions | linked_assets | total_risks
P-001 | Enterprise Knowledge and Risk Intelligence Pilot | Project Management | E-002 | Digital Transformation | 2025-10-29 | 2026-10-29 | AT_RISK | 52 | 1800000 | 9 | 25 | 19 | 3 | 0 | 16
P-002 | Risk Reporting Automation 02 | Supply Chain | E-026 | Workforce Capability | 2025-10-01 | 2027-01-24 | DELAYED | 74.8 | 4383052.07 | 7 | 20 | 16 | 4 | 0 | 13
P-003 | Training Digitization 03 | Quality and Performance | E-036 | Digital Transformation | 2025-01-22 | 2026-01-08 | ON_TRACK | 33 | 2991763.47 | 7 | 25 | 18 | 2 | 0 | 10
P-004 | Knowledge Management 04 | Learning and Development | E-191 | Sustainability | 2025-10-07 | 2026-09-04 | AT_RISK | 70.2 | 5785499.7 | 17 | 25 | 20 | 2 | 0 | 21
P-005 | Maintenance Planning Enhancement 05 | Enterprise ICT | E-155 | Quality Improvement | 2026-02-10 | 2026-11-10 | DELAYED | 89.7 | 5947522.55 | 13 | 20 | 16 | 1 | 0 | 17
P-006 | Analytics Enablement 06 | Project Management | E-002 | Digital Transformation | 2024-12-19 | 2026-01-26 | AT_RISK | 65.9 | 5286361.37 | 12 | 15 | 25 | 4 | 0 | 22
P-007 | Analytics Enablement 07 | Learning and Development | E-159 | Workforce Capability | 2025-12-05 | 2027-03-24 | AT_RISK | 47.2 | 5130137.16 | 9 | 20 | 14 | 2 | 0 | 12
P-008 | Data Quality Improvement 08 | Engineering | E-130 | Workforce Capability | 2025-07-13 | 2026-07-17 | ON_TRACK | 41.1 | 3444148.44 | 5 | 12 | 14 | 2 | 0 | 11
P-009 | Training Digitization 09 | Learning and Development | E-062 | Digital Transformation | 2026-02-16 | 2027-08-02 | ON_TRACK | 67.9 | 1182620.43 | 7 | 20 | 14 | 1 | 0 | 12
P-010 | Document Modernization 10 | Maintenance | E-057 | Digital Transformation | 2025-06-07 | 2026-10-29 | AT_RISK | 70.5 | 293994.35 | 12 | 25 | 21 | 4 | 0 | 17
P-011 | Maintenance Planning Enhancement 11 | Project Management | E-006 | Quality Improvement | 2026-01-20 | 2027-05-05 | AT_RISK | 83.7 | 4417500.41 | 8 | 20 | 15 | 5 | 0 | 13
P-012 | Document Modernization 12 | Supply Chain | E-052 | Workforce Capability | 2025-08-27 | 2026-08-08 | AT_RISK | 26 | 3290308.55 | 8 | 25 | 9 | 4 | 0 | 9
P-013 | Document Modernization 13 | Health Safety and Environment | E-138 | Workforce Capability | 2026-03-25 | 2026-12-28 | COMPLETED | 100 | 2781453.96 | 10 | 25 | 24 | 4 | 0 | 16
P-014 | Analytics Enablement 14 | Maintenance | E-057 | Workforce Capability | 2025-04-03 | 2026-11-03 | ON_TRACK | 86.3 | 1837514.01 | 11 | 16 | 11 | 3 | 0 | 16
P-015 | Document Modernization 15 | Health Safety and Environment | E-105 | Quality Improvement | 2025-06-25 | 2026-04-16 | DELAYED | 43.6 | 3288947.74 | 8 | 20 | 8 | 0 | 0 | 14
P-016 | Data Quality Improvement 16 | Health Safety and Environment | E-143 | Operational Excellence | 2025-12-25 | 2027-03-01 | AT_RISK | 66.1 | 4936474.5 | 8 | 20 | 17 | 6 | 0 | 16
P-017 | Analytics Enablement 17 | Learning and Development | E-119 | Quality Improvement | 2025-06-10 | 2026-05-17 | DELAYED | 67.6 | 3589355.03 | 13 | 25 | 20 | 9 | 0 | 17
P-018 | Document Modernization 18 | Quality and Performance | E-190 | Quality Improvement | 2025-10-15 | 2026-12-24 | AT_RISK | 60.3 | 2911734.78 | 8 | 20 | 15 | 4 | 0 | 15
P-019 | Maintenance Planning Enhancement 19 | Enterprise ICT | E-080 | Sustainability | 2025-02-02 | 2026-09-03 | COMPLETED | 100 | 3174734.45 | 11 | 15 | 16 | 1 | 0 | 16
P-020 | Training Digitization 20 | Enterprise ICT | E-136 | Operational Excellence | 2025-11-10 | 2027-04-28 | ON_TRACK | 39.5 | 1244042.98 | 9 | 10 | 20 | 3 | 0 | 14
P-021 | Data Quality Improvement 21 | Engineering | E-105 | Digital Transformation | 2025-11-18 | 2027-04-27 | ON_TRACK | 42.6 | 1074212.71 | 6 | 20 | 18 | 5 | 16 | 13
P-022 | Data Quality Improvement 22 | Health Safety and Environment | E-061 | Quality Improvement | 2025-11-20 | 2027-03-24 | AT_RISK | 83.2 | 1267999.57 | 13 | 20 | 22 | 2 | 0 | 22
P-023 | Supplier Performance Improvement 23 | Quality and Performance | E-079 | Workforce Capability | 2025-11-26 | 2027-03-09 | ON_TRACK | 55.3 | 305713.41 | 9 | 20 | 13 | 1 | 0 | 12
P-024 | Knowledge Management 24 | Enterprise ICT | E-070 | Workforce Capability | 2024-11-07 | 2025-11-06 | ON_TRACK | 44.6 | 2489082.95 | 6 | 25 | 10 | 3 | 0 | 10
P-025 | Knowledge Management 25 | Supply Chain | E-049 | Workforce Capability | 2025-01-27 | 2025-12-22 | ON_TRACK | 83.7 | 5602602.23 | 9 | 15 | 19 | 3 | 0 | 15
P-026 | Training Digitization 26 | Health Safety and Environment | E-182 | Quality Improvement | 2026-01-14 | 2027-07-20 | ON_TRACK | 56.2 | 5156959.03 | 11 | 20 | 20 | 3 | 0 | 19
P-027 | Supplier Performance Improvement 27 | Engineering | E-126 | Operational Excellence | 2026-03-19 | 2027-05-30 | ON_TRACK | 35.4 | 5820130.11 | 11 | 20 | 12 | 1 | 13 | 17
P-028 | Document Modernization 28 | Learning and Development | E-107 | Workforce Capability | 2026-04-16 | 2027-11-23 | ON_TRACK | 85.8 | 4408362.41 | 10 | 25 | 24 | 4 | 0 | 15
P-029 | A-001 Cooling Water Pump Reliability Improvement | Engineering | E-001 | Operational Excellence | 2026-08-20 | 2026-11-18 | AT_RISK | 0 | 20229.72 | 3 | 20 | 7 | 0 | 1 | 3

## project_kpis
project_id | kpi_month | planned_progress_pct | actual_progress_pct | planned_cost_usd | actual_cost_usd | quality_score | open_actions | project_name
P-001 | 2025-10-01 | 8 | 0 | 144000 | 158929.97 | 97.4 | 13 | Enterprise Knowledge and Risk Intelligence Pilot
P-001 | 2025-11-01 | 16 | 7.1 | 288000 | 321231.69 | 87 | 17 | Enterprise Knowledge and Risk Intelligence Pilot
P-001 | 2025-12-01 | 24 | 13.8 | 432000 | 451791.77 | 97.7 | 22 | Enterprise Knowledge and Risk Intelligence Pilot
P-001 | 2026-01-01 | 32 | 24.2 | 576000 | 628434.57 | 88.3 | 4 | Enterprise Knowledge and Risk Intelligence Pilot
P-001 | 2026-02-01 | 40 | 28.7 | 720000 | 799469.45 | 84.4 | 16 | Enterprise Knowledge and Risk Intelligence Pilot
P-001 | 2026-03-01 | 48 | 35.4 | 864000 | 898005.84 | 95.6 | 19 | Enterprise Knowledge and Risk Intelligence Pilot
P-001 | 2026-04-01 | 56 | 43.3 | 1008000 | 1058803.27 | 79.4 | 4 | Enterprise Knowledge and Risk Intelligence Pilot
P-001 | 2026-05-01 | 64 | 44.3 | 1152000 | 1474560 | 93.1 | 20 | Enterprise Knowledge and Risk Intelligence Pilot
P-001 | 2026-06-01 | 72 | 52 | 1296000 | 1658880 | 79.1 | 15 | Enterprise Knowledge and Risk Intelligence Pilot
P-001 | 2026-07-01 | 80 | 60.5 | 1440000 | 1843200 | 92.8 | 7 | Enterprise Knowledge and Risk Intelligence Pilot
P-001 | 2026-08-01 | 88 | 67.4 | 1584000 | 2027520 | 92.2 | 19 | Enterprise Knowledge and Risk Intelligence Pilot
P-001 | 2026-09-01 | 96 | 76.6 | 1728000 | 2211840 | 98.9 | 18 | Enterprise Knowledge and Risk Intelligence Pilot
P-002 | 2025-10-01 | 8 | 0 | 350644.17 | 382362.11 | 94.1 | 21 | Risk Reporting Automation 02
P-002 | 2025-11-01 | 16 | 12.6 | 701288.33 | 724416.96 | 88.7 | 11 | Risk Reporting Automation 02
P-002 | 2025-12-01 | 24 | 16.7 | 1051932.5 | 1175821.87 | 84.1 | 18 | Risk Reporting Automation 02
P-002 | 2026-01-01 | 32 | 19.6 | 1402576.66 | 1530067.37 | 91.8 | 18 | Risk Reporting Automation 02
P-002 | 2026-02-01 | 40 | 34.6 | 1753220.83 | 1920299.61 | 95.5 | 2 | Risk Reporting Automation 02
P-002 | 2026-03-01 | 48 | 39 | 2103864.99 | 2339694.85 | 97.5 | 25 | Risk Reporting Automation 02
P-002 | 2026-04-01 | 56 | 42.8 | 2454509.16 | 2678742.59 | 81.1 | 3 | Risk Reporting Automation 02
P-002 | 2026-05-01 | 64 | 49.1 | 2805153.32 | 3271609.72 | 88.8 | 24 | Risk Reporting Automation 02
P-002 | 2026-06-01 | 72 | 67.9 | 3155797.49 | 3242726.05 | 89 | 20 | Risk Reporting Automation 02
P-002 | 2026-07-01 | 80 | 74.2 | 3506441.66 | 3952954.74 | 84 | 23 | Risk Reporting Automation 02
P-002 | 2026-08-01 | 88 | 76.5 | 3857085.82 | 4276412.68 | 92.3 | 13 | Risk Reporting Automation 02
P-002 | 2026-09-01 | 96 | 84.5 | 4207729.99 | 4564330.58 | 91 | 26 | Risk Reporting Automation 02
P-003 | 2025-01-01 | 8 | 7.2 | 239341.08 | 239341.08 | 97.9 | 2 | Training Digitization 03
P-003 | 2025-02-01 | 16 | 17.3 | 478682.16 | 478682.16 | 87.4 | 11 | Training Digitization 03
P-003 | 2025-03-01 | 24 | 22.5 | 718023.23 | 718023.23 | 98.6 | 14 | Training Digitization 03
P-003 | 2025-04-01 | 32 | 32.4 | 957364.31 | 957364.31 | 95.8 | 15 | Training Digitization 03
P-003 | 2025-05-01 | 40 | 39.1 | 1196705.39 | 1196705.39 | 93.1 | 18 | Training Digitization 03
P-003 | 2025-06-01 | 48 | 49.4 | 1436046.47 | 1436046.47 | 88.5 | 24 | Training Digitization 03
P-003 | 2025-07-01 | 56 | 56.5 | 1675387.54 | 1675387.54 | 98.3 | 9 | Training Digitization 03
P-003 | 2025-08-01 | 64 | 62.5 | 1914728.62 | 1914728.62 | 90.9 | 7 | Training Digitization 03
P-003 | 2025-09-01 | 72 | 71.1 | 2154069.7 | 2154069.7 | 85.3 | 18 | Training Digitization 03
P-003 | 2025-10-01 | 80 | 81.9 | 2393410.78 | 2393410.78 | 87.1 | 20 | Training Digitization 03
P-003 | 2025-11-01 | 88 | 87.8 | 2632751.85 | 2632751.85 | 91.4 | 19 | Training Digitization 03
P-003 | 2025-12-01 | 96 | 97.9 | 2872092.93 | 2872092.93 | 95 | 8 | Training Digitization 03
P-004 | 2025-10-01 | 8 | 0 | 462839.98 | 492096.51 | 87.7 | 26 | Knowledge Management 04
P-004 | 2025-11-01 | 16 | 7.5 | 925679.95 | 981415.22 | 83.7 | 14 | Knowledge Management 04
P-004 | 2025-12-01 | 24 | 17.9 | 1388519.93 | 1422425.04 | 82.3 | 20 | Knowledge Management 04
P-004 | 2026-01-01 | 32 | 24.6 | 1851359.9 | 2091486.38 | 84.4 | 14 | Knowledge Management 04
P-004 | 2026-02-01 | 40 | 35.1 | 2314199.88 | 2683330.63 | 86.7 | 10 | Knowledge Management 04
P-004 | 2026-03-01 | 48 | 39.4 | 2777039.86 | 3045518.66 | 97.4 | 27 | Knowledge Management 04
P-004 | 2026-04-01 | 56 | 48.4 | 3239879.83 | 3634585.55 | 78.3 | 18 | Knowledge Management 04
P-004 | 2026-05-01 | 64 | 57.6 | 3702719.81 | 3946707.11 | 81.7 | 10 | Knowledge Management 04
P-004 | 2026-06-01 | 72 | 65.7 | 4165559.78 | 4475192.36 | 80.1 | 3 | Knowledge Management 04
P-004 | 2026-07-01 | 80 | 70.8 | 4628399.76 | 5256170.1 | 82.1 | 20 | Knowledge Management 04
P-004 | 2026-08-01 | 88 | 77.5 | 5091239.74 | 5350554.08 | 87.3 | 27 | Knowledge Management 04
P-004 | 2026-09-01 | 96 | 92 | 5554079.71 | 5896401.65 | 91.6 | 13 | Knowledge Management 04
P-005 | 2026-02-01 | 8 | 0 | 475801.8 | 502567.95 | 86.7 | 17 | Maintenance Planning Enhancement 05
P-005 | 2026-03-01 | 16 | 7.2 | 951603.61 | 1101829.61 | 86.6 | 18 | Maintenance Planning Enhancement 05
P-005 | 2026-04-01 | 24 | 16.5 | 1427405.41 | 1502681.73 | 86.7 | 2 | Maintenance Planning Enhancement 05
P-005 | 2026-05-01 | 32 | 26.1 | 1903207.22 | 2203584.85 | 80.3 | 21 | Maintenance Planning Enhancement 05
P-005 | 2026-06-01 | 40 | 32.7 | 2379009.02 | 2728197.4 | 80.3 | 21 | Maintenance Planning Enhancement 05
P-005 | 2026-07-01 | 48 | 40.4 | 2854810.82 | 3104394.09 | 91.8 | 11 | Maintenance Planning Enhancement 05
P-005 | 2026-08-01 | 56 | 50 | 3330612.63 | 3922449.2 | 96.1 | 15 | Maintenance Planning Enhancement 05
P-005 | 2026-09-01 | 64 | 51.5 | 3806414.43 | 4067816.4 | 89.3 | 6 | Maintenance Planning Enhancement 05
P-005 | 2026-10-01 | 72 | 63.4 | 4282216.24 | 4612257.16 | 82.9 | 13 | Maintenance Planning Enhancement 05
P-005 | 2026-11-01 | 80 | 72.7 | 4758018.04 | 5123175.97 | 96.7 | 19 | Maintenance Planning Enhancement 05
P-005 | 2026-12-01 | 88 | 77.8 | 5233819.84 | 6082245.58 | 92.4 | 19 | Maintenance Planning Enhancement 05
P-005 | 2027-01-01 | 96 | 88.9 | 5709621.65 | 6586472.27 | 79.2 | 17 | Maintenance Planning Enhancement 05
P-006 | 2024-12-01 | 8 | 0 | 422908.91 | 485147.06 | 91.7 | 25 | Analytics Enablement 06
P-006 | 2025-01-01 | 16 | 5.2 | 845817.82 | 963016.96 | 98.6 | 25 | Analytics Enablement 06
P-006 | 2025-02-01 | 24 | 9.9 | 1268726.73 | 1429824.25 | 92 | 11 | Analytics Enablement 06
P-006 | 2025-03-01 | 32 | 23.4 | 1691635.64 | 1936620.29 | 94.3 | 10 | Analytics Enablement 06
P-006 | 2025-04-01 | 40 | 27.7 | 2114544.55 | 2315512.22 | 85.7 | 4 | Analytics Enablement 06
P-006 | 2025-05-01 | 48 | 38.1 | 2537453.46 | 2904855.96 | 95.5 | 3 | Analytics Enablement 06
P-006 | 2025-06-01 | 56 | 47 | 2960362.37 | 3246069.89 | 97.3 | 7 | Analytics Enablement 06
P-006 | 2025-07-01 | 64 | 55.2 | 3383271.28 | 3825040.11 | 89.7 | 26 | Analytics Enablement 06
P-006 | 2025-08-01 | 72 | 60.9 | 3806180.19 | 4200209.91 | 91.4 | 16 | Analytics Enablement 06
P-006 | 2025-09-01 | 80 | 73.5 | 4229089.1 | 4646363.68 | 84.7 | 7 | Analytics Enablement 06
P-006 | 2025-10-01 | 88 | 80.8 | 4651998.01 | 4995166.19 | 96.6 | 17 | Analytics Enablement 06
P-006 | 2025-11-01 | 96 | 88.8 | 5074906.92 | 5479611.59 | 89.7 | 10 | Analytics Enablement 06
P-007 | 2025-12-01 | 8 | 0 | 410410.97 | 483742.92 | 96.1 | 12 | Analytics Enablement 07
P-007 | 2026-01-01 | 16 | 12.7 | 820821.95 | 963012.6 | 96.8 | 2 | Analytics Enablement 07
P-007 | 2026-02-01 | 24 | 16.2 | 1231232.92 | 1313416.63 | 82.8 | 12 | Analytics Enablement 07
P-007 | 2026-03-01 | 32 | 20.7 | 1641643.89 | 1846325.98 | 81.3 | 2 | Analytics Enablement 07
P-007 | 2026-04-01 | 40 | 26.4 | 2052054.86 | 2281848.99 | 92.4 | 26 | Analytics Enablement 07
P-007 | 2026-05-01 | 48 | 38.1 | 2462465.84 | 2548717.28 | 92.4 | 5 | Analytics Enablement 07
P-007 | 2026-06-01 | 56 | 39.5 | 2872876.81 | 3021824.91 | 97.8 | 10 | Analytics Enablement 07
P-007 | 2026-07-01 | 64 | 55.8 | 3283287.78 | 3815494.67 | 84.8 | 15 | Analytics Enablement 07
P-007 | 2026-08-01 | 72 | 66.7 | 3693698.76 | 4168126.76 | 93.9 | 25 | Analytics Enablement 07
P-007 | 2026-09-01 | 80 | 67.6 | 4104109.73 | 4605212 | 97.1 | 27 | Analytics Enablement 07
P-007 | 2026-10-01 | 88 | 77 | 4514520.7 | 5125394.08 | 88.1 | 18 | Analytics Enablement 07
P-007 | 2026-11-01 | 96 | 85.5 | 4924931.67 | 5044074.3 | 90.9 | 9 | Analytics Enablement 07
P-008 | 2025-07-01 | 8 | 6.2 | 275531.88 | 275531.88 | 98.8 | 2 | Data Quality Improvement 08
P-008 | 2025-08-01 | 16 | 14.4 | 551063.75 | 551063.75 | 83.3 | 4 | Data Quality Improvement 08
P-008 | 2025-09-01 | 24 | 25.5 | 826595.63 | 826595.63 | 94.4 | 4 | Data Quality Improvement 08
P-008 | 2025-10-01 | 32 | 33 | 1102127.5 | 1102127.5 | 84.1 | 3 | Data Quality Improvement 08
P-008 | 2025-11-01 | 40 | 40.3 | 1377659.38 | 1377659.38 | 87.6 | 17 | Data Quality Improvement 08
P-008 | 2025-12-01 | 48 | 46.9 | 1653191.25 | 1653191.25 | 87.3 | 26 | Data Quality Improvement 08
P-008 | 2026-01-01 | 56 | 54.3 | 1928723.13 | 1928723.13 | 90.3 | 3 | Data Quality Improvement 08
P-008 | 2026-02-01 | 64 | 65.9 | 2204255 | 2204255 | 86.4 | 21 | Data Quality Improvement 08
P-008 | 2026-03-01 | 72 | 71.8 | 2479786.88 | 2479786.88 | 97.9 | 26 | Data Quality Improvement 08
P-008 | 2026-04-01 | 80 | 81.1 | 2755318.75 | 2755318.75 | 98.5 | 8 | Data Quality Improvement 08
P-008 | 2026-05-01 | 88 | 86.7 | 3030850.63 | 3030850.63 | 96.3 | 16 | Data Quality Improvement 08
P-008 | 2026-06-01 | 96 | 97.8 | 3306382.5 | 3306382.5 | 86.7 | 9 | Data Quality Improvement 08
P-009 | 2026-02-01 | 8 | 7 | 94609.63 | 94609.63 | 98.6 | 3 | Training Digitization 09
P-009 | 2026-03-01 | 16 | 17.9 | 189219.27 | 189219.27 | 88.6 | 15 | Training Digitization 09
P-009 | 2026-04-01 | 24 | 22.5 | 283828.9 | 283828.9 | 83.9 | 19 | Training Digitization 09
P-009 | 2026-05-01 | 32 | 33.6 | 378438.54 | 378438.54 | 84.8 | 16 | Training Digitization 09
P-009 | 2026-06-01 | 40 | 40.8 | 473048.17 | 473048.17 | 85.1 | 8 | Training Digitization 09
P-009 | 2026-07-01 | 48 | 46.4 | 567657.81 | 567657.81 | 97.1 | 5 | Training Digitization 09
P-009 | 2026-08-01 | 56 | 54.1 | 662267.44 | 662267.44 | 84 | 27 | Training Digitization 09
P-009 | 2026-09-01 | 64 | 63.3 | 756877.08 | 756877.08 | 89.3 | 7 | Training Digitization 09
P-009 | 2026-10-01 | 72 | 71.5 | 851486.71 | 851486.71 | 83.5 | 28 | Training Digitization 09
P-009 | 2026-11-01 | 80 | 78.6 | 946096.34 | 946096.34 | 96.3 | 3 | Training Digitization 09
P-009 | 2026-12-01 | 88 | 86.7 | 1040705.98 | 1040705.98 | 78.6 | 7 | Training Digitization 09
P-009 | 2027-01-01 | 96 | 94.1 | 1135315.61 | 1135315.61 | 86.3 | 17 | Training Digitization 09
P-010 | 2025-06-01 | 8 | 1.4 | 23519.55 | 26924.48 | 88.5 | 19 | Document Modernization 10
P-010 | 2025-07-01 | 16 | 1 | 47039.1 | 54386.96 | 87.2 | 26 | Document Modernization 10
P-010 | 2025-08-01 | 24 | 11.5 | 70558.64 | 73355.29 | 78.4 | 20 | Document Modernization 10
P-010 | 2025-09-01 | 32 | 20.7 | 94078.19 | 104435.21 | 97 | 24 | Document Modernization 10
P-010 | 2025-10-01 | 40 | 31.6 | 117597.74 | 138364.01 | 80.8 | 26 | Document Modernization 10
P-010 | 2025-11-01 | 48 | 39.1 | 141117.29 | 149402.2 | 91.2 | 2 | Document Modernization 10
P-010 | 2025-12-01 | 56 | 49.9 | 164636.84 | 170651.29 | 97 | 20 | Document Modernization 10
P-010 | 2026-01-01 | 64 | 58 | 188156.38 | 205368.31 | 85.3 | 26 | Document Modernization 10
P-010 | 2026-02-01 | 72 | 68.2 | 211675.93 | 228379.18 | 96.5 | 25 | Document Modernization 10
P-010 | 2026-03-01 | 80 | 66.1 | 235195.48 | 259704.66 | 91.3 | 2 | Document Modernization 10
P-010 | 2026-04-01 | 88 | 71.5 | 258715.03 | 295473.57 | 84.1 | 18 | Document Modernization 10
P-010 | 2026-05-01 | 96 | 81.3 | 282234.58 | 289450.33 | 99 | 9 | Document Modernization 10
P-011 | 2026-01-01 | 8 | 0 | 353400.03 | 406460.58 | 89.8 | 20 | Maintenance Planning Enhancement 11
P-011 | 2026-02-01 | 16 | 4.4 | 706800.07 | 770635.47 | 98.9 | 24 | Maintenance Planning Enhancement 11
P-011 | 2026-03-01 | 24 | 16.5 | 1060200.1 | 1209299.1 | 82.4 | 5 | Maintenance Planning Enhancement 11
P-011 | 2026-04-01 | 32 | 27.8 | 1413600.13 | 1594184.22 | 90.8 | 25 | Maintenance Planning Enhancement 11
P-011 | 2026-05-01 | 40 | 32 | 1767000.16 | 2073585.38 | 80.3 | 9 | Maintenance Planning Enhancement 11
P-011 | 2026-06-01 | 48 | 37.5 | 2120400.2 | 2212171.3 | 89.5 | 6 | Maintenance Planning Enhancement 11
P-011 | 2026-07-01 | 56 | 52.9 | 2473800.23 | 2842143.56 | 86.3 | 14 | Maintenance Planning Enhancement 11
P-011 | 2026-08-01 | 64 | 53 | 2827200.26 | 3065609.85 | 78.3 | 6 | Maintenance Planning Enhancement 11
P-011 | 2026-09-01 | 72 | 57.8 | 3180600.3 | 3403606.44 | 78.3 | 5 | Maintenance Planning Enhancement 11
P-011 | 2026-10-01 | 80 | 73 | 3534000.33 | 3668445.06 | 90.6 | 15 | Maintenance Planning Enhancement 11
P-011 | 2026-11-01 | 88 | 76.3 | 3887400.36 | 4186486.64 | 91.3 | 19 | Maintenance Planning Enhancement 11
P-011 | 2026-12-01 | 96 | 89 | 4240800.39 | 4556211.38 | 88.2 | 20 | Maintenance Planning Enhancement 11
P-012 | 2025-08-01 | 8 | 0 | 263224.68 | 273196.91 | 84.4 | 24 | Document Modernization 12
P-012 | 2025-09-01 | 16 | 0.7 | 526449.37 | 554489.95 | 79.6 | 18 | Document Modernization 12
P-012 | 2025-10-01 | 24 | 10.4 | 789674.05 | 871282.24 | 97.3 | 5 | Document Modernization 12
P-012 | 2025-11-01 | 32 | 27.4 | 1052898.74 | 1180950.41 | 92.7 | 23 | Document Modernization 12
P-012 | 2025-12-01 | 40 | 37.2 | 1316123.42 | 1520823.5 | 88.1 | 24 | Document Modernization 12
P-012 | 2026-01-01 | 48 | 40.5 | 1579348.1 | 1612895.49 | 93.7 | 7 | Document Modernization 12
P-012 | 2026-02-01 | 56 | 40 | 1842572.79 | 2158347.13 | 92.7 | 18 | Document Modernization 12
P-012 | 2026-03-01 | 64 | 57.9 | 2105797.47 | 2272874.08 | 91.5 | 22 | Document Modernization 12
P-012 | 2026-04-01 | 72 | 60.3 | 2369022.16 | 2626433.33 | 82 | 22 | Document Modernization 12
P-012 | 2026-05-01 | 80 | 68.9 | 2632246.84 | 2990316.9 | 86.3 | 15 | Document Modernization 12
P-012 | 2026-06-01 | 88 | 81.1 | 2895471.52 | 3304691.88 | 89.5 | 20 | Document Modernization 12
P-012 | 2026-07-01 | 96 | 80.2 | 3158696.21 | 3325834.65 | 97.2 | 12 | Document Modernization 12
P-013 | 2026-03-01 | 8 | 7.9 | 222516.32 | 222516.32 | 97.2 | 27 | Document Modernization 13
P-013 | 2026-04-01 | 16 | 15.4 | 445032.63 | 445032.63 | 92.8 | 9 | Document Modernization 13
P-013 | 2026-05-01 | 24 | 24.7 | 667548.95 | 667548.95 | 80.4 | 10 | Document Modernization 13
P-013 | 2026-06-01 | 32 | 31.2 | 890065.27 | 890065.27 | 96.5 | 12 | Document Modernization 13
P-013 | 2026-07-01 | 40 | 38.5 | 1112581.58 | 1112581.58 | 80.3 | 7 | Document Modernization 13
P-013 | 2026-08-01 | 48 | 48.7 | 1335097.9 | 1335097.9 | 87.9 | 9 | Document Modernization 13
P-013 | 2026-09-01 | 56 | 58 | 1557614.22 | 1557614.22 | 79.7 | 28 | Document Modernization 13
P-013 | 2026-10-01 | 64 | 64.7 | 1780130.53 | 1780130.53 | 79.7 | 24 | Document Modernization 13
P-013 | 2026-11-01 | 72 | 73.2 | 2002646.85 | 2002646.85 | 82.9 | 8 | Document Modernization 13
P-013 | 2026-12-01 | 80 | 78.9 | 2225163.17 | 2225163.17 | 98.9 | 16 | Document Modernization 13
P-013 | 2027-01-01 | 88 | 87.8 | 2447679.48 | 2447679.48 | 93 | 25 | Document Modernization 13
P-013 | 2027-02-01 | 96 | 95.5 | 2670195.8 | 2670195.8 | 98.4 | 21 | Document Modernization 13
P-014 | 2025-04-01 | 8 | 8.5 | 147001.12 | 147001.12 | 93.7 | 27 | Analytics Enablement 14
P-014 | 2025-05-01 | 16 | 14.7 | 294002.24 | 294002.24 | 87.4 | 23 | Analytics Enablement 14
P-014 | 2025-06-01 | 24 | 22.3 | 441003.36 | 441003.36 | 85.1 | 10 | Analytics Enablement 14
P-014 | 2025-07-01 | 32 | 31.2 | 588004.48 | 588004.48 | 88.2 | 25 | Analytics Enablement 14
P-014 | 2025-08-01 | 40 | 38.5 | 735005.6 | 735005.6 | 78.4 | 24 | Analytics Enablement 14
P-014 | 2025-09-01 | 48 | 48.7 | 882006.72 | 882006.72 | 97.5 | 20 | Analytics Enablement 14
P-014 | 2025-10-01 | 56 | 58 | 1029007.85 | 1029007.85 | 78.8 | 6 | Analytics Enablement 14
P-014 | 2025-11-01 | 64 | 63.8 | 1176008.97 | 1176008.97 | 95.1 | 15 | Analytics Enablement 14
P-014 | 2025-12-01 | 72 | 71.2 | 1323010.09 | 1323010.09 | 97.3 | 5 | Analytics Enablement 14
P-014 | 2026-01-01 | 80 | 80 | 1470011.21 | 1470011.21 | 88.8 | 23 | Analytics Enablement 14
P-014 | 2026-02-01 | 88 | 89.1 | 1617012.33 | 1617012.33 | 89.3 | 25 | Analytics Enablement 14
P-014 | 2026-03-01 | 96 | 97.3 | 1764013.45 | 1764013.45 | 94.3 | 21 | Analytics Enablement 14
P-015 | 2025-06-01 | 8 | 0 | 263115.82 | 286348.7 | 86.3 | 23 | Document Modernization 15
P-015 | 2025-07-01 | 16 | 2.4 | 526231.64 | 596419.23 | 93 | 8 | Document Modernization 15
P-015 | 2025-08-01 | 24 | 9.6 | 789347.46 | 863649.8 | 82.9 | 25 | Document Modernization 15
P-015 | 2025-09-01 | 32 | 20.2 | 1052463.28 | 1185477.45 | 78.4 | 20 | Document Modernization 15
P-015 | 2025-10-01 | 40 | 23.4 | 1315579.1 | 1455248.44 | 78.2 | 17 | Document Modernization 15
P-015 | 2025-11-01 | 48 | 36.9 | 1578694.92 | 1747079.23 | 91.6 | 4 | Document Modernization 15
P-015 | 2025-12-01 | 56 | 46 | 1841810.73 | 1962915.75 | 93.8 | 8 | Document Modernization 15
P-015 | 2026-01-01 | 64 | 47.8 | 2104926.55 | 2228630.79 | 89.1 | 12 | Document Modernization 15
P-015 | 2026-02-01 | 72 | 61.2 | 2368042.37 | 2684314.1 | 98.2 | 24 | Document Modernization 15
P-015 | 2026-03-01 | 80 | 67.3 | 2631158.19 | 3093934.52 | 89.5 | 21 | Document Modernization 15
P-015 | 2026-04-01 | 88 | 82.9 | 2894274.01 | 3105364.01 | 87.3 | 21 | Document Modernization 15
P-015 | 2026-05-01 | 96 | 86.3 | 3157389.83 | 3351700.74 | 88.1 | 24 | Document Modernization 15
P-016 | 2025-12-01 | 8 | 0.2 | 394917.96 | 439278.39 | 97.4 | 27 | Data Quality Improvement 16
P-016 | 2026-01-01 | 16 | 4.9 | 789835.92 | 812580.51 | 94 | 7 | Data Quality Improvement 16
P-016 | 2026-02-01 | 24 | 17.5 | 1184753.88 | 1265519.64 | 80.5 | 17 | Data Quality Improvement 16
P-016 | 2026-03-01 | 32 | 27.7 | 1579671.84 | 1617083.51 | 80.2 | 18 | Data Quality Improvement 16
P-016 | 2026-04-01 | 40 | 32.9 | 1974589.8 | 2211765.36 | 90.5 | 16 | Data Quality Improvement 16
P-016 | 2026-05-01 | 48 | 33.9 | 2369507.76 | 2779963.05 | 95.4 | 18 | Data Quality Improvement 16
P-016 | 2026-06-01 | 56 | 48.4 | 2764425.72 | 3207053.87 | 80.4 | 28 | Data Quality Improvement 16
P-016 | 2026-07-01 | 64 | 60.8 | 3159343.68 | 3548339.49 | 78.1 | 27 | Data Quality Improvement 16
P-016 | 2026-08-01 | 72 | 64.8 | 3554261.64 | 4043610.13 | 91.7 | 4 | Data Quality Improvement 16
P-016 | 2026-09-01 | 80 | 71.5 | 3949179.6 | 4132399.1 | 91.7 | 22 | Data Quality Improvement 16
P-016 | 2026-10-01 | 88 | 73.7 | 4344097.56 | 4764003.18 | 91.3 | 12 | Data Quality Improvement 16
P-016 | 2026-11-01 | 96 | 85.1 | 4739015.52 | 5455625.7 | 98 | 15 | Data Quality Improvement 16
P-017 | 2025-06-01 | 8 | 0 | 287148.4 | 295648.39 | 83.4 | 22 | Analytics Enablement 17
P-017 | 2025-07-01 | 16 | 1.4 | 574296.8 | 675692.71 | 85.8 | 23 | Analytics Enablement 17
P-017 | 2025-08-01 | 24 | 12.3 | 861445.21 | 963757.24 | 97.1 | 13 | Analytics Enablement 17
P-017 | 2025-09-01 | 32 | 25.2 | 1148593.61 | 1281970.7 | 83.5 | 19 | Analytics Enablement 17
P-017 | 2025-10-01 | 40 | 33.1 | 1435742.01 | 1476494.88 | 97.3 | 9 | Analytics Enablement 17
P-017 | 2025-11-01 | 48 | 36.5 | 1722890.41 | 1807579.87 | 84.4 | 11 | Analytics Enablement 17
P-017 | 2025-12-01 | 56 | 45.2 | 2010038.82 | 2087237.57 | 84.6 | 27 | Analytics Enablement 17
P-017 | 2026-01-01 | 64 | 58.3 | 2297187.22 | 2647017.35 | 80.6 | 16 | Analytics Enablement 17
P-017 | 2026-02-01 | 72 | 62.2 | 2584335.62 | 2892888.74 | 91.4 | 6 | Analytics Enablement 17
P-017 | 2026-03-01 | 80 | 70.9 | 2871484.02 | 3387582.16 | 82.9 | 7 | Analytics Enablement 17
P-017 | 2026-04-01 | 88 | 74.4 | 3158632.43 | 3330691.73 | 96.3 | 20 | Analytics Enablement 17
P-017 | 2026-05-01 | 96 | 83.2 | 3445780.83 | 3629176.99 | 79 | 5 | Analytics Enablement 17
P-018 | 2025-10-01 | 8 | 0 | 232938.78 | 267772.49 | 78.3 | 11 | Document Modernization 18
P-018 | 2025-11-01 | 16 | 8.2 | 465877.56 | 539392.8 | 88.2 | 16 | Document Modernization 18
P-018 | 2025-12-01 | 24 | 15.4 | 698816.35 | 775205.78 | 90.2 | 19 | Document Modernization 18
P-018 | 2026-01-01 | 32 | 24 | 931755.13 | 1086829.38 | 89.2 | 10 | Document Modernization 18
P-018 | 2026-02-01 | 40 | 25.4 | 1164693.91 | 1299864.61 | 90.5 | 15 | Document Modernization 18
P-018 | 2026-03-01 | 48 | 41.4 | 1397632.69 | 1515143.35 | 92.5 | 7 | Document Modernization 18
P-018 | 2026-04-01 | 56 | 43.1 | 1630571.48 | 1773527.7 | 85.2 | 3 | Document Modernization 18
P-018 | 2026-05-01 | 64 | 61.8 | 1863510.26 | 1920852.37 | 88.4 | 18 | Document Modernization 18
P-018 | 2026-06-01 | 72 | 59.7 | 2096449.04 | 2294135.71 | 97.4 | 5 | Document Modernization 18
P-018 | 2026-07-01 | 80 | 65.6 | 2329387.82 | 2583482.32 | 96.8 | 18 | Document Modernization 18
P-018 | 2026-08-01 | 88 | 76.2 | 2562326.61 | 2918388.38 | 96 | 17 | Document Modernization 18
P-018 | 2026-09-01 | 96 | 88.8 | 2795265.39 | 3123577.96 | 82.3 | 14 | Document Modernization 18
P-019 | 2025-02-01 | 8 | 8.5 | 253978.76 | 253978.76 | 94.1 | 11 | Maintenance Planning Enhancement 19
P-019 | 2025-03-01 | 16 | 16.8 | 507957.51 | 507957.51 | 86.2 | 22 | Maintenance Planning Enhancement 19
P-019 | 2025-04-01 | 24 | 22.8 | 761936.27 | 761936.27 | 85.8 | 23 | Maintenance Planning Enhancement 19
P-019 | 2025-05-01 | 32 | 32.1 | 1015915.02 | 1015915.02 | 79.6 | 6 | Maintenance Planning Enhancement 19
P-019 | 2025-06-01 | 40 | 39.9 | 1269893.78 | 1269893.78 | 91.2 | 24 | Maintenance Planning Enhancement 19
P-019 | 2025-07-01 | 48 | 47.5 | 1523872.54 | 1523872.54 | 81.6 | 23 | Maintenance Planning Enhancement 19
P-019 | 2025-08-01 | 56 | 54.8 | 1777851.29 | 1777851.29 | 86.4 | 17 | Maintenance Planning Enhancement 19
P-019 | 2025-09-01 | 64 | 65.8 | 2031830.05 | 2031830.05 | 86.4 | 9 | Maintenance Planning Enhancement 19
P-019 | 2025-10-01 | 72 | 70.6 | 2285808.8 | 2285808.8 | 84.2 | 25 | Maintenance Planning Enhancement 19
P-019 | 2025-11-01 | 80 | 78.7 | 2539787.56 | 2539787.56 | 95.9 | 4 | Maintenance Planning Enhancement 19
P-019 | 2025-12-01 | 88 | 88.4 | 2793766.32 | 2793766.32 | 88.8 | 20 | Maintenance Planning Enhancement 19
P-019 | 2026-01-01 | 96 | 96.2 | 3047745.07 | 3047745.07 | 91.4 | 25 | Maintenance Planning Enhancement 19
P-020 | 2025-11-01 | 8 | 7.6 | 99523.44 | 99523.44 | 98.8 | 16 | Training Digitization 20
P-020 | 2025-12-01 | 16 | 15.3 | 199046.88 | 199046.88 | 97.9 | 13 | Training Digitization 20
P-020 | 2026-01-01 | 24 | 22 | 298570.32 | 298570.32 | 86.6 | 27 | Training Digitization 20
P-020 | 2026-02-01 | 32 | 33.6 | 398093.75 | 398093.75 | 98.5 | 4 | Training Digitization 20
P-020 | 2026-03-01 | 40 | 38.5 | 497617.19 | 497617.19 | 84.6 | 10 | Training Digitization 20
P-020 | 2026-04-01 | 48 | 46.7 | 597140.63 | 597140.63 | 88 | 2 | Training Digitization 20
P-020 | 2026-05-01 | 56 | 54.9 | 696664.07 | 696664.07 | 85.3 | 24 | Training Digitization 20
P-020 | 2026-06-01 | 64 | 65.4 | 796187.51 | 796187.51 | 79.3 | 13 | Training Digitization 20
P-020 | 2026-07-01 | 72 | 73.4 | 895710.95 | 895710.95 | 94.4 | 22 | Training Digitization 20
P-020 | 2026-08-01 | 80 | 78.7 | 995234.38 | 995234.38 | 94 | 11 | Training Digitization 20
P-020 | 2026-09-01 | 88 | 86.6 | 1094757.82 | 1094757.82 | 89.4 | 23 | Training Digitization 20
P-020 | 2026-10-01 | 96 | 97.4 | 1194281.26 | 1194281.26 | 82.2 | 28 | Training Digitization 20
P-021 | 2025-11-01 | 8 | 7.2 | 85937.02 | 85937.02 | 78.1 | 2 | Data Quality Improvement 21
P-021 | 2025-12-01 | 16 | 15.1 | 171874.03 | 171874.03 | 88.8 | 15 | Data Quality Improvement 21
P-021 | 2026-01-01 | 24 | 25.1 | 257811.05 | 257811.05 | 84.4 | 27 | Data Quality Improvement 21
P-021 | 2026-02-01 | 32 | 33.6 | 343748.07 | 343748.07 | 91.8 | 6 | Data Quality Improvement 21
P-021 | 2026-03-01 | 40 | 38.2 | 429685.08 | 429685.08 | 85.6 | 25 | Data Quality Improvement 21
P-021 | 2026-04-01 | 48 | 49.7 | 515622.1 | 515622.1 | 92.1 | 25 | Data Quality Improvement 21
P-021 | 2026-05-01 | 56 | 54.7 | 601559.12 | 601559.12 | 97.8 | 5 | Data Quality Improvement 21
P-021 | 2026-06-01 | 64 | 63.5 | 687496.13 | 687496.13 | 84.4 | 7 | Data Quality Improvement 21
P-021 | 2026-07-01 | 72 | 71.8 | 773433.15 | 773433.15 | 79.3 | 16 | Data Quality Improvement 21
P-021 | 2026-08-01 | 80 | 78.1 | 859370.17 | 859370.17 | 88.1 | 14 | Data Quality Improvement 21
P-021 | 2026-09-01 | 88 | 86.9 | 945307.18 | 945307.18 | 95.1 | 10 | Data Quality Improvement 21
P-021 | 2026-10-01 | 96 | 97.8 | 1031244.2 | 1031244.2 | 79.2 | 5 | Data Quality Improvement 21
P-022 | 2025-11-01 | 8 | 3.4 | 101439.97 | 104577.74 | 96.1 | 5 | Data Quality Improvement 22
P-022 | 2025-12-01 | 16 | 0 | 202879.93 | 228837.61 | 87.8 | 4 | Data Quality Improvement 22
P-022 | 2026-01-01 | 24 | 19.4 | 304319.9 | 323059.58 | 96.9 | 19 | Data Quality Improvement 22
P-022 | 2026-02-01 | 32 | 25.1 | 405759.86 | 454657.06 | 79.3 | 28 | Data Quality Improvement 22
P-022 | 2026-03-01 | 40 | 28.1 | 507199.83 | 586615.83 | 86.6 | 5 | Data Quality Improvement 22
P-022 | 2026-04-01 | 48 | 34.8 | 608639.79 | 694780.4 | 98.4 | 24 | Data Quality Improvement 22
P-022 | 2026-05-01 | 56 | 48.2 | 710079.76 | 783288.87 | 78 | 5 | Data Quality Improvement 22
P-022 | 2026-06-01 | 64 | 56.8 | 811519.72 | 861405.32 | 96.2 | 21 | Data Quality Improvement 22
P-022 | 2026-07-01 | 72 | 55.1 | 912959.69 | 1023113.92 | 79.3 | 7 | Data Quality Improvement 22
P-022 | 2026-08-01 | 80 | 75.5 | 1014399.66 | 1150394.92 | 96.8 | 3 | Data Quality Improvement 22
P-022 | 2026-09-01 | 88 | 77.4 | 1115839.62 | 1141390.33 | 84.5 | 4 | Data Quality Improvement 22
P-022 | 2026-10-01 | 96 | 81.4 | 1217279.59 | 1285865.98 | 96.3 | 26 | Data Quality Improvement 22
P-023 | 2025-11-01 | 8 | 9.6 | 24457.07 | 24457.07 | 96.4 | 4 | Supplier Performance Improvement 23
P-023 | 2025-12-01 | 16 | 17.7 | 48914.15 | 48914.15 | 78.2 | 5 | Supplier Performance Improvement 23
P-023 | 2026-01-01 | 24 | 24.2 | 73371.22 | 73371.22 | 86.7 | 11 | Supplier Performance Improvement 23
P-023 | 2026-02-01 | 32 | 30 | 97828.29 | 97828.29 | 81.7 | 19 | Supplier Performance Improvement 23
P-023 | 2026-03-01 | 40 | 38.6 | 122285.36 | 122285.36 | 84.4 | 4 | Supplier Performance Improvement 23
P-023 | 2026-04-01 | 48 | 49.7 | 146742.44 | 146742.44 | 98.4 | 14 | Supplier Performance Improvement 23
P-023 | 2026-05-01 | 56 | 54.3 | 171199.51 | 171199.51 | 97.1 | 9 | Supplier Performance Improvement 23
P-023 | 2026-06-01 | 64 | 62.4 | 195656.58 | 195656.58 | 94.7 | 14 | Supplier Performance Improvement 23
P-023 | 2026-07-01 | 72 | 73.3 | 220113.66 | 220113.66 | 86.5 | 10 | Supplier Performance Improvement 23
P-023 | 2026-08-01 | 80 | 80.4 | 244570.73 | 244570.73 | 84.1 | 7 | Supplier Performance Improvement 23
P-023 | 2026-09-01 | 88 | 86 | 269027.8 | 269027.8 | 98.7 | 14 | Supplier Performance Improvement 23
P-023 | 2026-10-01 | 96 | 95.6 | 293484.87 | 293484.87 | 82.4 | 2 | Supplier Performance Improvement 23
P-024 | 2024-11-01 | 8 | 7.2 | 199126.64 | 199126.64 | 82 | 21 | Knowledge Management 24
P-024 | 2024-12-01 | 16 | 15.2 | 398253.27 | 398253.27 | 79.6 | 6 | Knowledge Management 24
P-024 | 2025-01-01 | 24 | 22.4 | 597379.91 | 597379.91 | 80.5 | 11 | Knowledge Management 24
P-024 | 2025-02-01 | 32 | 30.4 | 796506.54 | 796506.54 | 84.8 | 15 | Knowledge Management 24
P-024 | 2025-03-01 | 40 | 38.2 | 995633.18 | 995633.18 | 98.9 | 28 | Knowledge Management 24
P-024 | 2025-04-01 | 48 | 46.1 | 1194759.82 | 1194759.82 | 85.1 | 19 | Knowledge Management 24
P-024 | 2025-05-01 | 56 | 54.3 | 1393886.45 | 1393886.45 | 80.6 | 16 | Knowledge Management 24
P-024 | 2025-06-01 | 64 | 64.3 | 1593013.09 | 1593013.09 | 89.8 | 25 | Knowledge Management 24
P-024 | 2025-07-01 | 72 | 72.7 | 1792139.72 | 1792139.72 | 81.2 | 16 | Knowledge Management 24
P-024 | 2025-08-01 | 80 | 78.6 | 1991266.36 | 1991266.36 | 78.5 | 9 | Knowledge Management 24
P-024 | 2025-09-01 | 88 | 86.6 | 2190393 | 2190393 | 87.2 | 5 | Knowledge Management 24
P-024 | 2025-10-01 | 96 | 96 | 2389519.63 | 2389519.63 | 97 | 8 | Knowledge Management 24
P-025 | 2025-01-01 | 8 | 9.9 | 448208.18 | 448208.18 | 79.5 | 3 | Knowledge Management 25
P-025 | 2025-02-01 | 16 | 15.8 | 896416.36 | 896416.36 | 97.6 | 27 | Knowledge Management 25
P-025 | 2025-03-01 | 24 | 24.6 | 1344624.54 | 1344624.54 | 97.9 | 18 | Knowledge Management 25
P-025 | 2025-04-01 | 32 | 30.3 | 1792832.71 | 1792832.71 | 81.1 | 12 | Knowledge Management 25
P-025 | 2025-05-01 | 40 | 39.4 | 2241040.89 | 2241040.89 | 85.2 | 25 | Knowledge Management 25
P-025 | 2025-06-01 | 48 | 47.4 | 2689249.07 | 2689249.07 | 92.4 | 18 | Knowledge Management 25
P-025 | 2025-07-01 | 56 | 55.1 | 3137457.25 | 3137457.25 | 89.9 | 18 | Knowledge Management 25
P-025 | 2025-08-01 | 64 | 62.4 | 3585665.43 | 3585665.43 | 84.3 | 13 | Knowledge Management 25
P-025 | 2025-09-01 | 72 | 73.7 | 4033873.61 | 4033873.61 | 82.5 | 21 | Knowledge Management 25
P-025 | 2025-10-01 | 80 | 79.4 | 4482081.78 | 4482081.78 | 98.6 | 6 | Knowledge Management 25
P-025 | 2025-11-01 | 88 | 86 | 4930289.96 | 4930289.96 | 78.3 | 5 | Knowledge Management 25
P-025 | 2025-12-01 | 96 | 94.7 | 5378498.14 | 5378498.14 | 97.9 | 10 | Knowledge Management 25
P-026 | 2026-01-01 | 8 | 8.4 | 412556.72 | 412556.72 | 82.4 | 12 | Training Digitization 26
P-026 | 2026-02-01 | 16 | 16.9 | 825113.44 | 825113.44 | 80.2 | 28 | Training Digitization 26
P-026 | 2026-03-01 | 24 | 22.3 | 1237670.17 | 1237670.17 | 81.2 | 13 | Training Digitization 26
P-026 | 2026-04-01 | 32 | 33.2 | 1650226.89 | 1650226.89 | 89.9 | 20 | Training Digitization 26
P-026 | 2026-05-01 | 40 | 41.2 | 2062783.61 | 2062783.61 | 97.8 | 2 | Training Digitization 26
P-026 | 2026-06-01 | 48 | 49.1 | 2475340.33 | 2475340.33 | 98.8 | 16 | Training Digitization 26
P-026 | 2026-07-01 | 56 | 57.8 | 2887897.06 | 2887897.06 | 83.3 | 20 | Training Digitization 26
P-026 | 2026-08-01 | 64 | 64.5 | 3300453.78 | 3300453.78 | 91.9 | 14 | Training Digitization 26
P-026 | 2026-09-01 | 72 | 71.9 | 3713010.5 | 3713010.5 | 83.3 | 14 | Training Digitization 26
P-026 | 2026-10-01 | 80 | 78.7 | 4125567.22 | 4125567.22 | 80 | 24 | Training Digitization 26
P-026 | 2026-11-01 | 88 | 89.7 | 4538123.95 | 4538123.95 | 98 | 22 | Training Digitization 26
P-026 | 2026-12-01 | 96 | 96.6 | 4950680.67 | 4950680.67 | 82.9 | 18 | Training Digitization 26
P-027 | 2026-03-01 | 8 | 9 | 465610.41 | 465610.41 | 93.4 | 12 | Supplier Performance Improvement 27
P-027 | 2026-04-01 | 16 | 17.9 | 931220.82 | 931220.82 | 88.4 | 17 | Supplier Performance Improvement 27
P-027 | 2026-05-01 | 24 | 25.4 | 1396831.23 | 1396831.23 | 95.7 | 17 | Supplier Performance Improvement 27
P-027 | 2026-06-01 | 32 | 30.8 | 1862441.64 | 1862441.64 | 89.7 | 15 | Supplier Performance Improvement 27
P-027 | 2026-07-01 | 40 | 39.2 | 2328052.04 | 2328052.04 | 80.1 | 17 | Supplier Performance Improvement 27
P-027 | 2026-08-01 | 48 | 47.1 | 2793662.45 | 2793662.45 | 82.1 | 12 | Supplier Performance Improvement 27
P-027 | 2026-09-01 | 56 | 54.8 | 3259272.86 | 3259272.86 | 82 | 6 | Supplier Performance Improvement 27
P-027 | 2026-10-01 | 64 | 64.6 | 3724883.27 | 3724883.27 | 93.8 | 5 | Supplier Performance Improvement 27
P-027 | 2026-11-01 | 72 | 70.7 | 4190493.68 | 4190493.68 | 90.7 | 4 | Supplier Performance Improvement 27
P-027 | 2026-12-01 | 80 | 79.6 | 4656104.09 | 4656104.09 | 97.6 | 9 | Supplier Performance Improvement 27
P-027 | 2027-01-01 | 88 | 88.3 | 5121714.5 | 5121714.5 | 96.7 | 4 | Supplier Performance Improvement 27
P-027 | 2027-02-01 | 96 | 95.5 | 5587324.91 | 5587324.91 | 78.9 | 3 | Supplier Performance Improvement 27
P-028 | 2026-04-01 | 8 | 7.2 | 352668.99 | 352668.99 | 81.7 | 28 | Document Modernization 28
P-028 | 2026-05-01 | 16 | 15.2 | 705337.99 | 705337.99 | 83.9 | 12 | Document Modernization 28
P-028 | 2026-06-01 | 24 | 23.5 | 1058006.98 | 1058006.98 | 91.1 | 21 | Document Modernization 28
P-028 | 2026-07-01 | 32 | 31.5 | 1410675.97 | 1410675.97 | 84.1 | 7 | Document Modernization 28
P-028 | 2026-08-01 | 40 | 38.2 | 1763344.96 | 1763344.96 | 90.3 | 18 | Document Modernization 28
P-028 | 2026-09-01 | 48 | 48.4 | 2116013.96 | 2116013.96 | 80.6 | 7 | Document Modernization 28
P-028 | 2026-10-01 | 56 | 56.6 | 2468682.95 | 2468682.95 | 81.2 | 6 | Document Modernization 28
P-028 | 2026-11-01 | 64 | 64.6 | 2821351.94 | 2821351.94 | 95 | 3 | Document Modernization 28
P-028 | 2026-12-01 | 72 | 71.1 | 3174020.94 | 3174020.94 | 80.4 | 28 | Document Modernization 28
P-028 | 2027-01-01 | 80 | 81.2 | 3526689.93 | 3526689.93 | 84.6 | 12 | Document Modernization 28
P-028 | 2027-02-01 | 88 | 89.5 | 3879358.92 | 3879358.92 | 81.5 | 10 | Document Modernization 28
P-028 | 2027-03-01 | 96 | 96.7 | 4232027.91 | 4232027.91 | 88.7 | 9 | Document Modernization 28

## risks
risk_id | project_id | risk_category | risk_description | probability | impact | exposure_score | owner_employee_id | mitigation_plan | target_date | status | project_name
R-0001 | P-001 | DATA | Conflicting document versions may cause the agent to cite an unapproved instruction. | 5 | 5 | 25 | E-002 | Filter retrieval by approval status and test against superseded and draft documents. | 2026-09-08 | OPEN | Enterprise Knowledge and Risk Intelligence Pilot
R-0002 | P-001 | GOVERNANCE | High-exposure AI workflow risk has no assigned owner. | 4 | 5 | 20 |  | Assign owner and define a mandatory human approval gate. | 2026-08-15 | OPEN | Enterprise Knowledge and Risk Intelligence Pilot
R-0003 | P-025 | COST | Data quality may delay analytics validation. | 3 | 4 | 12 | E-053 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-15 | CLOSED | Knowledge Management 25
R-0004 | P-002 | TECHNOLOGY | Resource availability may affect delivery schedule. | 2 | 4 | 8 | E-066 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-28 | ACCEPTED | Risk Reporting Automation 02
R-0005 | P-028 | QUALITY | Supplier dependency may increase lead time. | 1 | 3 | 3 | E-207 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-22 | ACCEPTED | Document Modernization 28
R-0006 | P-006 | DATA | Supplier dependency may increase lead time. | 3 | 4 | 12 | E-143 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-09 | OPEN | Analytics Enablement 06
R-0007 | P-028 | DATA | AI response quality may be insufficient without evaluation data. | 3 | 4 | 12 | E-173 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-08 | OPEN | Document Modernization 28
R-0008 | P-028 | PEOPLE | Current document version may be unclear to project users. | 3 | 2 | 6 | E-062 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-08 | CLOSED | Document Modernization 28
R-0009 | P-023 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 5 | 4 | 20 | E-152 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-02 | MITIGATING | Supplier Performance Improvement 23
R-0010 | P-020 | SCHEDULE | Required stakeholder review may not complete before milestone. | 3 | 1 | 3 | E-213 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-05 | MITIGATING | Training Digitization 20
R-0011 | P-006 | DATA | AI response quality may be insufficient without evaluation data. | 4 | 1 | 4 | E-223 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-23 | CLOSED | Analytics Enablement 06
R-0012 | P-005 | SCHEDULE | Supplier dependency may increase lead time. | 3 | 3 | 9 | E-215 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-07 | CLOSED | Maintenance Planning Enhancement 05
R-0013 | P-014 | QUALITY | Current document version may be unclear to project users. | 3 | 4 | 12 | E-148 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-16 | MITIGATING | Analytics Enablement 14
R-0014 | P-005 | SCHEDULE | Current document version may be unclear to project users. | 1 | 1 | 1 | E-196 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-22 | CLOSED | Maintenance Planning Enhancement 05
R-0015 | P-017 | TECHNOLOGY | Required stakeholder review may not complete before milestone. | 2 | 4 | 8 | E-148 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-06 | MITIGATING | Analytics Enablement 17
R-0016 | P-012 | QUALITY | Resource availability may affect delivery schedule. | 5 | 5 | 25 | E-194 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-30 | MITIGATING | Document Modernization 12
R-0017 | P-024 | SCHEDULE | Data quality may delay analytics validation. | 2 | 2 | 4 | E-140 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-25 | MITIGATING | Knowledge Management 24
R-0018 | P-028 | PEOPLE | Data quality may delay analytics validation. | 2 | 2 | 4 | E-145 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-04 | OPEN | Document Modernization 28
R-0019 | P-006 | SCHEDULE | Current document version may be unclear to project users. | 5 | 2 | 10 | E-216 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-02 | MITIGATING | Analytics Enablement 06
R-0020 | P-021 | TECHNOLOGY | Current document version may be unclear to project users. | 5 | 4 | 20 | E-034 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-21 | MITIGATING | Data Quality Improvement 21
R-0021 | P-016 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 2 | 3 | 6 | E-058 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-11 | OPEN | Data Quality Improvement 16
R-0022 | P-027 | COST | Current document version may be unclear to project users. | 1 | 4 | 4 | E-222 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-25 | MITIGATING | Supplier Performance Improvement 27
R-0023 | P-022 | QUALITY | Current document version may be unclear to project users. | 1 | 5 | 5 | E-155 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-10 | MITIGATING | Data Quality Improvement 22
R-0024 | P-027 | SCHEDULE | Resource availability may affect delivery schedule. | 3 | 4 | 12 | E-059 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-02 | MITIGATING | Supplier Performance Improvement 27
R-0025 | P-010 | PEOPLE | Required stakeholder review may not complete before milestone. | 3 | 2 | 6 | E-118 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-28 | OPEN | Document Modernization 10
R-0026 | P-008 | COST | Supplier dependency may increase lead time. | 4 | 3 | 12 | E-214 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-11 | CLOSED | Data Quality Improvement 08
R-0027 | P-009 | PEOPLE | Required stakeholder review may not complete before milestone. | 5 | 2 | 10 | E-204 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-13 | MITIGATING | Training Digitization 09
R-0028 | P-019 | COST | Data quality may delay analytics validation. | 2 | 4 | 8 | E-087 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-25 | OPEN | Maintenance Planning Enhancement 19
R-0029 | P-022 | COST | Data quality may delay analytics validation. | 4 | 5 | 20 | E-211 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-16 | OPEN | Data Quality Improvement 22
R-0030 | P-019 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 3 | 5 | 15 | E-008 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-07 | OPEN | Maintenance Planning Enhancement 19
R-0031 | P-007 | QUALITY | Resource availability may affect delivery schedule. | 4 | 5 | 20 | E-062 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-09 | MITIGATING | Analytics Enablement 07
R-0032 | P-017 | PEOPLE | Resource availability may affect delivery schedule. | 1 | 3 | 3 | E-044 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-09 | MITIGATING | Analytics Enablement 17
R-0033 | P-004 | QUALITY | Current document version may be unclear to project users. | 1 | 5 | 5 | E-038 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-15 | OPEN | Knowledge Management 04
R-0034 | P-023 | PEOPLE | AI response quality may be insufficient without evaluation data. | 4 | 5 | 20 | E-157 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-14 | MITIGATING | Supplier Performance Improvement 23
R-0035 | P-007 | SCHEDULE | Resource availability may affect delivery schedule. | 2 | 5 | 10 | E-163 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-01 | MITIGATING | Analytics Enablement 07
R-0036 | P-013 | PEOPLE | Resource availability may affect delivery schedule. | 4 | 4 | 16 | E-077 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-21 | ACCEPTED | Document Modernization 13
R-0037 | P-010 | COST | Resource availability may affect delivery schedule. | 2 | 5 | 10 | E-058 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-20 | ACCEPTED | Document Modernization 10
R-0038 | P-025 | COST | Required stakeholder review may not complete before milestone. | 2 | 2 | 4 | E-210 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-12 | MITIGATING | Knowledge Management 25
R-0039 | P-024 | SCHEDULE | Current document version may be unclear to project users. | 5 | 5 | 25 | E-018 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-12 | MITIGATING | Knowledge Management 24
R-0040 | P-004 | DATA | AI response quality may be insufficient without evaluation data. | 1 | 4 | 4 | E-111 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-25 | MITIGATING | Knowledge Management 04
R-0041 | P-004 | QUALITY | Data quality may delay analytics validation. | 5 | 1 | 5 | E-040 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-05 | CLOSED | Knowledge Management 04
R-0042 | P-027 | SCHEDULE | Current document version may be unclear to project users. | 5 | 2 | 10 | E-224 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-03 | CLOSED | Supplier Performance Improvement 27
R-0043 | P-025 | DATA | Supplier dependency may increase lead time. | 2 | 3 | 6 | E-185 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-09 | MITIGATING | Knowledge Management 25
R-0044 | P-013 | SCHEDULE | Resource availability may affect delivery schedule. | 1 | 4 | 4 | E-219 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-23 | OPEN | Document Modernization 13
R-0045 | P-022 | TECHNOLOGY | Resource availability may affect delivery schedule. | 1 | 3 | 3 | E-192 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-18 | OPEN | Data Quality Improvement 22
R-0046 | P-018 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 5 | 2 | 10 | E-239 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-26 | CLOSED | Document Modernization 18
R-0047 | P-019 | QUALITY | AI response quality may be insufficient without evaluation data. | 1 | 4 | 4 | E-121 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-22 | OPEN | Maintenance Planning Enhancement 19
R-0048 | P-023 | PEOPLE | Supplier dependency may increase lead time. | 1 | 4 | 4 | E-208 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-24 | MITIGATING | Supplier Performance Improvement 23
R-0049 | P-014 | DATA | Resource availability may affect delivery schedule. | 2 | 4 | 8 | E-226 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-12 | CLOSED | Analytics Enablement 14
R-0050 | P-017 | PEOPLE | AI response quality may be insufficient without evaluation data. | 5 | 4 | 20 | E-103 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-31 | OPEN | Analytics Enablement 17
R-0051 | P-024 | TECHNOLOGY | Data quality may delay analytics validation. | 4 | 3 | 12 | E-213 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-09 | ACCEPTED | Knowledge Management 24
R-0052 | P-005 | COST | Data quality may delay analytics validation. | 4 | 5 | 20 | E-065 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-31 | MITIGATING | Maintenance Planning Enhancement 05
R-0053 | P-025 | COST | Current document version may be unclear to project users. | 1 | 5 | 5 | E-049 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-07 | MITIGATING | Knowledge Management 25
R-0054 | P-019 | DATA | Required stakeholder review may not complete before milestone. | 4 | 3 | 12 | E-112 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-08 | OPEN | Maintenance Planning Enhancement 19
R-0055 | P-004 | QUALITY | Required stakeholder review may not complete before milestone. | 5 | 1 | 5 | E-177 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-25 | MITIGATING | Knowledge Management 04
R-0056 | P-027 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 3 | 3 | 9 | E-138 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-03 | CLOSED | Supplier Performance Improvement 27
R-0057 | P-016 | TECHNOLOGY | Resource availability may affect delivery schedule. | 4 | 4 | 16 | E-019 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-20 | OPEN | Data Quality Improvement 16
R-0058 | P-027 | COST | Supplier dependency may increase lead time. | 2 | 4 | 8 | E-098 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-26 | MITIGATING | Supplier Performance Improvement 27
R-0059 | P-004 | PEOPLE | Current document version may be unclear to project users. | 1 | 1 | 1 | E-084 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-12 | OPEN | Knowledge Management 04
R-0060 | P-023 | PEOPLE | Required stakeholder review may not complete before milestone. | 5 | 2 | 10 | E-026 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-21 | OPEN | Supplier Performance Improvement 23
R-0061 | P-005 | TECHNOLOGY | Required stakeholder review may not complete before milestone. | 2 | 2 | 4 | E-068 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-22 | MITIGATING | Maintenance Planning Enhancement 05
R-0062 | P-012 | QUALITY | Current document version may be unclear to project users. | 2 | 1 | 2 | E-199 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-05 | OPEN | Document Modernization 12
R-0063 | P-009 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 5 | 5 | 25 | E-196 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-17 | ACCEPTED | Training Digitization 09
R-0064 | P-012 | COST | Supplier dependency may increase lead time. | 1 | 2 | 2 | E-140 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-26 | MITIGATING | Document Modernization 12
R-0065 | P-026 | DATA | Resource availability may affect delivery schedule. | 3 | 3 | 9 | E-132 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-09 | ACCEPTED | Training Digitization 26
R-0066 | P-006 | COST | Data quality may delay analytics validation. | 2 | 3 | 6 | E-080 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-05 | ACCEPTED | Analytics Enablement 06
R-0067 | P-006 | QUALITY | Data quality may delay analytics validation. | 1 | 4 | 4 | E-132 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-07 | CLOSED | Analytics Enablement 06
R-0068 | P-018 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 2 | 3 | 6 | E-148 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-20 | CLOSED | Document Modernization 18
R-0069 | P-025 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 2 | 5 | 10 | E-101 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-22 | MITIGATING | Knowledge Management 25
R-0070 | P-020 | SCHEDULE | Data quality may delay analytics validation. | 2 | 2 | 4 | E-189 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-04 | OPEN | Training Digitization 20
R-0071 | P-014 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 5 | 3 | 15 | E-178 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-20 | OPEN | Analytics Enablement 14
R-0072 | P-013 | SCHEDULE | Required stakeholder review may not complete before milestone. | 3 | 1 | 3 | E-099 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-04 | MITIGATING | Document Modernization 13
R-0073 | P-011 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 1 | 5 | 5 | E-009 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-27 | CLOSED | Maintenance Planning Enhancement 11
R-0074 | P-007 | PEOPLE | AI response quality may be insufficient without evaluation data. | 3 | 5 | 15 | E-040 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-29 | CLOSED | Analytics Enablement 07
R-0075 | P-002 | QUALITY | Required stakeholder review may not complete before milestone. | 3 | 4 | 12 | E-207 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-20 | OPEN | Risk Reporting Automation 02
R-0076 | P-005 | QUALITY | Supplier dependency may increase lead time. | 1 | 4 | 4 | E-135 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-26 | OPEN | Maintenance Planning Enhancement 05
R-0077 | P-021 | DATA | Data quality may delay analytics validation. | 4 | 1 | 4 | E-104 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-17 | OPEN | Data Quality Improvement 21
R-0078 | P-013 | COST | Data quality may delay analytics validation. | 2 | 2 | 4 | E-022 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-27 | CLOSED | Document Modernization 13
R-0079 | P-011 | PEOPLE | Data quality may delay analytics validation. | 5 | 4 | 20 | E-068 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-05 | MITIGATING | Maintenance Planning Enhancement 11
R-0080 | P-009 | QUALITY | Current document version may be unclear to project users. | 2 | 1 | 2 | E-095 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-13 | OPEN | Training Digitization 09
R-0081 | P-015 | COST | Data quality may delay analytics validation. | 2 | 4 | 8 | E-143 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-29 | ACCEPTED | Document Modernization 15
R-0082 | P-009 | TECHNOLOGY | Data quality may delay analytics validation. | 1 | 1 | 1 | E-133 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-09 | CLOSED | Training Digitization 09
R-0083 | P-003 | SCHEDULE | Data quality may delay analytics validation. | 2 | 2 | 4 | E-085 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-23 | OPEN | Training Digitization 03
R-0084 | P-021 | COST | Supplier dependency may increase lead time. | 2 | 5 | 10 | E-140 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-30 | CLOSED | Data Quality Improvement 21
R-0085 | P-018 | TECHNOLOGY | Supplier dependency may increase lead time. | 1 | 4 | 4 | E-146 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-09 | MITIGATING | Document Modernization 18
R-0086 | P-019 | QUALITY | AI response quality may be insufficient without evaluation data. | 2 | 5 | 10 | E-188 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-10 | OPEN | Maintenance Planning Enhancement 19
R-0087 | P-026 | PEOPLE | Required stakeholder review may not complete before milestone. | 1 | 1 | 1 | E-031 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-01 | CLOSED | Training Digitization 26
R-0088 | P-012 | COST | AI response quality may be insufficient without evaluation data. | 1 | 5 | 5 | E-075 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-06 | OPEN | Document Modernization 12
R-0089 | P-017 | COST | AI response quality may be insufficient without evaluation data. | 1 | 4 | 4 | E-193 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-28 | CLOSED | Analytics Enablement 17
R-0090 | P-002 | PEOPLE | AI response quality may be insufficient without evaluation data. | 1 | 1 | 1 | E-143 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-17 | CLOSED | Risk Reporting Automation 02
R-0091 | P-004 | COST | Data quality may delay analytics validation. | 2 | 5 | 10 | E-043 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-06-29 | CLOSED | Knowledge Management 04
R-0092 | P-020 | COST | Supplier dependency may increase lead time. | 1 | 4 | 4 | E-217 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-19 | OPEN | Training Digitization 20
R-0093 | P-027 | PEOPLE | Resource availability may affect delivery schedule. | 5 | 1 | 5 | E-115 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-08 | OPEN | Supplier Performance Improvement 27
R-0094 | P-026 | COST | Required stakeholder review may not complete before milestone. | 5 | 3 | 15 | E-118 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-23 | OPEN | Training Digitization 26
R-0095 | P-017 | COST | Data quality may delay analytics validation. | 4 | 3 | 12 | E-072 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-31 | CLOSED | Analytics Enablement 17
R-0096 | P-022 | QUALITY | AI response quality may be insufficient without evaluation data. | 5 | 4 | 20 | E-222 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-06-28 | MITIGATING | Data Quality Improvement 22
R-0097 | P-018 | COST | Current document version may be unclear to project users. | 4 | 5 | 20 | E-029 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-08 | CLOSED | Document Modernization 18
R-0098 | P-020 | DATA | AI response quality may be insufficient without evaluation data. | 5 | 2 | 10 | E-084 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-14 | MITIGATING | Training Digitization 20
R-0099 | P-010 | PEOPLE | Data quality may delay analytics validation. | 1 | 3 | 3 | E-146 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-03 | MITIGATING | Document Modernization 10
R-0100 | P-020 | TECHNOLOGY | Current document version may be unclear to project users. | 2 | 5 | 10 | E-226 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-14 | OPEN | Training Digitization 20
R-0101 | P-027 | COST | Current document version may be unclear to project users. | 5 | 2 | 10 | E-179 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-25 | MITIGATING | Supplier Performance Improvement 27
R-0102 | P-006 | TECHNOLOGY | Data quality may delay analytics validation. | 5 | 5 | 25 | E-122 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-02 | CLOSED | Analytics Enablement 06
R-0103 | P-026 | QUALITY | Current document version may be unclear to project users. | 2 | 5 | 10 | E-180 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-27 | OPEN | Training Digitization 26
R-0104 | P-020 | DATA | Required stakeholder review may not complete before milestone. | 3 | 3 | 9 | E-139 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-07 | CLOSED | Training Digitization 20
R-0105 | P-001 | DATA | Current document version may be unclear to project users. | 2 | 2 | 4 | E-155 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-16 | OPEN | Enterprise Knowledge and Risk Intelligence Pilot
R-0106 | P-001 | DATA | Supplier dependency may increase lead time. | 1 | 3 | 3 | E-009 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-08 | MITIGATING | Enterprise Knowledge and Risk Intelligence Pilot
R-0107 | P-021 | QUALITY | Data quality may delay analytics validation. | 5 | 5 | 25 | E-144 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-13 | ACCEPTED | Data Quality Improvement 21
R-0108 | P-025 | QUALITY | Required stakeholder review may not complete before milestone. | 1 | 5 | 5 | E-004 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-22 | MITIGATING | Knowledge Management 25
R-0109 | P-010 | DATA | Supplier dependency may increase lead time. | 1 | 2 | 2 | E-236 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-06 | OPEN | Document Modernization 10
R-0110 | P-022 | SCHEDULE | Data quality may delay analytics validation. | 2 | 4 | 8 | E-214 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-08 | MITIGATING | Data Quality Improvement 22
R-0111 | P-009 | COST | AI response quality may be insufficient without evaluation data. | 5 | 2 | 10 | E-077 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-03 | MITIGATING | Training Digitization 09
R-0112 | P-022 | QUALITY | Data quality may delay analytics validation. | 4 | 4 | 16 | E-022 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-08 | CLOSED | Data Quality Improvement 22
R-0113 | P-006 | PEOPLE | Supplier dependency may increase lead time. | 3 | 1 | 3 | E-057 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-23 | CLOSED | Analytics Enablement 06
R-0114 | P-006 | COST | Required stakeholder review may not complete before milestone. | 4 | 3 | 12 | E-003 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-20 | MITIGATING | Analytics Enablement 06
R-0115 | P-028 | COST | Required stakeholder review may not complete before milestone. | 3 | 3 | 9 | E-229 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-25 | CLOSED | Document Modernization 28
R-0116 | P-014 | TECHNOLOGY | Current document version may be unclear to project users. | 5 | 2 | 10 | E-224 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-07 | OPEN | Analytics Enablement 14
R-0117 | P-005 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 4 | 4 | 16 | E-079 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-28 | MITIGATING | Maintenance Planning Enhancement 05
R-0118 | P-008 | PEOPLE | Supplier dependency may increase lead time. | 1 | 5 | 5 | E-032 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-02 | MITIGATING | Data Quality Improvement 08
R-0119 | P-018 | QUALITY | Current document version may be unclear to project users. | 3 | 5 | 15 | E-064 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-25 | MITIGATING | Document Modernization 18
R-0120 | P-009 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 3 | 3 | 9 | E-212 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-15 | OPEN | Training Digitization 09
R-0121 | P-002 | PEOPLE | Supplier dependency may increase lead time. | 5 | 4 | 20 | E-207 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-28 | MITIGATING | Risk Reporting Automation 02
R-0122 | P-020 | QUALITY | Supplier dependency may increase lead time. | 2 | 2 | 4 | E-195 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-16 | ACCEPTED | Training Digitization 20
R-0123 | P-019 | COST | Supplier dependency may increase lead time. | 4 | 2 | 8 | E-024 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-28 | ACCEPTED | Maintenance Planning Enhancement 19
R-0124 | P-006 | COST | Data quality may delay analytics validation. | 1 | 3 | 3 | E-121 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-10 | MITIGATING | Analytics Enablement 06
R-0125 | P-018 | DATA | Current document version may be unclear to project users. | 5 | 4 | 20 | E-205 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-13 | MITIGATING | Document Modernization 18
R-0126 | P-007 | TECHNOLOGY | Current document version may be unclear to project users. | 5 | 3 | 15 | E-164 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-16 | MITIGATING | Analytics Enablement 07
R-0127 | P-028 | COST | Data quality may delay analytics validation. | 2 | 5 | 10 | E-126 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-27 | MITIGATING | Document Modernization 28
R-0128 | P-005 | DATA | Supplier dependency may increase lead time. | 3 | 3 | 9 | E-137 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-25 | CLOSED | Maintenance Planning Enhancement 05
R-0129 | P-001 | QUALITY | Supplier dependency may increase lead time. | 4 | 4 | 16 | E-009 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-10 | ACCEPTED | Enterprise Knowledge and Risk Intelligence Pilot
R-0130 | P-013 | QUALITY | Current document version may be unclear to project users. | 2 | 4 | 8 | E-182 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-15 | MITIGATING | Document Modernization 13
R-0131 | P-011 | COST | Current document version may be unclear to project users. | 3 | 4 | 12 | E-024 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-19 | MITIGATING | Maintenance Planning Enhancement 11
R-0132 | P-010 | SCHEDULE | Supplier dependency may increase lead time. | 1 | 1 | 1 | E-032 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-07 | MITIGATING | Document Modernization 10
R-0133 | P-009 | QUALITY | Current document version may be unclear to project users. | 2 | 4 | 8 | E-180 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-06-27 | CLOSED | Training Digitization 09
R-0134 | P-008 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 1 | 2 | 2 | E-116 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-01 | CLOSED | Data Quality Improvement 08
R-0135 | P-011 | DATA | Supplier dependency may increase lead time. | 4 | 2 | 8 | E-226 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-18 | CLOSED | Maintenance Planning Enhancement 11
R-0136 | P-010 | PEOPLE | Current document version may be unclear to project users. | 5 | 1 | 5 | E-239 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-08 | MITIGATING | Document Modernization 10
R-0137 | P-009 | COST | AI response quality may be insufficient without evaluation data. | 4 | 5 | 20 | E-223 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-07 | MITIGATING | Training Digitization 09
R-0138 | P-025 | PEOPLE | Supplier dependency may increase lead time. | 2 | 5 | 10 | E-207 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-04 | CLOSED | Knowledge Management 25
R-0139 | P-010 | QUALITY | Current document version may be unclear to project users. | 3 | 5 | 15 | E-230 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-24 | CLOSED | Document Modernization 10
R-0140 | P-017 | DATA | Data quality may delay analytics validation. | 5 | 5 | 25 | E-141 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-18 | MITIGATING | Analytics Enablement 17
R-0141 | P-026 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 4 | 3 | 12 | E-214 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-24 | MITIGATING | Training Digitization 26
R-0142 | P-019 | SCHEDULE | Required stakeholder review may not complete before milestone. | 1 | 4 | 4 | E-141 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-15 | MITIGATING | Maintenance Planning Enhancement 19
R-0143 | P-020 | SCHEDULE | Required stakeholder review may not complete before milestone. | 2 | 4 | 8 | E-008 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-17 | OPEN | Training Digitization 20
R-0144 | P-021 | PEOPLE | AI response quality may be insufficient without evaluation data. | 3 | 2 | 6 | E-128 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-29 | CLOSED | Data Quality Improvement 21
R-0145 | P-010 | DATA | Current document version may be unclear to project users. | 5 | 3 | 15 | E-108 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-29 | MITIGATING | Document Modernization 10
R-0146 | P-014 | COST | Required stakeholder review may not complete before milestone. | 3 | 3 | 9 | E-076 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-01 | OPEN | Analytics Enablement 14
R-0147 | P-011 | TECHNOLOGY | Supplier dependency may increase lead time. | 5 | 2 | 10 | E-079 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-12 | CLOSED | Maintenance Planning Enhancement 11
R-0148 | P-001 | SCHEDULE | Data quality may delay analytics validation. | 1 | 1 | 1 | E-026 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-17 | CLOSED | Enterprise Knowledge and Risk Intelligence Pilot
R-0149 | P-012 | DATA | Supplier dependency may increase lead time. | 5 | 3 | 15 | E-106 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-10 | CLOSED | Document Modernization 12
R-0150 | P-004 | COST | Required stakeholder review may not complete before milestone. | 3 | 2 | 6 | E-011 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-08 | OPEN | Knowledge Management 04
R-0151 | P-028 | TECHNOLOGY | Resource availability may affect delivery schedule. | 2 | 5 | 10 | E-005 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-12 | OPEN | Document Modernization 28
R-0152 | P-006 | SCHEDULE | Resource availability may affect delivery schedule. | 5 | 2 | 10 | E-125 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-05 | CLOSED | Analytics Enablement 06
R-0153 | P-014 | SCHEDULE | Data quality may delay analytics validation. | 4 | 4 | 16 | E-119 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-02 | MITIGATING | Analytics Enablement 14
R-0154 | P-015 | DATA | Resource availability may affect delivery schedule. | 3 | 1 | 3 | E-100 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-06 | MITIGATING | Document Modernization 15
R-0155 | P-022 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 2 | 1 | 2 | E-081 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-01 | CLOSED | Data Quality Improvement 22
R-0156 | P-011 | COST | AI response quality may be insufficient without evaluation data. | 3 | 3 | 9 | E-220 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-24 | MITIGATING | Maintenance Planning Enhancement 11
R-0157 | P-021 | COST | Data quality may delay analytics validation. | 2 | 1 | 2 | E-191 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-05 | OPEN | Data Quality Improvement 21
R-0158 | P-007 | DATA | Resource availability may affect delivery schedule. | 3 | 4 | 12 | E-016 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-03 | MITIGATING | Analytics Enablement 07
R-0159 | P-005 | PEOPLE | Resource availability may affect delivery schedule. | 1 | 3 | 3 | E-064 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-26 | MITIGATING | Maintenance Planning Enhancement 05
R-0160 | P-002 | TECHNOLOGY | Current document version may be unclear to project users. | 4 | 4 | 16 | E-028 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-17 | OPEN | Risk Reporting Automation 02
R-0161 | P-001 | DATA | Supplier dependency may increase lead time. | 5 | 1 | 5 | E-206 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-30 | OPEN | Enterprise Knowledge and Risk Intelligence Pilot
R-0162 | P-019 | TECHNOLOGY | Current document version may be unclear to project users. | 1 | 5 | 5 | E-079 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-14 | OPEN | Maintenance Planning Enhancement 19
R-0163 | P-003 | TECHNOLOGY | Resource availability may affect delivery schedule. | 5 | 2 | 10 | E-147 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-22 | OPEN | Training Digitization 03
R-0164 | P-006 | DATA | Required stakeholder review may not complete before milestone. | 2 | 3 | 6 | E-029 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-19 | MITIGATING | Analytics Enablement 06
R-0165 | P-024 | DATA | Resource availability may affect delivery schedule. | 4 | 5 | 20 | E-063 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-16 | MITIGATING | Knowledge Management 24
R-0166 | P-021 | DATA | Supplier dependency may increase lead time. | 5 | 4 | 20 | E-011 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-05 | CLOSED | Data Quality Improvement 21
R-0167 | P-022 | DATA | Current document version may be unclear to project users. | 3 | 5 | 15 | E-050 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-07 | CLOSED | Data Quality Improvement 22
R-0168 | P-002 | SCHEDULE | Required stakeholder review may not complete before milestone. | 3 | 1 | 3 | E-082 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-12 | CLOSED | Risk Reporting Automation 02
R-0169 | P-010 | PEOPLE | AI response quality may be insufficient without evaluation data. | 5 | 5 | 25 | E-021 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-01 | OPEN | Document Modernization 10
R-0170 | P-015 | TECHNOLOGY | Supplier dependency may increase lead time. | 5 | 4 | 20 | E-143 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-15 | MITIGATING | Document Modernization 15
R-0171 | P-007 | DATA | Resource availability may affect delivery schedule. | 2 | 4 | 8 | E-153 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-20 | OPEN | Analytics Enablement 07
R-0172 | P-005 | SCHEDULE | Data quality may delay analytics validation. | 4 | 4 | 16 | E-051 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-06-28 | MITIGATING | Maintenance Planning Enhancement 05
R-0173 | P-013 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 2 | 2 | 4 | E-094 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-26 | CLOSED | Document Modernization 13
R-0174 | P-005 | TECHNOLOGY | Current document version may be unclear to project users. | 3 | 2 | 6 | E-035 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-09 | ACCEPTED | Maintenance Planning Enhancement 05
R-0175 | P-016 | SCHEDULE | Current document version may be unclear to project users. | 2 | 2 | 4 | E-124 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-01 | CLOSED | Data Quality Improvement 16
R-0176 | P-018 | COST | Supplier dependency may increase lead time. | 1 | 4 | 4 | E-049 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-13 | ACCEPTED | Document Modernization 18
R-0177 | P-026 | COST | Current document version may be unclear to project users. | 2 | 2 | 4 | E-014 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-12 | CLOSED | Training Digitization 26
R-0178 | P-013 | QUALITY | Supplier dependency may increase lead time. | 4 | 4 | 16 | E-227 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-24 | MITIGATING | Document Modernization 13
R-0179 | P-018 | COST | Current document version may be unclear to project users. | 4 | 3 | 12 | E-109 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-08 | OPEN | Document Modernization 18
R-0180 | P-013 | QUALITY | Current document version may be unclear to project users. | 2 | 3 | 6 | E-141 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-21 | OPEN | Document Modernization 13
R-0181 | P-022 | PEOPLE | Supplier dependency may increase lead time. | 3 | 5 | 15 | E-084 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-18 | ACCEPTED | Data Quality Improvement 22
R-0182 | P-007 | COST | Resource availability may affect delivery schedule. | 5 | 1 | 5 | E-102 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-17 | MITIGATING | Analytics Enablement 07
R-0183 | P-026 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 4 | 5 | 20 | E-073 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-15 | OPEN | Training Digitization 26
R-0184 | P-001 | TECHNOLOGY | Current document version may be unclear to project users. | 1 | 3 | 3 | E-005 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-26 | OPEN | Enterprise Knowledge and Risk Intelligence Pilot
R-0185 | P-006 | COST | Current document version may be unclear to project users. | 5 | 3 | 15 | E-125 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-25 | CLOSED | Analytics Enablement 06
R-0186 | P-001 | TECHNOLOGY | Resource availability may affect delivery schedule. | 5 | 3 | 15 | E-156 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-18 | MITIGATING | Enterprise Knowledge and Risk Intelligence Pilot
R-0187 | P-020 | SCHEDULE | Required stakeholder review may not complete before milestone. | 2 | 1 | 2 | E-027 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-24 | CLOSED | Training Digitization 20
R-0188 | P-002 | QUALITY | AI response quality may be insufficient without evaluation data. | 5 | 2 | 10 | E-133 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-08 | CLOSED | Risk Reporting Automation 02
R-0189 | P-019 | TECHNOLOGY | Current document version may be unclear to project users. | 3 | 4 | 12 | E-061 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-22 | OPEN | Maintenance Planning Enhancement 19
R-0190 | P-022 | PEOPLE | Supplier dependency may increase lead time. | 3 | 1 | 3 | E-159 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-03 | CLOSED | Data Quality Improvement 22
R-0191 | P-016 | QUALITY | AI response quality may be insufficient without evaluation data. | 1 | 3 | 3 | E-070 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-27 | MITIGATING | Data Quality Improvement 16
R-0192 | P-006 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 3 | 5 | 15 | E-097 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-02 | OPEN | Analytics Enablement 06
R-0193 | P-004 | QUALITY | Data quality may delay analytics validation. | 5 | 1 | 5 | E-220 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-02 | CLOSED | Knowledge Management 04
R-0194 | P-010 | QUALITY | Data quality may delay analytics validation. | 4 | 3 | 12 | E-223 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-30 | CLOSED | Document Modernization 10
R-0195 | P-010 | TECHNOLOGY | Resource availability may affect delivery schedule. | 3 | 4 | 12 | E-015 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-27 | MITIGATING | Document Modernization 10
R-0196 | P-025 | DATA | Current document version may be unclear to project users. | 5 | 1 | 5 | E-110 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-04 | ACCEPTED | Knowledge Management 25
R-0197 | P-026 | COST | AI response quality may be insufficient without evaluation data. | 3 | 4 | 12 | E-010 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-27 | CLOSED | Training Digitization 26
R-0198 | P-020 | COST | Current document version may be unclear to project users. | 1 | 5 | 5 | E-213 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-21 | CLOSED | Training Digitization 20
R-0199 | P-001 | SCHEDULE | Supplier dependency may increase lead time. | 4 | 5 | 20 | E-030 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-13 | CLOSED | Enterprise Knowledge and Risk Intelligence Pilot
R-0200 | P-014 | DATA | AI response quality may be insufficient without evaluation data. | 1 | 1 | 1 | E-104 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-31 | ACCEPTED | Analytics Enablement 14
R-0201 | P-016 | PEOPLE | Supplier dependency may increase lead time. | 5 | 2 | 10 | E-155 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-21 | ACCEPTED | Data Quality Improvement 16
R-0202 | P-016 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 1 | 4 | 4 | E-031 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-30 | CLOSED | Data Quality Improvement 16
R-0203 | P-026 | TECHNOLOGY | Current document version may be unclear to project users. | 4 | 3 | 12 | E-158 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-12 | MITIGATING | Training Digitization 26
R-0204 | P-012 | TECHNOLOGY | Required stakeholder review may not complete before milestone. | 2 | 5 | 10 | E-019 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-16 | MITIGATING | Document Modernization 12
R-0205 | P-018 | PEOPLE | Current document version may be unclear to project users. | 4 | 4 | 16 | E-198 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-30 | MITIGATING | Document Modernization 18
R-0206 | P-014 | QUALITY | Resource availability may affect delivery schedule. | 3 | 4 | 12 | E-175 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-09 | MITIGATING | Analytics Enablement 14
R-0207 | P-018 | PEOPLE | Current document version may be unclear to project users. | 4 | 2 | 8 | E-018 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-21 | CLOSED | Document Modernization 18
R-0208 | P-026 | COST | Current document version may be unclear to project users. | 2 | 3 | 6 | E-014 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-25 | CLOSED | Training Digitization 26
R-0209 | P-018 | PEOPLE | AI response quality may be insufficient without evaluation data. | 5 | 1 | 5 | E-129 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-31 | MITIGATING | Document Modernization 18
R-0210 | P-009 | COST | Current document version may be unclear to project users. | 2 | 4 | 8 | E-177 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-19 | CLOSED | Training Digitization 09
R-0211 | P-004 | COST | AI response quality may be insufficient without evaluation data. | 1 | 1 | 1 | E-073 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-24 | OPEN | Knowledge Management 04
R-0212 | P-016 | COST | Resource availability may affect delivery schedule. | 3 | 1 | 3 | E-140 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-26 | CLOSED | Data Quality Improvement 16
R-0213 | P-024 | PEOPLE | Required stakeholder review may not complete before milestone. | 3 | 2 | 6 | E-097 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-15 | CLOSED | Knowledge Management 24
R-0214 | P-015 | COST | Required stakeholder review may not complete before milestone. | 4 | 1 | 4 | E-137 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-21 | MITIGATING | Document Modernization 15
R-0215 | P-013 | QUALITY | Resource availability may affect delivery schedule. | 1 | 2 | 2 | E-225 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-11 | MITIGATING | Document Modernization 13
R-0216 | P-026 | DATA | Current document version may be unclear to project users. | 2 | 1 | 2 | E-031 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-09 | CLOSED | Training Digitization 26
R-0217 | P-022 | QUALITY | Required stakeholder review may not complete before milestone. | 4 | 3 | 12 | E-041 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-29 | OPEN | Data Quality Improvement 22
R-0218 | P-004 | DATA | Supplier dependency may increase lead time. | 4 | 5 | 20 | E-131 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-19 | OPEN | Knowledge Management 04
R-0219 | P-013 | DATA | Required stakeholder review may not complete before milestone. | 5 | 3 | 15 | E-018 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-30 | CLOSED | Document Modernization 13
R-0220 | P-006 | PEOPLE | AI response quality may be insufficient without evaluation data. | 1 | 1 | 1 | E-218 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-16 | MITIGATING | Analytics Enablement 06
R-0221 | P-018 | SCHEDULE | Current document version may be unclear to project users. | 3 | 4 | 12 | E-081 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-09 | OPEN | Document Modernization 18
R-0222 | P-006 | SCHEDULE | Current document version may be unclear to project users. | 2 | 2 | 4 | E-109 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-05 | CLOSED | Analytics Enablement 06
R-0223 | P-014 | DATA | Supplier dependency may increase lead time. | 4 | 2 | 8 | E-054 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-01 | MITIGATING | Analytics Enablement 14
R-0224 | P-002 | PEOPLE | Required stakeholder review may not complete before milestone. | 4 | 1 | 4 | E-232 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-15 | MITIGATING | Risk Reporting Automation 02
R-0225 | P-028 | QUALITY | Current document version may be unclear to project users. | 5 | 2 | 10 | E-045 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-19 | MITIGATING | Document Modernization 28
R-0226 | P-025 | COST | Required stakeholder review may not complete before milestone. | 2 | 2 | 4 | E-044 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-28 | OPEN | Knowledge Management 25
R-0227 | P-028 | COST | Current document version may be unclear to project users. | 4 | 5 | 20 | E-003 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-08 | OPEN | Document Modernization 28
R-0228 | P-004 | TECHNOLOGY | Supplier dependency may increase lead time. | 3 | 5 | 15 | E-147 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-04 | OPEN | Knowledge Management 04
R-0229 | P-027 | COST | Data quality may delay analytics validation. | 5 | 1 | 5 | E-072 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-11 | ACCEPTED | Supplier Performance Improvement 27
R-0230 | P-023 | COST | AI response quality may be insufficient without evaluation data. | 3 | 4 | 12 | E-185 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-11 | MITIGATING | Supplier Performance Improvement 23
R-0231 | P-003 | QUALITY | Required stakeholder review may not complete before milestone. | 4 | 2 | 8 | E-204 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-07 | MITIGATING | Training Digitization 03
R-0232 | P-016 | PEOPLE | Resource availability may affect delivery schedule. | 4 | 5 | 20 | E-080 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-25 | ACCEPTED | Data Quality Improvement 16
R-0233 | P-011 | PEOPLE | Current document version may be unclear to project users. | 1 | 2 | 2 | E-198 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-28 | ACCEPTED | Maintenance Planning Enhancement 11
R-0234 | P-017 | TECHNOLOGY | Resource availability may affect delivery schedule. | 1 | 2 | 2 | E-231 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-05 | OPEN | Analytics Enablement 17
R-0235 | P-003 | DATA | Resource availability may affect delivery schedule. | 5 | 5 | 25 | E-093 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-26 | OPEN | Training Digitization 03
R-0236 | P-012 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 4 | 4 | 16 | E-190 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-20 | OPEN | Document Modernization 12
R-0237 | P-011 | SCHEDULE | Supplier dependency may increase lead time. | 5 | 3 | 15 | E-068 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-14 | ACCEPTED | Maintenance Planning Enhancement 11
R-0238 | P-007 | SCHEDULE | Required stakeholder review may not complete before milestone. | 3 | 3 | 9 | E-108 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-13 | MITIGATING | Analytics Enablement 07
R-0239 | P-022 | QUALITY | Data quality may delay analytics validation. | 2 | 5 | 10 | E-135 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-26 | CLOSED | Data Quality Improvement 22
R-0240 | P-015 | QUALITY | Resource availability may affect delivery schedule. | 3 | 2 | 6 | E-107 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-18 | OPEN | Document Modernization 15
R-0241 | P-008 | DATA | Supplier dependency may increase lead time. | 1 | 3 | 3 | E-235 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-20 | CLOSED | Data Quality Improvement 08
R-0242 | P-017 | COST | Required stakeholder review may not complete before milestone. | 2 | 5 | 10 | E-125 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-19 | OPEN | Analytics Enablement 17
R-0243 | P-025 | TECHNOLOGY | Supplier dependency may increase lead time. | 5 | 3 | 15 | E-110 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-12 | OPEN | Knowledge Management 25
R-0244 | P-015 | TECHNOLOGY | Data quality may delay analytics validation. | 4 | 4 | 16 | E-237 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-09 | OPEN | Document Modernization 15
R-0245 | P-007 | COST | Supplier dependency may increase lead time. | 3 | 3 | 9 | E-117 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-19 | OPEN | Analytics Enablement 07
R-0246 | P-025 | PEOPLE | Current document version may be unclear to project users. | 3 | 3 | 9 | E-193 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-03 | MITIGATING | Knowledge Management 25
R-0247 | P-014 | PEOPLE | Resource availability may affect delivery schedule. | 2 | 4 | 8 | E-111 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-16 | CLOSED | Analytics Enablement 14
R-0248 | P-024 | COST | Required stakeholder review may not complete before milestone. | 4 | 1 | 4 | E-216 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-28 | OPEN | Knowledge Management 24
R-0249 | P-002 | DATA | Required stakeholder review may not complete before milestone. | 3 | 5 | 15 | E-079 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-03 | MITIGATING | Risk Reporting Automation 02
R-0250 | P-004 | PEOPLE | Data quality may delay analytics validation. | 1 | 4 | 4 | E-160 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-11 | OPEN | Knowledge Management 04
R-0251 | P-017 | SCHEDULE | Resource availability may affect delivery schedule. | 2 | 4 | 8 | E-220 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-28 | OPEN | Analytics Enablement 17
R-0252 | P-008 | QUALITY | Resource availability may affect delivery schedule. | 1 | 5 | 5 | E-034 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-13 | CLOSED | Data Quality Improvement 08
R-0253 | P-004 | PEOPLE | Data quality may delay analytics validation. | 2 | 1 | 2 | E-080 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-22 | OPEN | Knowledge Management 04
R-0254 | P-021 | DATA | Data quality may delay analytics validation. | 2 | 2 | 4 | E-099 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-29 | CLOSED | Data Quality Improvement 21
R-0255 | P-012 | TECHNOLOGY | Resource availability may affect delivery schedule. | 1 | 2 | 2 | E-198 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-30 | OPEN | Document Modernization 12
R-0256 | P-020 | QUALITY | Data quality may delay analytics validation. | 1 | 4 | 4 | E-047 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-28 | MITIGATING | Training Digitization 20
R-0257 | P-020 | PEOPLE | Resource availability may affect delivery schedule. | 2 | 5 | 10 | E-090 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-24 | CLOSED | Training Digitization 20
R-0258 | P-001 | TECHNOLOGY | Supplier dependency may increase lead time. | 2 | 5 | 10 | E-054 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-07 | ACCEPTED | Enterprise Knowledge and Risk Intelligence Pilot
R-0259 | P-024 | DATA | Data quality may delay analytics validation. | 2 | 4 | 8 | E-178 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-29 | OPEN | Knowledge Management 24
R-0260 | P-015 | PEOPLE | AI response quality may be insufficient without evaluation data. | 4 | 2 | 8 | E-149 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-07 | MITIGATING | Document Modernization 15
R-0261 | P-027 | SCHEDULE | Supplier dependency may increase lead time. | 3 | 4 | 12 | E-002 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-09 | ACCEPTED | Supplier Performance Improvement 27
R-0262 | P-024 | SCHEDULE | Current document version may be unclear to project users. | 2 | 1 | 2 | E-165 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-23 | CLOSED | Knowledge Management 24
R-0263 | P-004 | DATA | Resource availability may affect delivery schedule. | 4 | 2 | 8 | E-082 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-26 | MITIGATING | Knowledge Management 04
R-0264 | P-002 | PEOPLE | AI response quality may be insufficient without evaluation data. | 3 | 3 | 9 | E-013 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-17 | MITIGATING | Risk Reporting Automation 02
R-0265 | P-005 | COST | Resource availability may affect delivery schedule. | 3 | 4 | 12 | E-237 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-18 | MITIGATING | Maintenance Planning Enhancement 05
R-0266 | P-003 | PEOPLE | Supplier dependency may increase lead time. | 1 | 3 | 3 | E-077 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-24 | CLOSED | Training Digitization 03
R-0267 | P-023 | SCHEDULE | Current document version may be unclear to project users. | 2 | 1 | 2 | E-070 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-06 | MITIGATING | Supplier Performance Improvement 23
R-0268 | P-026 | PEOPLE | Resource availability may affect delivery schedule. | 1 | 3 | 3 | E-026 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-06 | OPEN | Training Digitization 26
R-0269 | P-021 | TECHNOLOGY | Data quality may delay analytics validation. | 3 | 1 | 3 | E-223 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-08 | ACCEPTED | Data Quality Improvement 21
R-0270 | P-004 | COST | Supplier dependency may increase lead time. | 3 | 2 | 6 | E-047 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-31 | OPEN | Knowledge Management 04
R-0271 | P-010 | PEOPLE | Data quality may delay analytics validation. | 2 | 1 | 2 | E-121 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-19 | MITIGATING | Document Modernization 10
R-0272 | P-024 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 5 | 3 | 15 | E-043 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-15 | MITIGATING | Knowledge Management 24
R-0273 | P-016 | TECHNOLOGY | Required stakeholder review may not complete before milestone. | 3 | 3 | 9 | E-113 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-06-27 | MITIGATING | Data Quality Improvement 16
R-0274 | P-023 | PEOPLE | AI response quality may be insufficient without evaluation data. | 5 | 2 | 10 | E-205 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-06-26 | CLOSED | Supplier Performance Improvement 23
R-0275 | P-020 | QUALITY | Resource availability may affect delivery schedule. | 2 | 4 | 8 | E-095 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-13 | OPEN | Training Digitization 20
R-0276 | P-005 | TECHNOLOGY | Current document version may be unclear to project users. | 1 | 1 | 1 | E-011 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-02 | MITIGATING | Maintenance Planning Enhancement 05
R-0277 | P-006 | QUALITY | Current document version may be unclear to project users. | 4 | 3 | 12 | E-062 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-17 | MITIGATING | Analytics Enablement 06
R-0278 | P-027 | TECHNOLOGY | Required stakeholder review may not complete before milestone. | 4 | 3 | 12 | E-049 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-24 | CLOSED | Supplier Performance Improvement 27
R-0279 | P-017 | SCHEDULE | Resource availability may affect delivery schedule. | 4 | 3 | 12 | E-177 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-27 | OPEN | Analytics Enablement 17
R-0280 | P-015 | QUALITY | Required stakeholder review may not complete before milestone. | 3 | 4 | 12 | E-182 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-11 | CLOSED | Document Modernization 15
R-0281 | P-018 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 5 | 5 | 25 | E-177 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-02 | CLOSED | Document Modernization 18
R-0282 | P-010 | DATA | Resource availability may affect delivery schedule. | 4 | 4 | 16 | E-112 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-26 | CLOSED | Document Modernization 10
R-0283 | P-001 | TECHNOLOGY | Required stakeholder review may not complete before milestone. | 5 | 5 | 25 | E-024 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-16 | OPEN | Enterprise Knowledge and Risk Intelligence Pilot
R-0284 | P-027 | TECHNOLOGY | Resource availability may affect delivery schedule. | 4 | 5 | 20 | E-078 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-24 | OPEN | Supplier Performance Improvement 27
R-0285 | P-008 | QUALITY | Resource availability may affect delivery schedule. | 1 | 1 | 1 | E-205 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-20 | CLOSED | Data Quality Improvement 08
R-0286 | P-017 | DATA | Supplier dependency may increase lead time. | 2 | 1 | 2 | E-058 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-14 | MITIGATING | Analytics Enablement 17
R-0287 | P-003 | QUALITY | Data quality may delay analytics validation. | 3 | 2 | 6 | E-201 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-04 | MITIGATING | Training Digitization 03
R-0288 | P-006 | SCHEDULE | Resource availability may affect delivery schedule. | 4 | 4 | 16 | E-179 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-14 | CLOSED | Analytics Enablement 06
R-0289 | P-022 | QUALITY | Required stakeholder review may not complete before milestone. | 2 | 4 | 8 | E-098 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-10 | OPEN | Data Quality Improvement 22
R-0290 | P-025 | TECHNOLOGY | Supplier dependency may increase lead time. | 4 | 1 | 4 | E-069 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-09 | CLOSED | Knowledge Management 25
R-0291 | P-014 | COST | Required stakeholder review may not complete before milestone. | 4 | 2 | 8 | E-235 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-05 | OPEN | Analytics Enablement 14
R-0292 | P-004 | QUALITY | AI response quality may be insufficient without evaluation data. | 1 | 4 | 4 | E-076 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-25 | MITIGATING | Knowledge Management 04
R-0293 | P-015 | TECHNOLOGY | Current document version may be unclear to project users. | 1 | 2 | 2 | E-177 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-02 | ACCEPTED | Document Modernization 15
R-0294 | P-004 | QUALITY | Supplier dependency may increase lead time. | 3 | 5 | 15 | E-036 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-20 | OPEN | Knowledge Management 04
R-0295 | P-006 | COST | Resource availability may affect delivery schedule. | 2 | 5 | 10 | E-055 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-14 | OPEN | Analytics Enablement 06
R-0296 | P-026 | TECHNOLOGY | Supplier dependency may increase lead time. | 4 | 4 | 16 | E-219 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-25 | ACCEPTED | Training Digitization 26
R-0297 | P-010 | QUALITY | Data quality may delay analytics validation. | 5 | 3 | 15 | E-115 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-30 | OPEN | Document Modernization 10
R-0298 | P-004 | DATA | Required stakeholder review may not complete before milestone. | 4 | 1 | 4 | E-169 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-06 | OPEN | Knowledge Management 04
R-0299 | P-016 | COST | Supplier dependency may increase lead time. | 3 | 5 | 15 | E-048 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-19 | CLOSED | Data Quality Improvement 16
R-0300 | P-026 | QUALITY | Current document version may be unclear to project users. | 4 | 1 | 4 | E-001 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-17 | OPEN | Training Digitization 26
R-0301 | P-020 | PEOPLE | Data quality may delay analytics validation. | 3 | 3 | 9 | E-079 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-30 | OPEN | Training Digitization 20
R-0302 | P-002 | DATA | Current document version may be unclear to project users. | 2 | 1 | 2 | E-178 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-06 | CLOSED | Risk Reporting Automation 02
R-0303 | P-024 | DATA | Required stakeholder review may not complete before milestone. | 3 | 1 | 3 | E-031 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-10 | CLOSED | Knowledge Management 24
R-0304 | P-023 | TECHNOLOGY | Data quality may delay analytics validation. | 3 | 2 | 6 | E-054 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-27 | CLOSED | Supplier Performance Improvement 23
R-0305 | P-003 | SCHEDULE | Data quality may delay analytics validation. | 1 | 5 | 5 | E-165 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-13 | MITIGATING | Training Digitization 03
R-0306 | P-015 | TECHNOLOGY | Supplier dependency may increase lead time. | 5 | 4 | 20 | E-052 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-15 | ACCEPTED | Document Modernization 15
R-0307 | P-023 | SCHEDULE | Current document version may be unclear to project users. | 2 | 2 | 4 | E-086 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-23 | CLOSED | Supplier Performance Improvement 23
R-0308 | P-011 | PEOPLE | AI response quality may be insufficient without evaluation data. | 3 | 4 | 12 | E-181 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-23 | OPEN | Maintenance Planning Enhancement 11
R-0309 | P-022 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 5 | 3 | 15 | E-215 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-01 | MITIGATING | Data Quality Improvement 22
R-0310 | P-004 | TECHNOLOGY | Current document version may be unclear to project users. | 2 | 1 | 2 | E-218 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-14 | MITIGATING | Knowledge Management 04
R-0311 | P-013 | COST | Required stakeholder review may not complete before milestone. | 4 | 5 | 20 | E-028 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-24 | OPEN | Document Modernization 13
R-0312 | P-022 | COST | Data quality may delay analytics validation. | 1 | 3 | 3 | E-151 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-15 | ACCEPTED | Data Quality Improvement 22
R-0313 | P-026 | SCHEDULE | Supplier dependency may increase lead time. | 5 | 2 | 10 | E-124 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-03 | OPEN | Training Digitization 26
R-0314 | P-014 | SCHEDULE | Supplier dependency may increase lead time. | 1 | 2 | 2 | E-204 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-25 | OPEN | Analytics Enablement 14
R-0315 | P-025 | DATA | AI response quality may be insufficient without evaluation data. | 2 | 2 | 4 | E-061 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-30 | ACCEPTED | Knowledge Management 25
R-0316 | P-022 | COST | Data quality may delay analytics validation. | 5 | 4 | 20 | E-035 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-20 | MITIGATING | Data Quality Improvement 22
R-0317 | P-028 | SCHEDULE | Supplier dependency may increase lead time. | 4 | 3 | 12 | E-042 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-21 | ACCEPTED | Document Modernization 28
R-0318 | P-022 | QUALITY | Data quality may delay analytics validation. | 3 | 1 | 3 | E-017 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-01 | OPEN | Data Quality Improvement 22
R-0319 | P-008 | TECHNOLOGY | Resource availability may affect delivery schedule. | 4 | 3 | 12 | E-084 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-12 | MITIGATING | Data Quality Improvement 08
R-0320 | P-027 | PEOPLE | Data quality may delay analytics validation. | 2 | 1 | 2 | E-162 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-29 | CLOSED | Supplier Performance Improvement 27
R-0321 | P-006 | TECHNOLOGY | Current document version may be unclear to project users. | 4 | 1 | 4 | E-022 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-04 | MITIGATING | Analytics Enablement 06
R-0322 | P-028 | COST | Supplier dependency may increase lead time. | 5 | 5 | 25 | E-087 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-06-28 | MITIGATING | Document Modernization 28
R-0323 | P-010 | COST | Resource availability may affect delivery schedule. | 2 | 4 | 8 | E-075 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-28 | ACCEPTED | Document Modernization 10
R-0324 | P-015 | PEOPLE | Required stakeholder review may not complete before milestone. | 2 | 1 | 2 | E-089 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-26 | MITIGATING | Document Modernization 15
R-0325 | P-019 | PEOPLE | Current document version may be unclear to project users. | 2 | 1 | 2 | E-160 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-27 | OPEN | Maintenance Planning Enhancement 19
R-0326 | P-006 | SCHEDULE | Resource availability may affect delivery schedule. | 1 | 2 | 2 | E-208 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-26 | MITIGATING | Analytics Enablement 06
R-0327 | P-011 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 1 | 2 | 2 | E-085 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-02 | MITIGATING | Maintenance Planning Enhancement 11
R-0328 | P-016 | TECHNOLOGY | Resource availability may affect delivery schedule. | 4 | 5 | 20 | E-189 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-17 | ACCEPTED | Data Quality Improvement 16
R-0329 | P-023 | SCHEDULE | Resource availability may affect delivery schedule. | 4 | 3 | 12 | E-168 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-04 | OPEN | Supplier Performance Improvement 23
R-0330 | P-017 | TECHNOLOGY | Data quality may delay analytics validation. | 5 | 3 | 15 | E-186 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-13 | OPEN | Analytics Enablement 17
R-0331 | P-004 | SCHEDULE | Data quality may delay analytics validation. | 5 | 5 | 25 | E-054 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-18 | ACCEPTED | Knowledge Management 04
R-0332 | P-028 | DATA | Supplier dependency may increase lead time. | 4 | 3 | 12 | E-089 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-17 | ACCEPTED | Document Modernization 28
R-0333 | P-014 | PEOPLE | Supplier dependency may increase lead time. | 5 | 5 | 25 | E-129 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-11 | ACCEPTED | Analytics Enablement 14
R-0334 | P-013 | SCHEDULE | Current document version may be unclear to project users. | 5 | 5 | 25 | E-115 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-11 | MITIGATING | Document Modernization 13
R-0335 | P-006 | QUALITY | Current document version may be unclear to project users. | 5 | 1 | 5 | E-126 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-17 | ACCEPTED | Analytics Enablement 06
R-0336 | P-017 | TECHNOLOGY | Data quality may delay analytics validation. | 5 | 3 | 15 | E-026 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-28 | MITIGATING | Analytics Enablement 17
R-0337 | P-025 | PEOPLE | Supplier dependency may increase lead time. | 3 | 2 | 6 | E-101 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-18 | OPEN | Knowledge Management 25
R-0338 | P-005 | QUALITY | Supplier dependency may increase lead time. | 3 | 4 | 12 | E-163 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-31 | MITIGATING | Maintenance Planning Enhancement 05
R-0339 | P-028 | DATA | Required stakeholder review may not complete before milestone. | 2 | 3 | 6 | E-089 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-19 | MITIGATING | Document Modernization 28
R-0340 | P-011 | COST | AI response quality may be insufficient without evaluation data. | 2 | 2 | 4 | E-104 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-08 | OPEN | Maintenance Planning Enhancement 11
R-0341 | P-010 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 4 | 1 | 4 | E-210 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-24 | MITIGATING | Document Modernization 10
R-0342 | P-022 | SCHEDULE | Required stakeholder review may not complete before milestone. | 3 | 3 | 9 | E-076 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-12 | CLOSED | Data Quality Improvement 22
R-0343 | P-022 | QUALITY | AI response quality may be insufficient without evaluation data. | 1 | 3 | 3 | E-224 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-04 | ACCEPTED | Data Quality Improvement 22
R-0344 | P-014 | DATA | Resource availability may affect delivery schedule. | 3 | 3 | 9 | E-207 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-26 | ACCEPTED | Analytics Enablement 14
R-0345 | P-021 | PEOPLE | Resource availability may affect delivery schedule. | 4 | 1 | 4 | E-082 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-15 | MITIGATING | Data Quality Improvement 21
R-0346 | P-008 | TECHNOLOGY | Resource availability may affect delivery schedule. | 3 | 2 | 6 | E-196 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-05 | CLOSED | Data Quality Improvement 08
R-0347 | P-013 | QUALITY | Supplier dependency may increase lead time. | 3 | 1 | 3 | E-046 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-08 | CLOSED | Document Modernization 13
R-0348 | P-022 | TECHNOLOGY | Required stakeholder review may not complete before milestone. | 3 | 1 | 3 | E-227 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-13 | MITIGATING | Data Quality Improvement 22
R-0349 | P-019 | SCHEDULE | Data quality may delay analytics validation. | 2 | 5 | 10 | E-083 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-18 | MITIGATING | Maintenance Planning Enhancement 19
R-0350 | P-011 | QUALITY | Resource availability may affect delivery schedule. | 1 | 1 | 1 | E-069 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-18 | OPEN | Maintenance Planning Enhancement 11
R-0351 | P-026 | QUALITY | Data quality may delay analytics validation. | 1 | 5 | 5 | E-159 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-17 | MITIGATING | Training Digitization 26
R-0352 | P-017 | SCHEDULE | Supplier dependency may increase lead time. | 1 | 1 | 1 | E-004 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-11 | CLOSED | Analytics Enablement 17
R-0353 | P-004 | PEOPLE | Required stakeholder review may not complete before milestone. | 5 | 5 | 25 | E-237 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-02 | OPEN | Knowledge Management 04
R-0354 | P-015 | TECHNOLOGY | Supplier dependency may increase lead time. | 1 | 4 | 4 | E-115 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-19 | CLOSED | Document Modernization 15
R-0355 | P-018 | QUALITY | Required stakeholder review may not complete before milestone. | 1 | 4 | 4 | E-074 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-30 | ACCEPTED | Document Modernization 18
R-0356 | P-002 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 4 | 1 | 4 | E-159 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-23 | OPEN | Risk Reporting Automation 02
R-0357 | P-014 | COST | Required stakeholder review may not complete before milestone. | 2 | 1 | 2 | E-168 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-24 | MITIGATING | Analytics Enablement 14
R-0358 | P-001 | SCHEDULE | Supplier dependency may increase lead time. | 4 | 5 | 20 | E-141 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-27 | OPEN | Enterprise Knowledge and Risk Intelligence Pilot
R-0359 | P-021 | PEOPLE | Required stakeholder review may not complete before milestone. | 5 | 5 | 25 | E-237 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-09 | CLOSED | Data Quality Improvement 21
R-0360 | P-016 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 1 | 2 | 2 | E-187 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-13 | OPEN | Data Quality Improvement 16
R-0361 | P-016 | DATA | Supplier dependency may increase lead time. | 5 | 1 | 5 | E-175 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-06 | OPEN | Data Quality Improvement 16
R-0362 | P-001 | TECHNOLOGY | Resource availability may affect delivery schedule. | 4 | 2 | 8 | E-076 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-06 | ACCEPTED | Enterprise Knowledge and Risk Intelligence Pilot
R-0363 | P-011 | TECHNOLOGY | Data quality may delay analytics validation. | 1 | 3 | 3 | E-062 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-28 | OPEN | Maintenance Planning Enhancement 11
R-0364 | P-019 | DATA | Required stakeholder review may not complete before milestone. | 4 | 2 | 8 | E-043 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-06 | CLOSED | Maintenance Planning Enhancement 19
R-0365 | P-010 | COST | Current document version may be unclear to project users. | 3 | 3 | 9 | E-036 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-28 | OPEN | Document Modernization 10
R-0366 | P-016 | PEOPLE | Current document version may be unclear to project users. | 5 | 4 | 20 | E-058 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-19 | MITIGATING | Data Quality Improvement 16
R-0367 | P-005 | QUALITY | AI response quality may be insufficient without evaluation data. | 5 | 2 | 10 | E-019 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-09 | OPEN | Maintenance Planning Enhancement 05
R-0368 | P-018 | SCHEDULE | Current document version may be unclear to project users. | 2 | 4 | 8 | E-023 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-13 | MITIGATING | Document Modernization 18
R-0369 | P-005 | PEOPLE | Required stakeholder review may not complete before milestone. | 3 | 3 | 9 | E-226 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-09 | MITIGATING | Maintenance Planning Enhancement 05
R-0370 | P-023 | DATA | Resource availability may affect delivery schedule. | 2 | 3 | 6 | E-161 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-26 | MITIGATING | Supplier Performance Improvement 23
R-0371 | P-022 | SCHEDULE | Supplier dependency may increase lead time. | 3 | 4 | 12 | E-177 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-11 | MITIGATING | Data Quality Improvement 22
R-0372 | P-017 | COST | Supplier dependency may increase lead time. | 2 | 1 | 2 | E-085 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-29 | MITIGATING | Analytics Enablement 17
R-0373 | P-027 | COST | Resource availability may affect delivery schedule. | 1 | 5 | 5 | E-189 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-04 | OPEN | Supplier Performance Improvement 27
R-0374 | P-007 | COST | AI response quality may be insufficient without evaluation data. | 2 | 1 | 2 | E-123 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-28 | CLOSED | Analytics Enablement 07
R-0375 | P-009 | TECHNOLOGY | Current document version may be unclear to project users. | 5 | 3 | 15 | E-193 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-22 | CLOSED | Training Digitization 09
R-0376 | P-015 | SCHEDULE | Required stakeholder review may not complete before milestone. | 5 | 5 | 25 | E-016 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-18 | ACCEPTED | Document Modernization 15
R-0377 | P-001 | TECHNOLOGY | Required stakeholder review may not complete before milestone. | 3 | 2 | 6 | E-141 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-13 | CLOSED | Enterprise Knowledge and Risk Intelligence Pilot
R-0378 | P-013 | SCHEDULE | Resource availability may affect delivery schedule. | 2 | 5 | 10 | E-208 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-20 | OPEN | Document Modernization 13
R-0379 | P-012 | QUALITY | AI response quality may be insufficient without evaluation data. | 5 | 2 | 10 | E-059 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-29 | MITIGATING | Document Modernization 12
R-0380 | P-028 | SCHEDULE | Data quality may delay analytics validation. | 2 | 3 | 6 | E-026 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-20 | OPEN | Document Modernization 28
R-0381 | P-019 | DATA | Resource availability may affect delivery schedule. | 2 | 1 | 2 | E-079 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-23 | CLOSED | Maintenance Planning Enhancement 19
R-0382 | P-002 | PEOPLE | Current document version may be unclear to project users. | 4 | 2 | 8 | E-224 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-15 | CLOSED | Risk Reporting Automation 02
R-0383 | P-015 | DATA | Supplier dependency may increase lead time. | 4 | 3 | 12 | E-205 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-07 | MITIGATING | Document Modernization 15
R-0384 | P-007 | DATA | Supplier dependency may increase lead time. | 5 | 1 | 5 | E-206 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-19 | ACCEPTED | Analytics Enablement 07
R-0385 | P-026 | COST | AI response quality may be insufficient without evaluation data. | 2 | 4 | 8 | E-049 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-16 | CLOSED | Training Digitization 26
R-0386 | P-026 | TECHNOLOGY | Required stakeholder review may not complete before milestone. | 2 | 1 | 2 | E-148 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-10 | MITIGATING | Training Digitization 26
R-0387 | P-009 | QUALITY | Current document version may be unclear to project users. | 4 | 4 | 16 | E-014 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-20 | OPEN | Training Digitization 09
R-0388 | P-023 | SCHEDULE | Required stakeholder review may not complete before milestone. | 4 | 5 | 20 | E-231 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-06 | OPEN | Supplier Performance Improvement 23
R-0389 | P-019 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 2 | 5 | 10 | E-163 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-20 | OPEN | Maintenance Planning Enhancement 19
R-0390 | P-014 | SCHEDULE | AI response quality may be insufficient without evaluation data. | 4 | 3 | 12 | E-164 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-17 | MITIGATING | Analytics Enablement 14
R-0391 | P-013 | PEOPLE | AI response quality may be insufficient without evaluation data. | 2 | 1 | 2 | E-050 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-18 | OPEN | Document Modernization 13
R-0392 | P-005 | DATA | AI response quality may be insufficient without evaluation data. | 1 | 1 | 1 | E-184 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-29 | OPEN | Maintenance Planning Enhancement 05
R-0393 | P-001 | TECHNOLOGY | Resource availability may affect delivery schedule. | 2 | 4 | 8 | E-111 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-21 | CLOSED | Enterprise Knowledge and Risk Intelligence Pilot
R-0394 | P-027 | TECHNOLOGY | AI response quality may be insufficient without evaluation data. | 2 | 5 | 10 | E-132 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-17 | MITIGATING | Supplier Performance Improvement 27
R-0395 | P-009 | TECHNOLOGY | Required stakeholder review may not complete before milestone. | 3 | 2 | 6 | E-234 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-27 | MITIGATING | Training Digitization 09
R-0396 | P-017 | SCHEDULE | Required stakeholder review may not complete before milestone. | 2 | 4 | 8 | E-110 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-21 | OPEN | Analytics Enablement 17
R-0397 | P-025 | TECHNOLOGY | Data quality may delay analytics validation. | 1 | 3 | 3 | E-202 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-28 | CLOSED | Knowledge Management 25
R-0398 | P-027 | QUALITY | Current document version may be unclear to project users. | 2 | 5 | 10 | E-180 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-07-17 | OPEN | Supplier Performance Improvement 27
R-0399 | P-027 | SCHEDULE | Data quality may delay analytics validation. | 1 | 2 | 2 | E-175 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-20 | MITIGATING | Supplier Performance Improvement 27
R-0400 | P-016 | SCHEDULE | Resource availability may affect delivery schedule. | 1 | 2 | 2 | E-216 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-14 | MITIGATING | Data Quality Improvement 16
R-0401 | P-003 | DATA | Supplier dependency may increase lead time. | 5 | 5 | 25 | E-145 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-22 | ACCEPTED | Training Digitization 03
R-0402 | P-008 | DATA | Current document version may be unclear to project users. | 1 | 2 | 2 | E-110 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-31 | MITIGATING | Data Quality Improvement 08
R-0403 | P-017 | SCHEDULE | Data quality may delay analytics validation. | 3 | 4 | 12 | E-162 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-08-02 | CLOSED | Analytics Enablement 17
R-0404 | P-028 | DATA | Current document version may be unclear to project users. | 2 | 3 | 6 | E-062 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-30 | MITIGATING | Document Modernization 28
R-0405 | P-026 | COST | Resource availability may affect delivery schedule. | 1 | 1 | 1 | E-039 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-08 | OPEN | Training Digitization 26
R-0406 | P-008 | QUALITY | Supplier dependency may increase lead time. | 1 | 3 | 3 | E-235 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-12-02 | MITIGATING | Data Quality Improvement 08
R-0407 | P-027 | QUALITY | AI response quality may be insufficient without evaluation data. | 3 | 1 | 3 | E-104 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-24 | OPEN | Supplier Performance Improvement 27
R-0408 | P-008 | DATA | Supplier dependency may increase lead time. | 3 | 1 | 3 | E-124 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-07 | OPEN | Data Quality Improvement 08
R-0409 | P-021 | PEOPLE | Current document version may be unclear to project users. | 1 | 3 | 3 | E-209 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-27 | MITIGATING | Data Quality Improvement 21
R-0410 | P-019 | SCHEDULE | Required stakeholder review may not complete before milestone. | 5 | 2 | 10 | E-199 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-12 | CLOSED | Maintenance Planning Enhancement 19
R-0411 | P-022 | SCHEDULE | Supplier dependency may increase lead time. | 4 | 4 | 16 | E-112 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-04 | MITIGATING | Data Quality Improvement 22
R-0412 | P-013 | TECHNOLOGY | Resource availability may affect delivery schedule. | 3 | 5 | 15 | E-225 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-07 | ACCEPTED | Document Modernization 13
R-0413 | P-021 | COST | Current document version may be unclear to project users. | 4 | 5 | 20 | E-045 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-02-16 | OPEN | Data Quality Improvement 21
R-0414 | P-019 | QUALITY | AI response quality may be insufficient without evaluation data. | 2 | 5 | 10 | E-094 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-07 | CLOSED | Maintenance Planning Enhancement 19
R-0415 | P-005 | PEOPLE | Required stakeholder review may not complete before milestone. | 5 | 1 | 5 | E-026 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-09-28 | MITIGATING | Maintenance Planning Enhancement 05
R-0416 | P-007 | PEOPLE | Supplier dependency may increase lead time. | 2 | 3 | 6 | E-089 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-23 | MITIGATING | Analytics Enablement 07
R-0417 | P-003 | PEOPLE | Data quality may delay analytics validation. | 4 | 3 | 12 | E-147 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-03 | CLOSED | Training Digitization 03
R-0418 | P-016 | PEOPLE | Required stakeholder review may not complete before milestone. | 4 | 1 | 4 | E-182 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-11-26 | CLOSED | Data Quality Improvement 16
R-0419 | P-006 | TECHNOLOGY | Current document version may be unclear to project users. | 3 | 4 | 12 | E-118 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2027-01-11 | MITIGATING | Analytics Enablement 06
R-0420 | P-003 | PEOPLE | Supplier dependency may increase lead time. | 5 | 2 | 10 | E-202 | Review evidence, assign an accountable owner, and track mitigation to closure. | 2026-10-10 | MITIGATING | Training Digitization 03
R-0421 | P-029 | ASSET_RELIABILITY | Continued vibration degradation may reduce A-001 availability if the source is not identified and controlled. | 5 | 4 | 20 | E-001 | Confirm vibration source using approved inspection procedure, increase monitoring frequency, and obtain human approval before corrective intervention. | 2026-08-27 | MITIGATING | A-001 Cooling Water Pump Reliability Improvement
R-0422 | P-029 | MAINTENANCE_EXECUTION | Open, deferred, or not-yet-completed A-001 work orders may delay closure of the reliability issue. | 4 | 3 | 12 | E-075 | Reconcile the A-001 work-order backlog, prioritize condition-related work, and document closure evidence. | 2026-09-04 | MITIGATING | A-001 Cooling Water Pump Reliability Improvement
R-0423 | P-029 | DOCUMENT_CONTROL | Multiple procedure versions may create ambiguity if a superseded or draft inspection procedure is used instead of the approved version. | 3 | 3 | 9 | E-041 | Use DOC-PROC-001-V2 as the approved procedure and explicitly block superseded V1 and draft V3 from execution decisions. | 2026-08-30 | MITIGATING | A-001 Cooling Water Pump Reliability Improvement

## actions
action_id | project_id | risk_id | action_description | owner_employee_id | priority | due_date | completed_date | status | evidence_reference | project_name
ACT-0001 | P-001 | R-0001 | Create approval-status metadata filter and run the conflicting-version evaluation set. | E-015 | HIGH | 2026-08-18 |  | OVERDUE |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0002 | P-001 | R-0002 | Assign a risk owner and define the human approval role before pilot release. |  | HIGH | 2026-08-22 |  | OVERDUE |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0003 | P-001 | R-0001 | Document the retrieval test evidence. | E-018 | HIGH | 2026-08-23 | 2026-08-24 | COMPLETED |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0004 | P-004 | R-0055 | Validate source data and document evidence. | E-051 | MEDIUM | 2026-10-19 |  | IN_PROGRESS |  | Knowledge Management 04
ACT-0005 | P-022 | R-0029 | Update the risk response and obtain owner approval. | E-036 | HIGH | 2026-06-30 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0006 | P-008 | R-0118 | Complete independent review of the proposed control. | E-185 | LOW | 2026-10-09 |  | IN_PROGRESS |  | Data Quality Improvement 08
ACT-0007 | P-026 | R-0203 | Complete independent review of the proposed control. | E-089 | HIGH | 2027-01-10 |  | OPEN |  | Training Digitization 26
ACT-0008 | P-026 | R-0216 | Complete independent review of the proposed control. | E-068 | LOW | 2026-07-05 |  | OVERDUE |  | Training Digitization 26
ACT-0009 | P-003 | R-0287 | Complete independent review of the proposed control. | E-089 | LOW | 2026-06-07 |  | OPEN |  | Training Digitization 03
ACT-0010 | P-010 | R-0099 | Validate source data and document evidence. | E-071 | HIGH | 2026-07-12 |  | OVERDUE |  | Document Modernization 10
ACT-0011 | P-022 | R-0167 | Run the evaluation set and document failure cases. | E-087 | MEDIUM | 2027-01-13 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0012 | P-015 | R-0324 | Update the risk response and obtain owner approval. | E-087 | MEDIUM | 2026-12-07 |  | OPEN |  | Document Modernization 15
ACT-0013 | P-004 | R-0353 | Run the evaluation set and document failure cases. | E-216 | LOW | 2026-07-13 |  | OPEN |  | Knowledge Management 04
ACT-0014 | P-003 | R-0417 | Update the risk response and obtain owner approval. | E-120 | MEDIUM | 2027-01-17 |  | IN_PROGRESS |  | Training Digitization 03
ACT-0015 | P-002 | R-0264 | Update the risk response and obtain owner approval. | E-045 | LOW | 2026-08-05 |  | IN_PROGRESS |  | Risk Reporting Automation 02
ACT-0016 | P-005 | R-0014 | Complete independent review of the proposed control. | E-075 | MEDIUM | 2026-12-18 |  | OPEN |  | Maintenance Planning Enhancement 05
ACT-0017 | P-014 | R-0344 | Run the evaluation set and document failure cases. | E-170 | LOW | 2027-01-01 |  | IN_PROGRESS |  | Analytics Enablement 14
ACT-0018 | P-011 | R-0073 | Validate source data and document evidence. | E-060 | LOW | 2026-08-17 | 2026-08-07 | COMPLETED | EVID-0018 | Maintenance Planning Enhancement 11
ACT-0019 | P-015 | R-0154 | Run the evaluation set and document failure cases. | E-076 | HIGH | 2026-07-02 | 2026-06-25 | COMPLETED | EVID-0019 | Document Modernization 15
ACT-0020 | P-026 | R-0065 | Update the risk response and obtain owner approval. | E-138 | LOW | 2026-11-28 |  | OPEN |  | Training Digitization 26
ACT-0021 | P-021 | R-0084 | Complete independent review of the proposed control. | E-137 | MEDIUM | 2027-02-04 | 2027-02-02 | COMPLETED | EVID-0021 | Data Quality Improvement 21
ACT-0022 | P-028 | R-0007 | Run the evaluation set and document failure cases. | E-171 | LOW | 2026-06-29 | 2026-06-29 | COMPLETED | EVID-0022 | Document Modernization 28
ACT-0023 | P-028 | R-0008 | Complete independent review of the proposed control. | E-189 | MEDIUM | 2026-06-16 | 2026-06-06 | COMPLETED | EVID-0023 | Document Modernization 28
ACT-0024 | P-009 | R-0063 | Validate source data and document evidence. | E-167 | HIGH | 2026-08-10 | 2026-08-09 | COMPLETED | EVID-0024 | Training Digitization 09
ACT-0025 | P-025 | R-0003 | Run the evaluation set and document failure cases. | E-018 | HIGH | 2026-08-01 |  | OPEN |  | Knowledge Management 25
ACT-0026 | P-006 | R-0006 | Run the evaluation set and document failure cases. | E-210 | HIGH | 2026-06-26 | 2026-06-18 | COMPLETED | EVID-0026 | Analytics Enablement 06
ACT-0027 | P-025 | R-0069 | Validate source data and document evidence. | E-134 | HIGH | 2026-08-13 | 2026-08-12 | COMPLETED | EVID-0027 | Knowledge Management 25
ACT-0028 | P-011 | R-0237 | Update the risk response and obtain owner approval. | E-172 | MEDIUM | 2026-12-14 |  | OPEN |  | Maintenance Planning Enhancement 11
ACT-0029 | P-017 | R-0089 | Update the risk response and obtain owner approval. | E-045 | LOW | 2026-10-17 | 2026-10-11 | COMPLETED | EVID-0029 | Analytics Enablement 17
ACT-0030 | P-018 | R-0281 | Validate source data and document evidence. | E-064 | MEDIUM | 2026-09-14 | 2026-09-13 | COMPLETED | EVID-0030 | Document Modernization 18
ACT-0031 | P-015 | R-0293 | Run the evaluation set and document failure cases. | E-105 | MEDIUM | 2026-11-16 |  | OPEN |  | Document Modernization 15
ACT-0032 | P-004 | R-0040 | Validate source data and document evidence. | E-163 | HIGH | 2027-01-30 | 2027-01-29 | COMPLETED | EVID-0032 | Knowledge Management 04
ACT-0033 | P-008 | R-0134 | Validate source data and document evidence. | E-071 | LOW | 2026-07-10 |  | IN_PROGRESS |  | Data Quality Improvement 08
ACT-0034 | P-024 | R-0259 | Validate source data and document evidence. | E-013 | LOW | 2026-11-26 | 2026-11-16 | COMPLETED | EVID-0034 | Knowledge Management 24
ACT-0035 | P-025 | R-0315 | Run the evaluation set and document failure cases. | E-014 | HIGH | 2026-08-10 |  | OPEN |  | Knowledge Management 25
ACT-0036 | P-013 | R-0412 | Validate source data and document evidence. | E-186 | HIGH | 2027-01-29 |  | IN_PROGRESS |  | Document Modernization 13
ACT-0037 | P-017 | R-0352 | Validate source data and document evidence. | E-236 | LOW | 2027-02-06 |  | IN_PROGRESS |  | Analytics Enablement 17
ACT-0038 | P-025 | R-0069 | Update the risk response and obtain owner approval. | E-162 | LOW | 2026-09-22 |  | OVERDUE |  | Knowledge Management 25
ACT-0039 | P-027 | R-0093 | Validate source data and document evidence. | E-074 | LOW | 2026-06-06 | 2026-05-28 | COMPLETED | EVID-0039 | Supplier Performance Improvement 27
ACT-0040 | P-018 | R-0368 | Validate source data and document evidence. | E-232 | LOW | 2026-09-27 | 2026-09-24 | COMPLETED | EVID-0040 | Document Modernization 18
ACT-0041 | P-002 | R-0356 | Update the risk response and obtain owner approval. | E-023 | LOW | 2026-09-19 |  | IN_PROGRESS |  | Risk Reporting Automation 02
ACT-0042 | P-021 | R-0084 | Run the evaluation set and document failure cases. | E-225 | LOW | 2027-02-11 | 2027-02-07 | COMPLETED | EVID-0042 | Data Quality Improvement 21
ACT-0043 | P-005 | R-0415 | Run the evaluation set and document failure cases. | E-088 | LOW | 2026-09-11 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 05
ACT-0044 | P-021 | R-0254 | Validate source data and document evidence. | E-134 | LOW | 2026-08-24 | 2026-08-21 | COMPLETED | EVID-0044 | Data Quality Improvement 21
ACT-0045 | P-015 | R-0324 | Run the evaluation set and document failure cases. | E-029 | MEDIUM | 2026-11-07 |  | IN_PROGRESS |  | Document Modernization 15
ACT-0046 | P-019 | R-0410 | Complete independent review of the proposed control. | E-196 | MEDIUM | 2026-11-25 | 2026-11-22 | COMPLETED | EVID-0046 | Maintenance Planning Enhancement 19
ACT-0047 | P-004 | R-0294 | Validate source data and document evidence. | E-022 | LOW | 2026-11-19 | 2026-11-17 | COMPLETED | EVID-0047 | Knowledge Management 04
ACT-0048 | P-026 | R-0197 | Validate source data and document evidence. | E-081 | MEDIUM | 2026-12-21 | 2026-12-20 | COMPLETED | EVID-0048 | Training Digitization 26
ACT-0049 | P-024 | R-0272 | Run the evaluation set and document failure cases. | E-051 | LOW | 2026-11-22 | 2026-11-12 | COMPLETED | EVID-0049 | Knowledge Management 24
ACT-0050 | P-026 | R-0177 | Update the risk response and obtain owner approval. | E-054 | HIGH | 2026-10-17 |  | IN_PROGRESS |  | Training Digitization 26
ACT-0051 | P-014 | R-0116 | Update the risk response and obtain owner approval. | E-016 | HIGH | 2027-01-29 | 2027-01-19 | COMPLETED | EVID-0051 | Analytics Enablement 14
ACT-0052 | P-001 | R-0377 | Complete independent review of the proposed control. | E-114 | MEDIUM | 2026-06-24 |  | OPEN |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0053 | P-025 | R-0038 | Run the evaluation set and document failure cases. | E-104 | HIGH | 2027-01-17 |  | OVERDUE |  | Knowledge Management 25
ACT-0054 | P-010 | R-0195 | Validate source data and document evidence. | E-151 | MEDIUM | 2026-10-18 |  | OVERDUE |  | Document Modernization 10
ACT-0055 | P-003 | R-0266 | Validate source data and document evidence. | E-127 | HIGH | 2027-02-17 |  | OVERDUE |  | Training Digitization 03
ACT-0056 | P-001 | R-0283 | Validate source data and document evidence. | E-086 | HIGH | 2026-07-28 |  | OPEN |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0057 | P-012 | R-0062 | Run the evaluation set and document failure cases. | E-133 | LOW | 2026-10-14 |  | OVERDUE |  | Document Modernization 12
ACT-0058 | P-019 | R-0349 | Run the evaluation set and document failure cases. | E-236 | LOW | 2026-08-04 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 19
ACT-0059 | P-027 | R-0101 | Run the evaluation set and document failure cases. | E-054 | LOW | 2026-07-21 |  | OPEN |  | Supplier Performance Improvement 27
ACT-0060 | P-024 | R-0303 | Validate source data and document evidence. | E-163 | MEDIUM | 2026-07-02 |  | OPEN |  | Knowledge Management 24
ACT-0061 | P-013 | R-0215 | Run the evaluation set and document failure cases. | E-011 | MEDIUM | 2026-10-17 | 2026-10-14 | COMPLETED | EVID-0061 | Document Modernization 13
ACT-0062 | P-028 | R-0332 | Complete independent review of the proposed control. | E-227 | HIGH | 2026-07-17 |  | IN_PROGRESS |  | Document Modernization 28
ACT-0063 | P-015 | R-0324 | Update the risk response and obtain owner approval. | E-177 | MEDIUM | 2026-08-31 | 2026-08-28 | COMPLETED | EVID-0063 | Document Modernization 15
ACT-0064 | P-027 | R-0261 | Run the evaluation set and document failure cases. | E-233 | HIGH | 2026-10-17 | 2026-10-09 | COMPLETED | EVID-0064 | Supplier Performance Improvement 27
ACT-0065 | P-002 | R-0121 | Complete independent review of the proposed control. | E-128 | HIGH | 2027-02-03 |  | IN_PROGRESS |  | Risk Reporting Automation 02
ACT-0066 | P-017 | R-0032 | Run the evaluation set and document failure cases. | E-209 | MEDIUM | 2026-07-29 |  | OVERDUE |  | Analytics Enablement 17
ACT-0067 | P-026 | R-0183 | Update the risk response and obtain owner approval. | E-090 | LOW | 2027-02-11 | 2027-02-06 | COMPLETED | EVID-0067 | Training Digitization 26
ACT-0068 | P-001 | R-0186 | Run the evaluation set and document failure cases. | E-220 | MEDIUM | 2026-12-27 |  | IN_PROGRESS |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0069 | P-028 | R-0151 | Update the risk response and obtain owner approval. | E-109 | MEDIUM | 2026-09-11 | 2026-09-11 | COMPLETED | EVID-0069 | Document Modernization 28
ACT-0070 | P-016 | R-0361 | Update the risk response and obtain owner approval. | E-166 | HIGH | 2026-08-01 |  | OPEN |  | Data Quality Improvement 16
ACT-0071 | P-005 | R-0174 | Complete independent review of the proposed control. | E-073 | MEDIUM | 2026-10-14 | 2026-10-07 | COMPLETED | EVID-0071 | Maintenance Planning Enhancement 05
ACT-0072 | P-016 | R-0328 | Run the evaluation set and document failure cases. | E-109 | MEDIUM | 2026-08-22 |  | OVERDUE |  | Data Quality Improvement 16
ACT-0073 | P-020 | R-0275 | Run the evaluation set and document failure cases. | E-032 | LOW | 2026-06-21 |  | OVERDUE |  | Training Digitization 20
ACT-0074 | P-025 | R-0108 | Complete independent review of the proposed control. | E-160 | HIGH | 2026-05-30 |  | OPEN |  | Knowledge Management 25
ACT-0075 | P-009 | R-0082 | Run the evaluation set and document failure cases. | E-019 | LOW | 2026-09-01 |  | OPEN |  | Training Digitization 09
ACT-0076 | P-022 | R-0110 | Complete independent review of the proposed control. | E-144 | HIGH | 2027-01-16 | 2027-01-11 | COMPLETED | EVID-0076 | Data Quality Improvement 22
ACT-0077 | P-011 | R-0147 | Validate source data and document evidence. | E-188 | HIGH | 2026-12-24 |  | OVERDUE |  | Maintenance Planning Enhancement 11
ACT-0078 | P-028 | R-0151 | Run the evaluation set and document failure cases. | E-135 | LOW | 2026-10-28 | 2026-10-19 | COMPLETED | EVID-0078 | Document Modernization 28
ACT-0079 | P-013 | R-0078 | Validate source data and document evidence. | E-049 | HIGH | 2026-05-31 | 2026-05-26 | COMPLETED | EVID-0079 | Document Modernization 13
ACT-0080 | P-004 | R-0250 | Validate source data and document evidence. | E-204 | MEDIUM | 2026-12-01 |  | IN_PROGRESS |  | Knowledge Management 04
ACT-0081 | P-006 | R-0220 | Update the risk response and obtain owner approval. | E-123 | HIGH | 2026-12-29 | 2026-12-23 | COMPLETED | EVID-0081 | Analytics Enablement 06
ACT-0082 | P-005 | R-0172 | Update the risk response and obtain owner approval. | E-150 | HIGH | 2026-06-17 |  | OPEN |  | Maintenance Planning Enhancement 05
ACT-0083 | P-018 | R-0355 | Complete independent review of the proposed control. | E-166 | LOW | 2027-02-19 | 2027-02-19 | COMPLETED | EVID-0083 | Document Modernization 18
ACT-0084 | P-022 | R-0343 | Run the evaluation set and document failure cases. | E-080 | MEDIUM | 2026-08-13 | 2026-08-06 | COMPLETED | EVID-0084 | Data Quality Improvement 22
ACT-0085 | P-008 | R-0252 | Run the evaluation set and document failure cases. | E-028 | LOW | 2027-02-21 |  | IN_PROGRESS |  | Data Quality Improvement 08
ACT-0086 | P-011 | R-0147 | Run the evaluation set and document failure cases. | E-091 | HIGH | 2026-11-27 | 2026-11-17 | COMPLETED | EVID-0086 | Maintenance Planning Enhancement 11
ACT-0087 | P-019 | R-0364 | Update the risk response and obtain owner approval. | E-209 | MEDIUM | 2027-02-20 | 2027-02-13 | COMPLETED | EVID-0087 | Maintenance Planning Enhancement 19
ACT-0088 | P-002 | R-0075 | Run the evaluation set and document failure cases. | E-080 | LOW | 2026-07-03 | 2026-06-25 | COMPLETED | EVID-0088 | Risk Reporting Automation 02
ACT-0089 | P-021 | R-0084 | Run the evaluation set and document failure cases. | E-137 | LOW | 2027-01-05 | 2027-01-01 | COMPLETED | EVID-0089 | Data Quality Improvement 21
ACT-0090 | P-018 | R-0119 | Run the evaluation set and document failure cases. | E-107 | HIGH | 2026-06-05 | 2026-05-27 | COMPLETED | EVID-0090 | Document Modernization 18
ACT-0091 | P-004 | R-0270 | Run the evaluation set and document failure cases. | E-162 | HIGH | 2026-11-01 |  | OVERDUE |  | Knowledge Management 04
ACT-0092 | P-026 | R-0183 | Complete independent review of the proposed control. | E-048 | MEDIUM | 2026-06-06 | 2026-06-01 | COMPLETED | EVID-0092 | Training Digitization 26
ACT-0093 | P-004 | R-0033 | Validate source data and document evidence. | E-037 | MEDIUM | 2026-10-21 | 2026-10-16 | COMPLETED | EVID-0093 | Knowledge Management 04
ACT-0094 | P-004 | R-0091 | Complete independent review of the proposed control. | E-117 | MEDIUM | 2026-06-11 |  | IN_PROGRESS |  | Knowledge Management 04
ACT-0095 | P-010 | R-0109 | Complete independent review of the proposed control. | E-181 | LOW | 2026-07-18 |  | OPEN |  | Document Modernization 10
ACT-0096 | P-007 | R-0182 | Update the risk response and obtain owner approval. | E-095 | MEDIUM | 2026-08-19 | 2026-08-15 | COMPLETED | EVID-0096 | Analytics Enablement 07
ACT-0097 | P-013 | R-0391 | Run the evaluation set and document failure cases. | E-161 | HIGH | 2026-10-24 |  | IN_PROGRESS |  | Document Modernization 13
ACT-0098 | P-019 | R-0364 | Run the evaluation set and document failure cases. | E-067 | LOW | 2026-09-18 | 2026-09-15 | COMPLETED | EVID-0098 | Maintenance Planning Enhancement 19
ACT-0099 | P-020 | R-0143 | Update the risk response and obtain owner approval. | E-060 | LOW | 2027-02-09 |  | IN_PROGRESS |  | Training Digitization 20
ACT-0100 | P-016 | R-0299 | Run the evaluation set and document failure cases. | E-109 | MEDIUM | 2026-06-14 | 2026-06-04 | COMPLETED | EVID-0100 | Data Quality Improvement 16
ACT-0101 | P-004 | R-0310 | Run the evaluation set and document failure cases. | E-216 | HIGH | 2027-01-12 | 2027-01-10 | COMPLETED | EVID-0101 | Knowledge Management 04
ACT-0102 | P-023 | R-0274 | Run the evaluation set and document failure cases. | E-157 | HIGH | 2026-10-01 |  | IN_PROGRESS |  | Supplier Performance Improvement 23
ACT-0103 | P-028 | R-0008 | Run the evaluation set and document failure cases. | E-173 | MEDIUM | 2026-07-09 |  | IN_PROGRESS |  | Document Modernization 28
ACT-0104 | P-016 | R-0400 | Validate source data and document evidence. | E-126 | LOW | 2026-09-06 |  | OPEN |  | Data Quality Improvement 16
ACT-0105 | P-005 | R-0128 | Run the evaluation set and document failure cases. | E-119 | MEDIUM | 2027-02-04 | 2027-02-03 | COMPLETED | EVID-0105 | Maintenance Planning Enhancement 05
ACT-0106 | P-026 | R-0141 | Run the evaluation set and document failure cases. | E-089 | HIGH | 2026-08-16 | 2026-08-12 | COMPLETED | EVID-0106 | Training Digitization 26
ACT-0107 | P-002 | R-0382 | Complete independent review of the proposed control. | E-061 | LOW | 2026-07-05 | 2026-06-27 | COMPLETED | EVID-0107 | Risk Reporting Automation 02
ACT-0108 | P-015 | R-0280 | Validate source data and document evidence. | E-011 | MEDIUM | 2026-06-22 | 2026-06-14 | COMPLETED | EVID-0108 | Document Modernization 15
ACT-0109 | P-018 | R-0119 | Update the risk response and obtain owner approval. | E-198 | MEDIUM | 2026-06-19 | 2026-06-10 | COMPLETED | EVID-0109 | Document Modernization 18
ACT-0110 | P-003 | R-0266 | Complete independent review of the proposed control. | E-035 | MEDIUM | 2026-08-14 | 2026-08-09 | COMPLETED | EVID-0110 | Training Digitization 03
ACT-0111 | P-025 | R-0138 | Update the risk response and obtain owner approval. | E-226 | LOW | 2026-12-15 |  | IN_PROGRESS |  | Knowledge Management 25
ACT-0112 | P-003 | R-0287 | Complete independent review of the proposed control. | E-077 | MEDIUM | 2026-12-25 |  | IN_PROGRESS |  | Training Digitization 03
ACT-0113 | P-017 | R-0396 | Run the evaluation set and document failure cases. | E-138 | LOW | 2027-01-15 | 2027-01-07 | COMPLETED | EVID-0113 | Analytics Enablement 17
ACT-0114 | P-015 | R-0354 | Validate source data and document evidence. | E-153 | MEDIUM | 2027-02-05 | 2027-01-28 | COMPLETED | EVID-0114 | Document Modernization 15
ACT-0115 | P-015 | R-0244 | Validate source data and document evidence. | E-045 | HIGH | 2027-01-18 |  | OPEN |  | Document Modernization 15
ACT-0116 | P-013 | R-0072 | Validate source data and document evidence. | E-177 | MEDIUM | 2026-09-24 |  | OVERDUE |  | Document Modernization 13
ACT-0117 | P-010 | R-0341 | Run the evaluation set and document failure cases. | E-240 | HIGH | 2027-01-10 | 2027-01-04 | COMPLETED | EVID-0117 | Document Modernization 10
ACT-0118 | P-017 | R-0336 | Validate source data and document evidence. | E-144 | MEDIUM | 2026-09-01 |  | OVERDUE |  | Analytics Enablement 17
ACT-0119 | P-016 | R-0212 | Update the risk response and obtain owner approval. | E-097 | LOW | 2026-11-30 |  | IN_PROGRESS |  | Data Quality Improvement 16
ACT-0120 | P-028 | R-0380 | Update the risk response and obtain owner approval. | E-041 | LOW | 2027-02-01 |  | OVERDUE |  | Document Modernization 28
ACT-0121 | P-001 | R-0106 | Complete independent review of the proposed control. | E-197 | HIGH | 2026-10-02 | 2026-10-02 | COMPLETED | EVID-0121 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0122 | P-022 | R-0181 | Update the risk response and obtain owner approval. | E-138 | HIGH | 2026-12-16 | 2026-12-06 | COMPLETED | EVID-0122 | Data Quality Improvement 22
ACT-0123 | P-012 | R-0062 | Run the evaluation set and document failure cases. | E-214 | LOW | 2026-06-18 |  | OPEN |  | Document Modernization 12
ACT-0124 | P-026 | R-0087 | Run the evaluation set and document failure cases. | E-063 | HIGH | 2026-08-22 |  | OPEN |  | Training Digitization 26
ACT-0125 | P-021 | R-0107 | Update the risk response and obtain owner approval. | E-238 | LOW | 2026-09-30 |  | OPEN |  | Data Quality Improvement 21
ACT-0126 | P-007 | R-0384 | Complete independent review of the proposed control. | E-142 | HIGH | 2027-01-13 |  | OVERDUE |  | Analytics Enablement 07
ACT-0127 | P-014 | R-0146 | Update the risk response and obtain owner approval. | E-194 | HIGH | 2026-06-01 |  | OVERDUE |  | Analytics Enablement 14
ACT-0128 | P-015 | R-0383 | Validate source data and document evidence. | E-023 | LOW | 2026-10-10 | 2026-10-03 | COMPLETED | EVID-0128 | Document Modernization 15
ACT-0129 | P-019 | R-0054 | Complete independent review of the proposed control. | E-017 | LOW | 2026-08-04 |  | OPEN |  | Maintenance Planning Enhancement 19
ACT-0130 | P-018 | R-0209 | Validate source data and document evidence. | E-057 | LOW | 2026-07-10 |  | IN_PROGRESS |  | Document Modernization 18
ACT-0131 | P-002 | R-0160 | Update the risk response and obtain owner approval. | E-006 | LOW | 2027-02-14 |  | OPEN |  | Risk Reporting Automation 02
ACT-0132 | P-002 | R-0356 | Complete independent review of the proposed control. | E-153 | MEDIUM | 2026-06-30 | 2026-06-22 | COMPLETED | EVID-0132 | Risk Reporting Automation 02
ACT-0133 | P-001 | R-0199 | Run the evaluation set and document failure cases. | E-159 | HIGH | 2026-08-10 | 2026-08-10 | COMPLETED | EVID-0133 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0134 | P-020 | R-0104 | Complete independent review of the proposed control. | E-069 | LOW | 2026-11-12 |  | IN_PROGRESS |  | Training Digitization 20
ACT-0135 | P-009 | R-0133 | Validate source data and document evidence. | E-016 | MEDIUM | 2026-12-12 |  | IN_PROGRESS |  | Training Digitization 09
ACT-0136 | P-014 | R-0314 | Update the risk response and obtain owner approval. | E-004 | HIGH | 2026-09-01 |  | OVERDUE |  | Analytics Enablement 14
ACT-0137 | P-010 | R-0323 | Run the evaluation set and document failure cases. | E-015 | MEDIUM | 2026-08-09 |  | OPEN |  | Document Modernization 10
ACT-0138 | P-028 | R-0227 | Update the risk response and obtain owner approval. | E-073 | HIGH | 2026-10-31 |  | IN_PROGRESS |  | Document Modernization 28
ACT-0139 | P-012 | R-0255 | Update the risk response and obtain owner approval. | E-015 | LOW | 2026-12-11 |  | OVERDUE |  | Document Modernization 12
ACT-0140 | P-014 | R-0049 | Complete independent review of the proposed control. | E-207 | HIGH | 2026-06-09 | 2026-06-04 | COMPLETED | EVID-0140 | Analytics Enablement 14
ACT-0141 | P-010 | R-0195 | Complete independent review of the proposed control. | E-117 | HIGH | 2026-11-02 |  | OPEN |  | Document Modernization 10
ACT-0142 | P-027 | R-0278 | Update the risk response and obtain owner approval. | E-144 | MEDIUM | 2026-09-15 | 2026-09-14 | COMPLETED | EVID-0142 | Supplier Performance Improvement 27
ACT-0143 | P-022 | R-0348 | Complete independent review of the proposed control. | E-007 | LOW | 2026-09-11 | 2026-09-02 | COMPLETED | EVID-0143 | Data Quality Improvement 22
ACT-0144 | P-007 | R-0035 | Update the risk response and obtain owner approval. | E-100 | LOW | 2026-11-14 |  | OPEN |  | Analytics Enablement 07
ACT-0145 | P-002 | R-0004 | Update the risk response and obtain owner approval. | E-081 | HIGH | 2026-09-11 | 2026-09-03 | COMPLETED | EVID-0145 | Risk Reporting Automation 02
ACT-0146 | P-006 | R-0006 | Run the evaluation set and document failure cases. | E-001 | HIGH | 2026-12-25 |  | OVERDUE |  | Analytics Enablement 06
ACT-0147 | P-002 | R-0224 | Validate source data and document evidence. | E-062 | MEDIUM | 2027-02-09 | 2027-02-02 | COMPLETED | EVID-0147 | Risk Reporting Automation 02
ACT-0148 | P-002 | R-0121 | Update the risk response and obtain owner approval. | E-003 | HIGH | 2027-01-24 |  | OPEN |  | Risk Reporting Automation 02
ACT-0149 | P-022 | R-0289 | Update the risk response and obtain owner approval. | E-140 | LOW | 2026-06-14 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0150 | P-022 | R-0316 | Update the risk response and obtain owner approval. | E-191 | MEDIUM | 2027-02-13 | 2027-02-04 | COMPLETED | EVID-0150 | Data Quality Improvement 22
ACT-0151 | P-022 | R-0289 | Complete independent review of the proposed control. | E-036 | LOW | 2026-11-26 | 2026-11-23 | COMPLETED | EVID-0151 | Data Quality Improvement 22
ACT-0152 | P-020 | R-0010 | Update the risk response and obtain owner approval. | E-166 | HIGH | 2026-09-09 |  | IN_PROGRESS |  | Training Digitization 20
ACT-0153 | P-009 | R-0395 | Update the risk response and obtain owner approval. | E-212 | MEDIUM | 2026-06-14 |  | OPEN |  | Training Digitization 09
ACT-0154 | P-010 | R-0109 | Run the evaluation set and document failure cases. | E-128 | LOW | 2026-10-31 |  | IN_PROGRESS |  | Document Modernization 10
ACT-0155 | P-017 | R-0336 | Update the risk response and obtain owner approval. | E-101 | LOW | 2026-08-25 | 2026-08-22 | COMPLETED | EVID-0155 | Analytics Enablement 17
ACT-0156 | P-018 | R-0085 | Run the evaluation set and document failure cases. | E-081 | MEDIUM | 2026-07-06 | 2026-06-28 | COMPLETED | EVID-0156 | Document Modernization 18
ACT-0157 | P-028 | R-0404 | Validate source data and document evidence. | E-199 | MEDIUM | 2026-09-04 | 2026-09-03 | COMPLETED | EVID-0157 | Document Modernization 28
ACT-0158 | P-020 | R-0104 | Run the evaluation set and document failure cases. | E-221 | LOW | 2026-08-20 | 2026-08-10 | COMPLETED | EVID-0158 | Training Digitization 20
ACT-0159 | P-001 | R-0129 | Validate source data and document evidence. | E-024 | LOW | 2026-06-01 | 2026-05-25 | COMPLETED | EVID-0159 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0160 | P-015 | R-0280 | Update the risk response and obtain owner approval. | E-097 | LOW | 2026-12-14 | 2026-12-07 | COMPLETED | EVID-0160 | Document Modernization 15
ACT-0161 | P-005 | R-0338 | Update the risk response and obtain owner approval. | E-128 | LOW | 2026-10-29 | 2026-10-26 | COMPLETED | EVID-0161 | Maintenance Planning Enhancement 05
ACT-0162 | P-004 | R-0055 | Run the evaluation set and document failure cases. | E-157 | MEDIUM | 2026-08-13 |  | IN_PROGRESS |  | Knowledge Management 04
ACT-0163 | P-013 | R-0173 | Update the risk response and obtain owner approval. | E-087 | LOW | 2026-08-28 |  | IN_PROGRESS |  | Document Modernization 13
ACT-0164 | P-012 | R-0236 | Update the risk response and obtain owner approval. | E-010 | MEDIUM | 2026-08-04 |  | IN_PROGRESS |  | Document Modernization 12
ACT-0165 | P-024 | R-0039 | Validate source data and document evidence. | E-190 | HIGH | 2026-10-07 | 2026-10-07 | COMPLETED | EVID-0165 | Knowledge Management 24
ACT-0166 | P-001 | R-0161 | Run the evaluation set and document failure cases. | E-232 | MEDIUM | 2026-10-30 |  | OPEN |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0167 | P-002 | R-0249 | Update the risk response and obtain owner approval. | E-124 | MEDIUM | 2026-11-30 |  | OPEN |  | Risk Reporting Automation 02
ACT-0168 | P-027 | R-0229 | Complete independent review of the proposed control. | E-155 | HIGH | 2026-09-20 | 2026-09-11 | COMPLETED | EVID-0168 | Supplier Performance Improvement 27
ACT-0169 | P-002 | R-0188 | Complete independent review of the proposed control. | E-074 | MEDIUM | 2026-10-28 |  | OPEN |  | Risk Reporting Automation 02
ACT-0170 | P-027 | R-0398 | Complete independent review of the proposed control. | E-159 | HIGH | 2027-01-26 |  | OPEN |  | Supplier Performance Improvement 27
ACT-0171 | P-002 | R-0249 | Run the evaluation set and document failure cases. | E-034 | MEDIUM | 2026-06-24 |  | OPEN |  | Risk Reporting Automation 02
ACT-0172 | P-025 | R-0315 | Validate source data and document evidence. | E-075 | MEDIUM | 2026-12-17 |  | OPEN |  | Knowledge Management 25
ACT-0173 | P-004 | R-0292 | Update the risk response and obtain owner approval. | E-150 | LOW | 2026-11-26 |  | IN_PROGRESS |  | Knowledge Management 04
ACT-0174 | P-014 | R-0390 | Validate source data and document evidence. | E-197 | MEDIUM | 2027-01-31 |  | OPEN |  | Analytics Enablement 14
ACT-0175 | P-025 | R-0226 | Validate source data and document evidence. | E-113 | LOW | 2027-01-08 |  | OPEN |  | Knowledge Management 25
ACT-0176 | P-017 | R-0251 | Run the evaluation set and document failure cases. | E-112 | LOW | 2026-07-05 |  | OPEN |  | Analytics Enablement 17
ACT-0177 | P-025 | R-0315 | Validate source data and document evidence. | E-238 | LOW | 2026-12-21 | 2026-12-20 | COMPLETED | EVID-0177 | Knowledge Management 25
ACT-0178 | P-011 | R-0135 | Update the risk response and obtain owner approval. | E-141 | MEDIUM | 2026-07-05 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 11
ACT-0179 | P-020 | R-0187 | Complete independent review of the proposed control. | E-066 | LOW | 2027-02-08 |  | IN_PROGRESS |  | Training Digitization 20
ACT-0180 | P-019 | R-0030 | Validate source data and document evidence. | E-173 | MEDIUM | 2026-08-15 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 19
ACT-0181 | P-022 | R-0343 | Run the evaluation set and document failure cases. | E-197 | LOW | 2027-02-19 | 2027-02-18 | COMPLETED | EVID-0181 | Data Quality Improvement 22
ACT-0182 | P-020 | R-0100 | Update the risk response and obtain owner approval. | E-063 | MEDIUM | 2026-07-29 |  | IN_PROGRESS |  | Training Digitization 20
ACT-0183 | P-025 | R-0397 | Run the evaluation set and document failure cases. | E-105 | HIGH | 2026-07-23 | 2026-07-13 | COMPLETED | EVID-0183 | Knowledge Management 25
ACT-0184 | P-020 | R-0098 | Update the risk response and obtain owner approval. | E-058 | LOW | 2026-09-03 | 2026-08-25 | COMPLETED | EVID-0184 | Training Digitization 20
ACT-0185 | P-024 | R-0165 | Run the evaluation set and document failure cases. | E-218 | HIGH | 2026-10-11 |  | IN_PROGRESS |  | Knowledge Management 24
ACT-0186 | P-023 | R-0274 | Complete independent review of the proposed control. | E-152 | LOW | 2026-10-09 | 2026-09-29 | COMPLETED | EVID-0186 | Supplier Performance Improvement 23
ACT-0187 | P-026 | R-0177 | Complete independent review of the proposed control. | E-085 | MEDIUM | 2026-10-02 | 2026-09-25 | COMPLETED | EVID-0187 | Training Digitization 26
ACT-0188 | P-011 | R-0308 | Run the evaluation set and document failure cases. | E-166 | LOW | 2026-09-10 |  | OPEN |  | Maintenance Planning Enhancement 11
ACT-0189 | P-006 | R-0321 | Run the evaluation set and document failure cases. | E-235 | HIGH | 2026-08-13 | 2026-08-03 | COMPLETED | EVID-0189 | Analytics Enablement 06
ACT-0190 | P-017 | R-0330 | Run the evaluation set and document failure cases. | E-191 | HIGH | 2027-01-13 |  | IN_PROGRESS |  | Analytics Enablement 17
ACT-0191 | P-016 | R-0212 | Run the evaluation set and document failure cases. | E-094 | LOW | 2026-11-16 | 2026-11-12 | COMPLETED | EVID-0191 | Data Quality Improvement 16
ACT-0192 | P-017 | R-0330 | Validate source data and document evidence. | E-060 | LOW | 2026-06-30 | 2026-06-23 | COMPLETED | EVID-0192 | Analytics Enablement 17
ACT-0193 | P-022 | R-0112 | Validate source data and document evidence. | E-035 | HIGH | 2026-11-27 |  | OPEN |  | Data Quality Improvement 22
ACT-0194 | P-008 | R-0285 | Validate source data and document evidence. | E-063 | HIGH | 2026-08-10 | 2026-07-31 | COMPLETED | EVID-0194 | Data Quality Improvement 08
ACT-0195 | P-004 | R-0292 | Validate source data and document evidence. | E-065 | HIGH | 2027-02-05 |  | IN_PROGRESS |  | Knowledge Management 04
ACT-0196 | P-022 | R-0167 | Update the risk response and obtain owner approval. | E-181 | LOW | 2026-08-06 | 2026-07-30 | COMPLETED | EVID-0196 | Data Quality Improvement 22
ACT-0197 | P-015 | R-0376 | Run the evaluation set and document failure cases. | E-213 | LOW | 2026-09-05 | 2026-09-01 | COMPLETED | EVID-0197 | Document Modernization 15
ACT-0198 | P-013 | R-0334 | Complete independent review of the proposed control. | E-220 | LOW | 2026-08-27 |  | OVERDUE |  | Document Modernization 13
ACT-0199 | P-013 | R-0378 | Validate source data and document evidence. | E-031 | HIGH | 2026-12-01 | 2026-12-01 | COMPLETED | EVID-0199 | Document Modernization 13
ACT-0200 | P-024 | R-0017 | Complete independent review of the proposed control. | E-112 | MEDIUM | 2026-07-11 | 2026-07-05 | COMPLETED | EVID-0200 | Knowledge Management 24
ACT-0201 | P-006 | R-0220 | Validate source data and document evidence. | E-011 | MEDIUM | 2026-11-13 |  | IN_PROGRESS |  | Analytics Enablement 06
ACT-0202 | P-022 | R-0316 | Validate source data and document evidence. | E-030 | HIGH | 2026-12-16 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0203 | P-017 | R-0403 | Update the risk response and obtain owner approval. | E-014 | LOW | 2026-12-05 |  | OPEN |  | Analytics Enablement 17
ACT-0204 | P-027 | R-0042 | Run the evaluation set and document failure cases. | E-146 | HIGH | 2026-12-12 | 2026-12-12 | COMPLETED | EVID-0204 | Supplier Performance Improvement 27
ACT-0205 | P-028 | R-0018 | Run the evaluation set and document failure cases. | E-123 | HIGH | 2026-10-24 |  | OVERDUE |  | Document Modernization 28
ACT-0206 | P-001 | R-0283 | Validate source data and document evidence. | E-054 | HIGH | 2026-06-28 |  | OPEN |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0207 | P-021 | R-0345 | Update the risk response and obtain owner approval. | E-179 | LOW | 2026-12-11 |  | OPEN |  | Data Quality Improvement 21
ACT-0208 | P-013 | R-0412 | Complete independent review of the proposed control. | E-048 | HIGH | 2026-09-02 | 2026-09-01 | COMPLETED | EVID-0208 | Document Modernization 13
ACT-0209 | P-017 | R-0050 | Complete independent review of the proposed control. | E-122 | LOW | 2027-01-17 | 2027-01-12 | COMPLETED | EVID-0209 | Analytics Enablement 17
ACT-0210 | P-011 | R-0073 | Run the evaluation set and document failure cases. | E-160 | LOW | 2026-09-17 |  | OVERDUE |  | Maintenance Planning Enhancement 11
ACT-0211 | P-026 | R-0065 | Complete independent review of the proposed control. | E-213 | MEDIUM | 2027-01-06 | 2026-12-29 | COMPLETED | EVID-0211 | Training Digitization 26
ACT-0212 | P-006 | R-0102 | Run the evaluation set and document failure cases. | E-010 | LOW | 2026-11-07 | 2026-10-29 | COMPLETED | EVID-0212 | Analytics Enablement 06
ACT-0213 | P-026 | R-0094 | Complete independent review of the proposed control. | E-218 | LOW | 2026-08-14 |  | OPEN |  | Training Digitization 26
ACT-0214 | P-005 | R-0338 | Complete independent review of the proposed control. | E-026 | LOW | 2026-08-30 | 2026-08-23 | COMPLETED | EVID-0214 | Maintenance Planning Enhancement 05
ACT-0215 | P-025 | R-0003 | Complete independent review of the proposed control. | E-091 | MEDIUM | 2026-08-15 | 2026-08-10 | COMPLETED | EVID-0215 | Knowledge Management 25
ACT-0216 | P-015 | R-0354 | Run the evaluation set and document failure cases. | E-022 | LOW | 2026-06-02 | 2026-05-25 | COMPLETED | EVID-0216 | Document Modernization 15
ACT-0217 | P-018 | R-0179 | Complete independent review of the proposed control. | E-210 | HIGH | 2026-12-01 |  | OVERDUE |  | Document Modernization 18
ACT-0218 | P-009 | R-0387 | Update the risk response and obtain owner approval. | E-025 | HIGH | 2026-07-31 |  | OPEN |  | Training Digitization 09
ACT-0219 | P-017 | R-0015 | Complete independent review of the proposed control. | E-188 | MEDIUM | 2027-01-03 | 2026-12-30 | COMPLETED | EVID-0219 | Analytics Enablement 17
ACT-0220 | P-002 | R-0121 | Validate source data and document evidence. | E-164 | LOW | 2027-01-21 |  | IN_PROGRESS |  | Risk Reporting Automation 02
ACT-0221 | P-022 | R-0029 | Complete independent review of the proposed control. | E-237 | HIGH | 2027-02-18 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0222 | P-016 | R-0201 | Run the evaluation set and document failure cases. | E-028 | LOW | 2026-10-14 | 2026-10-13 | COMPLETED | EVID-0222 | Data Quality Improvement 16
ACT-0223 | P-006 | R-0006 | Complete independent review of the proposed control. | E-168 | LOW | 2027-01-09 |  | IN_PROGRESS |  | Analytics Enablement 06
ACT-0224 | P-008 | R-0026 | Update the risk response and obtain owner approval. | E-236 | LOW | 2026-12-11 | 2026-12-02 | COMPLETED | EVID-0224 | Data Quality Improvement 08
ACT-0225 | P-001 | R-0199 | Complete independent review of the proposed control. | E-171 | MEDIUM | 2026-08-28 |  | IN_PROGRESS |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0226 | P-021 | R-0107 | Update the risk response and obtain owner approval. | E-165 | HIGH | 2026-06-15 |  | OPEN |  | Data Quality Improvement 21
ACT-0227 | P-006 | R-0419 | Validate source data and document evidence. | E-081 | HIGH | 2027-01-25 |  | OPEN |  | Analytics Enablement 06
ACT-0228 | P-028 | R-0115 | Run the evaluation set and document failure cases. | E-118 | HIGH | 2026-07-09 |  | OPEN |  | Document Modernization 28
ACT-0229 | P-022 | R-0411 | Update the risk response and obtain owner approval. | E-092 | HIGH | 2027-01-30 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0230 | P-002 | R-0004 | Validate source data and document evidence. | E-096 | MEDIUM | 2027-01-20 |  | IN_PROGRESS |  | Risk Reporting Automation 02
ACT-0231 | P-003 | R-0266 | Update the risk response and obtain owner approval. | E-203 | MEDIUM | 2026-07-11 | 2026-07-08 | COMPLETED | EVID-0231 | Training Digitization 03
ACT-0232 | P-013 | R-0311 | Run the evaluation set and document failure cases. | E-201 | LOW | 2026-12-10 | 2026-12-04 | COMPLETED | EVID-0232 | Document Modernization 13
ACT-0233 | P-005 | R-0415 | Update the risk response and obtain owner approval. | E-003 | MEDIUM | 2026-11-04 |  | OPEN |  | Maintenance Planning Enhancement 05
ACT-0234 | P-022 | R-0045 | Validate source data and document evidence. | E-054 | LOW | 2026-08-09 | 2026-08-05 | COMPLETED | EVID-0234 | Data Quality Improvement 22
ACT-0235 | P-006 | R-0222 | Complete independent review of the proposed control. | E-221 | MEDIUM | 2026-05-31 | 2026-05-28 | COMPLETED | EVID-0235 | Analytics Enablement 06
ACT-0236 | P-011 | R-0308 | Complete independent review of the proposed control. | E-188 | HIGH | 2026-12-10 |  | OPEN |  | Maintenance Planning Enhancement 11
ACT-0237 | P-014 | R-0013 | Update the risk response and obtain owner approval. | E-163 | MEDIUM | 2027-02-11 | 2027-02-01 | COMPLETED | EVID-0237 | Analytics Enablement 14
ACT-0238 | P-006 | R-0114 | Update the risk response and obtain owner approval. | E-210 | LOW | 2026-11-16 |  | IN_PROGRESS |  | Analytics Enablement 06
ACT-0239 | P-006 | R-0295 | Update the risk response and obtain owner approval. | E-190 | LOW | 2026-07-04 |  | IN_PROGRESS |  | Analytics Enablement 06
ACT-0240 | P-021 | R-0254 | Update the risk response and obtain owner approval. | E-184 | LOW | 2026-06-10 | 2026-06-03 | COMPLETED | EVID-0240 | Data Quality Improvement 21
ACT-0241 | P-022 | R-0371 | Update the risk response and obtain owner approval. | E-010 | LOW | 2026-10-25 | 2026-10-18 | COMPLETED | EVID-0241 | Data Quality Improvement 22
ACT-0242 | P-005 | R-0338 | Update the risk response and obtain owner approval. | E-092 | HIGH | 2027-01-02 |  | OPEN |  | Maintenance Planning Enhancement 05
ACT-0243 | P-010 | R-0169 | Run the evaluation set and document failure cases. | E-171 | HIGH | 2026-12-10 |  | OPEN |  | Document Modernization 10
ACT-0244 | P-008 | R-0346 | Validate source data and document evidence. | E-142 | MEDIUM | 2027-02-06 |  | IN_PROGRESS |  | Data Quality Improvement 08
ACT-0245 | P-012 | R-0016 | Complete independent review of the proposed control. | E-085 | LOW | 2027-01-01 | 2026-12-22 | COMPLETED | EVID-0245 | Document Modernization 12
ACT-0246 | P-008 | R-0406 | Complete independent review of the proposed control. | E-053 | LOW | 2026-10-02 |  | OPEN |  | Data Quality Improvement 08
ACT-0247 | P-011 | R-0147 | Update the risk response and obtain owner approval. | E-052 | HIGH | 2026-09-11 | 2026-09-05 | COMPLETED | EVID-0247 | Maintenance Planning Enhancement 11
ACT-0248 | P-010 | R-0169 | Validate source data and document evidence. | E-219 | HIGH | 2026-05-27 |  | OPEN |  | Document Modernization 10
ACT-0249 | P-026 | R-0087 | Update the risk response and obtain owner approval. | E-013 | HIGH | 2026-12-15 |  | OPEN |  | Training Digitization 26
ACT-0250 | P-002 | R-0249 | Run the evaluation set and document failure cases. | E-191 | MEDIUM | 2027-01-21 |  | OVERDUE |  | Risk Reporting Automation 02
ACT-0251 | P-021 | R-0409 | Update the risk response and obtain owner approval. | E-060 | LOW | 2027-01-24 |  | OVERDUE |  | Data Quality Improvement 21
ACT-0252 | P-019 | R-0325 | Complete independent review of the proposed control. | E-071 | LOW | 2026-09-27 |  | OPEN |  | Maintenance Planning Enhancement 19
ACT-0253 | P-009 | R-0082 | Validate source data and document evidence. | E-036 | LOW | 2026-05-27 |  | OVERDUE |  | Training Digitization 09
ACT-0254 | P-011 | R-0350 | Run the evaluation set and document failure cases. | E-146 | HIGH | 2026-12-17 | 2026-12-14 | COMPLETED | EVID-0254 | Maintenance Planning Enhancement 11
ACT-0255 | P-014 | R-0344 | Complete independent review of the proposed control. | E-039 | MEDIUM | 2026-12-19 |  | OPEN |  | Analytics Enablement 14
ACT-0256 | P-017 | R-0050 | Complete independent review of the proposed control. | E-136 | LOW | 2026-11-16 |  | OVERDUE |  | Analytics Enablement 17
ACT-0257 | P-020 | R-0198 | Run the evaluation set and document failure cases. | E-142 | MEDIUM | 2026-10-27 |  | IN_PROGRESS |  | Training Digitization 20
ACT-0258 | P-017 | R-0050 | Complete independent review of the proposed control. | E-131 | MEDIUM | 2026-10-17 |  | IN_PROGRESS |  | Analytics Enablement 17
ACT-0259 | P-019 | R-0410 | Complete independent review of the proposed control. | E-110 | HIGH | 2026-07-22 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 19
ACT-0260 | P-025 | R-0038 | Run the evaluation set and document failure cases. | E-020 | MEDIUM | 2026-06-14 |  | OPEN |  | Knowledge Management 25
ACT-0261 | P-013 | R-0215 | Update the risk response and obtain owner approval. | E-032 | HIGH | 2026-08-20 |  | IN_PROGRESS |  | Document Modernization 13
ACT-0262 | P-022 | R-0096 | Update the risk response and obtain owner approval. | E-005 | HIGH | 2026-06-20 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0263 | P-006 | R-0419 | Update the risk response and obtain owner approval. | E-041 | MEDIUM | 2027-02-20 |  | IN_PROGRESS |  | Analytics Enablement 06
ACT-0264 | P-022 | R-0318 | Validate source data and document evidence. | E-179 | MEDIUM | 2026-12-14 | 2026-12-10 | COMPLETED | EVID-0264 | Data Quality Improvement 22
ACT-0265 | P-020 | R-0275 | Validate source data and document evidence. | E-053 | LOW | 2027-02-20 |  | IN_PROGRESS |  | Training Digitization 20
ACT-0266 | P-018 | R-0207 | Validate source data and document evidence. | E-165 | MEDIUM | 2027-02-08 |  | OPEN |  | Document Modernization 18
ACT-0267 | P-027 | R-0056 | Update the risk response and obtain owner approval. | E-232 | LOW | 2027-01-25 |  | IN_PROGRESS |  | Supplier Performance Improvement 27
ACT-0268 | P-007 | R-0158 | Validate source data and document evidence. | E-159 | HIGH | 2026-12-10 |  | IN_PROGRESS |  | Analytics Enablement 07
ACT-0269 | P-001 | R-0105 | Update the risk response and obtain owner approval. | E-225 | LOW | 2027-01-09 |  | IN_PROGRESS |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0270 | P-026 | R-0268 | Run the evaluation set and document failure cases. | E-169 | LOW | 2027-02-20 | 2027-02-17 | COMPLETED | EVID-0270 | Training Digitization 26
ACT-0271 | P-026 | R-0141 | Validate source data and document evidence. | E-163 | HIGH | 2026-10-03 |  | IN_PROGRESS |  | Training Digitization 26
ACT-0272 | P-008 | R-0285 | Update the risk response and obtain owner approval. | E-037 | LOW | 2027-01-19 | 2027-01-16 | COMPLETED | EVID-0272 | Data Quality Improvement 08
ACT-0273 | P-023 | R-0388 | Validate source data and document evidence. | E-111 | LOW | 2026-09-08 | 2026-08-31 | COMPLETED | EVID-0273 | Supplier Performance Improvement 23
ACT-0274 | P-010 | R-0271 | Update the risk response and obtain owner approval. | E-223 | MEDIUM | 2026-09-09 | 2026-09-01 | COMPLETED | EVID-0274 | Document Modernization 10
ACT-0275 | P-015 | R-0376 | Validate source data and document evidence. | E-005 | LOW | 2026-12-01 | 2026-11-27 | COMPLETED | EVID-0275 | Document Modernization 15
ACT-0276 | P-020 | R-0275 | Run the evaluation set and document failure cases. | E-132 | LOW | 2026-11-04 | 2026-11-04 | COMPLETED | EVID-0276 | Training Digitization 20
ACT-0277 | P-018 | R-0119 | Update the risk response and obtain owner approval. | E-127 | LOW | 2026-10-06 | 2026-10-05 | COMPLETED | EVID-0277 | Document Modernization 18
ACT-0278 | P-024 | R-0272 | Run the evaluation set and document failure cases. | E-054 | HIGH | 2026-10-10 |  | OPEN |  | Knowledge Management 24
ACT-0279 | P-007 | R-0238 | Validate source data and document evidence. | E-197 | LOW | 2026-10-01 |  | OPEN |  | Analytics Enablement 07
ACT-0280 | P-028 | R-0115 | Validate source data and document evidence. | E-128 | MEDIUM | 2026-06-10 | 2026-06-06 | COMPLETED | EVID-0280 | Document Modernization 28
ACT-0281 | P-007 | R-0074 | Run the evaluation set and document failure cases. | E-181 | MEDIUM | 2026-11-18 | 2026-11-18 | COMPLETED | EVID-0281 | Analytics Enablement 07
ACT-0282 | P-021 | R-0359 | Run the evaluation set and document failure cases. | E-142 | HIGH | 2026-05-27 | 2026-05-27 | COMPLETED | EVID-0282 | Data Quality Improvement 21
ACT-0283 | P-017 | R-0234 | Run the evaluation set and document failure cases. | E-152 | HIGH | 2026-07-29 |  | OVERDUE |  | Analytics Enablement 17
ACT-0284 | P-001 | R-0393 | Update the risk response and obtain owner approval. | E-152 | LOW | 2026-06-03 |  | OPEN |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0285 | P-027 | R-0284 | Validate source data and document evidence. | E-011 | MEDIUM | 2026-10-20 |  | OPEN |  | Supplier Performance Improvement 27
ACT-0286 | P-014 | R-0314 | Run the evaluation set and document failure cases. | E-217 | MEDIUM | 2026-08-04 | 2026-08-03 | COMPLETED | EVID-0286 | Analytics Enablement 14
ACT-0287 | P-025 | R-0243 | Complete independent review of the proposed control. | E-009 | LOW | 2026-12-18 | 2026-12-11 | COMPLETED | EVID-0287 | Knowledge Management 25
ACT-0288 | P-006 | R-0335 | Run the evaluation set and document failure cases. | E-225 | LOW | 2026-12-25 |  | IN_PROGRESS |  | Analytics Enablement 06
ACT-0289 | P-010 | R-0194 | Validate source data and document evidence. | E-191 | HIGH | 2027-01-15 |  | OPEN |  | Document Modernization 10
ACT-0290 | P-023 | R-0009 | Run the evaluation set and document failure cases. | E-146 | LOW | 2027-02-01 |  | OPEN |  | Supplier Performance Improvement 23
ACT-0291 | P-013 | R-0412 | Update the risk response and obtain owner approval. | E-123 | LOW | 2026-11-10 |  | IN_PROGRESS |  | Document Modernization 13
ACT-0292 | P-016 | R-0202 | Update the risk response and obtain owner approval. | E-197 | HIGH | 2026-07-04 | 2026-07-04 | COMPLETED | EVID-0292 | Data Quality Improvement 16
ACT-0293 | P-019 | R-0028 | Complete independent review of the proposed control. | E-048 | LOW | 2026-09-23 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 19
ACT-0294 | P-004 | R-0298 | Complete independent review of the proposed control. | E-165 | HIGH | 2026-10-13 |  | IN_PROGRESS |  | Knowledge Management 04
ACT-0295 | P-015 | R-0324 | Run the evaluation set and document failure cases. | E-188 | HIGH | 2026-06-01 | 2026-05-23 | COMPLETED | EVID-0295 | Document Modernization 15
ACT-0296 | P-005 | R-0012 | Complete independent review of the proposed control. | E-106 | LOW | 2026-11-03 | 2026-11-03 | COMPLETED | EVID-0296 | Maintenance Planning Enhancement 05
ACT-0297 | P-012 | R-0255 | Validate source data and document evidence. | E-070 | MEDIUM | 2027-02-18 |  | OPEN |  | Document Modernization 12
ACT-0298 | P-022 | R-0411 | Complete independent review of the proposed control. | E-120 | MEDIUM | 2026-08-17 | 2026-08-12 | COMPLETED | EVID-0298 | Data Quality Improvement 22
ACT-0299 | P-025 | R-0138 | Complete independent review of the proposed control. | E-031 | MEDIUM | 2026-08-19 | 2026-08-11 | COMPLETED | EVID-0299 | Knowledge Management 25
ACT-0300 | P-014 | R-0013 | Validate source data and document evidence. | E-239 | LOW | 2026-06-24 | 2026-06-21 | COMPLETED | EVID-0300 | Analytics Enablement 14
ACT-0301 | P-009 | R-0137 | Run the evaluation set and document failure cases. | E-175 | HIGH | 2026-07-17 | 2026-07-17 | COMPLETED | EVID-0301 | Training Digitization 09
ACT-0302 | P-021 | R-0157 | Validate source data and document evidence. | E-152 | LOW | 2026-10-05 | 2026-10-02 | COMPLETED | EVID-0302 | Data Quality Improvement 21
ACT-0303 | P-010 | R-0145 | Run the evaluation set and document failure cases. | E-047 | MEDIUM | 2026-12-27 |  | IN_PROGRESS |  | Document Modernization 10
ACT-0304 | P-018 | R-0085 | Update the risk response and obtain owner approval. | E-189 | LOW | 2026-09-22 |  | OPEN |  | Document Modernization 18
ACT-0305 | P-017 | R-0234 | Update the risk response and obtain owner approval. | E-013 | HIGH | 2026-08-13 | 2026-08-06 | COMPLETED | EVID-0305 | Analytics Enablement 17
ACT-0306 | P-022 | R-0110 | Validate source data and document evidence. | E-229 | MEDIUM | 2026-08-20 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0307 | P-020 | R-0122 | Update the risk response and obtain owner approval. | E-150 | HIGH | 2026-08-12 | 2026-08-05 | COMPLETED | EVID-0307 | Training Digitization 20
ACT-0308 | P-011 | R-0340 | Run the evaluation set and document failure cases. | E-069 | HIGH | 2026-08-03 | 2026-07-30 | COMPLETED | EVID-0308 | Maintenance Planning Enhancement 11
ACT-0309 | P-010 | R-0025 | Validate source data and document evidence. | E-090 | MEDIUM | 2026-08-27 |  | OPEN |  | Document Modernization 10
ACT-0310 | P-010 | R-0297 | Update the risk response and obtain owner approval. | E-120 | MEDIUM | 2027-02-12 |  | IN_PROGRESS |  | Document Modernization 10
ACT-0311 | P-002 | R-0090 | Run the evaluation set and document failure cases. | E-205 | MEDIUM | 2026-08-28 | 2026-08-23 | COMPLETED | EVID-0311 | Risk Reporting Automation 02
ACT-0312 | P-009 | R-0063 | Run the evaluation set and document failure cases. | E-015 | HIGH | 2026-09-03 | 2026-08-27 | COMPLETED | EVID-0312 | Training Digitization 09
ACT-0313 | P-005 | R-0052 | Validate source data and document evidence. | E-084 | LOW | 2026-07-18 | 2026-07-16 | COMPLETED | EVID-0313 | Maintenance Planning Enhancement 05
ACT-0314 | P-016 | R-0201 | Validate source data and document evidence. | E-076 | MEDIUM | 2026-06-27 |  | OPEN |  | Data Quality Improvement 16
ACT-0315 | P-005 | R-0276 | Update the risk response and obtain owner approval. | E-004 | MEDIUM | 2026-11-25 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 05
ACT-0316 | P-015 | R-0081 | Validate source data and document evidence. | E-099 | HIGH | 2026-12-25 | 2026-12-18 | COMPLETED | EVID-0316 | Document Modernization 15
ACT-0317 | P-020 | R-0301 | Update the risk response and obtain owner approval. | E-056 | LOW | 2027-01-24 | 2027-01-16 | COMPLETED | EVID-0317 | Training Digitization 20
ACT-0318 | P-015 | R-0376 | Validate source data and document evidence. | E-204 | HIGH | 2026-11-01 |  | OPEN |  | Document Modernization 15
ACT-0319 | P-022 | R-0411 | Complete independent review of the proposed control. | E-061 | MEDIUM | 2027-01-09 |  | OVERDUE |  | Data Quality Improvement 22
ACT-0320 | P-011 | R-0308 | Complete independent review of the proposed control. | E-185 | HIGH | 2026-08-10 | 2026-08-08 | COMPLETED | EVID-0320 | Maintenance Planning Enhancement 11
ACT-0321 | P-014 | R-0223 | Update the risk response and obtain owner approval. | E-070 | LOW | 2026-07-28 |  | IN_PROGRESS |  | Analytics Enablement 14
ACT-0322 | P-006 | R-0220 | Complete independent review of the proposed control. | E-203 | LOW | 2026-09-07 |  | OPEN |  | Analytics Enablement 06
ACT-0323 | P-006 | R-0066 | Validate source data and document evidence. | E-093 | LOW | 2026-11-21 |  | IN_PROGRESS |  | Analytics Enablement 06
ACT-0324 | P-024 | R-0165 | Update the risk response and obtain owner approval. | E-097 | LOW | 2027-02-21 |  | OVERDUE |  | Knowledge Management 24
ACT-0325 | P-019 | R-0086 | Validate source data and document evidence. | E-068 | MEDIUM | 2027-02-21 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 19
ACT-0326 | P-028 | R-0018 | Validate source data and document evidence. | E-104 | MEDIUM | 2026-07-26 |  | OPEN |  | Document Modernization 28
ACT-0327 | P-008 | R-0319 | Run the evaluation set and document failure cases. | E-131 | LOW | 2026-07-02 |  | OPEN |  | Data Quality Improvement 08
ACT-0328 | P-016 | R-0328 | Complete independent review of the proposed control. | E-186 | HIGH | 2027-01-22 |  | OVERDUE |  | Data Quality Improvement 16
ACT-0329 | P-005 | R-0415 | Complete independent review of the proposed control. | E-001 | MEDIUM | 2026-07-09 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 05
ACT-0330 | P-013 | R-0036 | Update the risk response and obtain owner approval. | E-112 | MEDIUM | 2026-06-04 |  | OPEN |  | Document Modernization 13
ACT-0331 | P-010 | R-0025 | Validate source data and document evidence. | E-115 | HIGH | 2027-01-19 |  | IN_PROGRESS |  | Document Modernization 10
ACT-0332 | P-028 | R-0339 | Run the evaluation set and document failure cases. | E-144 | LOW | 2027-02-21 |  | OPEN |  | Document Modernization 28
ACT-0333 | P-024 | R-0248 | Validate source data and document evidence. | E-078 | LOW | 2026-12-06 |  | OPEN |  | Knowledge Management 24
ACT-0334 | P-027 | R-0042 | Update the risk response and obtain owner approval. | E-029 | HIGH | 2026-09-07 |  | IN_PROGRESS |  | Supplier Performance Improvement 27
ACT-0335 | P-008 | R-0408 | Run the evaluation set and document failure cases. | E-100 | HIGH | 2026-09-24 | 2026-09-16 | COMPLETED | EVID-0335 | Data Quality Improvement 08
ACT-0336 | P-024 | R-0165 | Complete independent review of the proposed control. | E-071 | LOW | 2026-12-19 | 2026-12-12 | COMPLETED | EVID-0336 | Knowledge Management 24
ACT-0337 | P-021 | R-0254 | Complete independent review of the proposed control. | E-091 | HIGH | 2026-12-20 | 2026-12-16 | COMPLETED | EVID-0337 | Data Quality Improvement 21
ACT-0338 | P-007 | R-0171 | Validate source data and document evidence. | E-065 | HIGH | 2026-05-29 |  | IN_PROGRESS |  | Analytics Enablement 07
ACT-0339 | P-013 | R-0215 | Update the risk response and obtain owner approval. | E-115 | HIGH | 2026-06-04 |  | OVERDUE |  | Document Modernization 13
ACT-0340 | P-027 | R-0407 | Update the risk response and obtain owner approval. | E-031 | MEDIUM | 2026-12-21 |  | OPEN |  | Supplier Performance Improvement 27
ACT-0341 | P-020 | R-0092 | Validate source data and document evidence. | E-033 | MEDIUM | 2026-06-07 |  | IN_PROGRESS |  | Training Digitization 20
ACT-0342 | P-028 | R-0007 | Update the risk response and obtain owner approval. | E-238 | HIGH | 2026-07-19 | 2026-07-14 | COMPLETED | EVID-0342 | Document Modernization 28
ACT-0343 | P-028 | R-0007 | Validate source data and document evidence. | E-195 | HIGH | 2026-05-28 |  | IN_PROGRESS |  | Document Modernization 28
ACT-0344 | P-010 | R-0195 | Run the evaluation set and document failure cases. | E-146 | MEDIUM | 2026-06-16 | 2026-06-13 | COMPLETED | EVID-0344 | Document Modernization 10
ACT-0345 | P-020 | R-0104 | Update the risk response and obtain owner approval. | E-028 | HIGH | 2026-09-25 |  | IN_PROGRESS |  | Training Digitization 20
ACT-0346 | P-011 | R-0327 | Validate source data and document evidence. | E-187 | HIGH | 2027-01-31 |  | OPEN |  | Maintenance Planning Enhancement 11
ACT-0347 | P-004 | R-0253 | Complete independent review of the proposed control. | E-104 | LOW | 2027-02-17 |  | OPEN |  | Knowledge Management 04
ACT-0348 | P-005 | R-0369 | Complete independent review of the proposed control. | E-122 | LOW | 2026-08-23 | 2026-08-16 | COMPLETED | EVID-0348 | Maintenance Planning Enhancement 05
ACT-0349 | P-015 | R-0240 | Update the risk response and obtain owner approval. | E-208 | LOW | 2026-10-11 | 2026-10-06 | COMPLETED | EVID-0349 | Document Modernization 15
ACT-0350 | P-027 | R-0093 | Validate source data and document evidence. | E-193 | HIGH | 2026-11-20 | 2026-11-17 | COMPLETED | EVID-0350 | Supplier Performance Improvement 27
ACT-0351 | P-019 | R-0389 | Complete independent review of the proposed control. | E-147 | MEDIUM | 2026-09-03 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 19
ACT-0352 | P-028 | R-0225 | Update the risk response and obtain owner approval. | E-049 | LOW | 2026-07-16 |  | OPEN |  | Document Modernization 28
ACT-0353 | P-028 | R-0007 | Run the evaluation set and document failure cases. | E-139 | LOW | 2026-10-05 |  | IN_PROGRESS |  | Document Modernization 28
ACT-0354 | P-021 | R-0144 | Update the risk response and obtain owner approval. | E-098 | LOW | 2026-11-25 |  | OVERDUE |  | Data Quality Improvement 21
ACT-0355 | P-010 | R-0271 | Update the risk response and obtain owner approval. | E-162 | HIGH | 2026-09-12 |  | OPEN |  | Document Modernization 10
ACT-0356 | P-015 | R-0170 | Validate source data and document evidence. | E-232 | HIGH | 2026-10-20 | 2026-10-18 | COMPLETED | EVID-0356 | Document Modernization 15
ACT-0357 | P-022 | R-0348 | Complete independent review of the proposed control. | E-030 | HIGH | 2027-01-11 | 2027-01-09 | COMPLETED | EVID-0357 | Data Quality Improvement 22
ACT-0358 | P-021 | R-0020 | Update the risk response and obtain owner approval. | E-220 | MEDIUM | 2027-01-12 |  | OPEN |  | Data Quality Improvement 21
ACT-0359 | P-020 | R-0100 | Validate source data and document evidence. | E-027 | LOW | 2026-09-28 | 2026-09-19 | COMPLETED | EVID-0359 | Training Digitization 20
ACT-0360 | P-002 | R-0168 | Validate source data and document evidence. | E-038 | MEDIUM | 2027-02-06 |  | OVERDUE |  | Risk Reporting Automation 02
ACT-0361 | P-009 | R-0063 | Validate source data and document evidence. | E-081 | LOW | 2026-08-17 | 2026-08-15 | COMPLETED | EVID-0361 | Training Digitization 09
ACT-0362 | P-009 | R-0133 | Run the evaluation set and document failure cases. | E-024 | MEDIUM | 2027-02-13 |  | IN_PROGRESS |  | Training Digitization 09
ACT-0363 | P-005 | R-0128 | Update the risk response and obtain owner approval. | E-145 | HIGH | 2026-12-05 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 05
ACT-0364 | P-004 | R-0091 | Run the evaluation set and document failure cases. | E-171 | LOW | 2026-10-04 |  | OPEN |  | Knowledge Management 04
ACT-0365 | P-010 | R-0037 | Validate source data and document evidence. | E-210 | HIGH | 2026-07-22 |  | OPEN |  | Document Modernization 10
ACT-0366 | P-013 | R-0311 | Update the risk response and obtain owner approval. | E-012 | HIGH | 2027-02-04 | 2027-01-31 | COMPLETED | EVID-0366 | Document Modernization 13
ACT-0367 | P-011 | R-0156 | Update the risk response and obtain owner approval. | E-102 | LOW | 2026-09-15 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 11
ACT-0368 | P-009 | R-0063 | Run the evaluation set and document failure cases. | E-027 | MEDIUM | 2027-02-18 |  | IN_PROGRESS |  | Training Digitization 09
ACT-0369 | P-002 | R-0004 | Complete independent review of the proposed control. | E-205 | MEDIUM | 2027-02-05 | 2027-01-31 | COMPLETED | EVID-0369 | Risk Reporting Automation 02
ACT-0370 | P-014 | R-0153 | Complete independent review of the proposed control. | E-200 | LOW | 2026-10-18 |  | IN_PROGRESS |  | Analytics Enablement 14
ACT-0371 | P-019 | R-0414 | Validate source data and document evidence. | E-111 | MEDIUM | 2026-11-26 |  | OVERDUE |  | Maintenance Planning Enhancement 19
ACT-0372 | P-014 | R-0013 | Run the evaluation set and document failure cases. | E-218 | MEDIUM | 2027-02-11 |  | IN_PROGRESS |  | Analytics Enablement 14
ACT-0373 | P-004 | R-0353 | Update the risk response and obtain owner approval. | E-155 | LOW | 2026-09-20 | 2026-09-20 | COMPLETED | EVID-0373 | Knowledge Management 04
ACT-0374 | P-023 | R-0274 | Run the evaluation set and document failure cases. | E-146 | HIGH | 2027-01-11 |  | IN_PROGRESS |  | Supplier Performance Improvement 23
ACT-0375 | P-023 | R-0307 | Validate source data and document evidence. | E-240 | MEDIUM | 2026-06-29 |  | OPEN |  | Supplier Performance Improvement 23
ACT-0376 | P-022 | R-0181 | Run the evaluation set and document failure cases. | E-148 | LOW | 2027-02-07 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0377 | P-022 | R-0342 | Run the evaluation set and document failure cases. | E-040 | MEDIUM | 2026-12-23 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0378 | P-007 | R-0416 | Run the evaluation set and document failure cases. | E-005 | LOW | 2026-11-26 |  | OVERDUE |  | Analytics Enablement 07
ACT-0379 | P-007 | R-0384 | Run the evaluation set and document failure cases. | E-147 | HIGH | 2026-08-23 | 2026-08-19 | COMPLETED | EVID-0379 | Analytics Enablement 07
ACT-0380 | P-016 | R-0202 | Complete independent review of the proposed control. | E-133 | HIGH | 2026-12-04 | 2026-12-03 | COMPLETED | EVID-0380 | Data Quality Improvement 16
ACT-0381 | P-008 | R-0118 | Run the evaluation set and document failure cases. | E-193 | MEDIUM | 2026-09-18 |  | OPEN |  | Data Quality Improvement 08
ACT-0382 | P-012 | R-0062 | Complete independent review of the proposed control. | E-112 | LOW | 2026-07-25 |  | IN_PROGRESS |  | Document Modernization 12
ACT-0383 | P-011 | R-0327 | Run the evaluation set and document failure cases. | E-025 | LOW | 2026-06-09 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 11
ACT-0384 | P-024 | R-0213 | Validate source data and document evidence. | E-196 | HIGH | 2027-02-13 | 2027-02-05 | COMPLETED | EVID-0384 | Knowledge Management 24
ACT-0385 | P-021 | R-0166 | Validate source data and document evidence. | E-056 | HIGH | 2026-07-14 |  | OPEN |  | Data Quality Improvement 21
ACT-0386 | P-026 | R-0103 | Update the risk response and obtain owner approval. | E-030 | HIGH | 2026-08-29 |  | OPEN |  | Training Digitization 26
ACT-0387 | P-017 | R-0089 | Validate source data and document evidence. | E-137 | HIGH | 2027-01-25 |  | OPEN |  | Analytics Enablement 17
ACT-0388 | P-018 | R-0068 | Complete independent review of the proposed control. | E-016 | HIGH | 2026-09-11 | 2026-09-10 | COMPLETED | EVID-0388 | Document Modernization 18
ACT-0389 | P-024 | R-0259 | Validate source data and document evidence. | E-163 | LOW | 2026-06-19 | 2026-06-17 | COMPLETED | EVID-0389 | Knowledge Management 24
ACT-0390 | P-007 | R-0074 | Validate source data and document evidence. | E-028 | MEDIUM | 2026-09-11 | 2026-09-10 | COMPLETED | EVID-0390 | Analytics Enablement 07
ACT-0391 | P-002 | R-0224 | Complete independent review of the proposed control. | E-176 | MEDIUM | 2026-08-25 | 2026-08-23 | COMPLETED | EVID-0391 | Risk Reporting Automation 02
ACT-0392 | P-001 | R-0184 | Complete independent review of the proposed control. | E-227 | MEDIUM | 2026-09-14 | 2026-09-11 | COMPLETED | EVID-0392 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0393 | P-027 | R-0394 | Validate source data and document evidence. | E-002 | HIGH | 2027-01-05 |  | OPEN |  | Supplier Performance Improvement 27
ACT-0394 | P-008 | R-0346 | Update the risk response and obtain owner approval. | E-040 | HIGH | 2027-02-15 |  | OPEN |  | Data Quality Improvement 08
ACT-0395 | P-001 | R-0106 | Run the evaluation set and document failure cases. | E-048 | MEDIUM | 2026-11-11 |  | IN_PROGRESS |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0396 | P-019 | R-0162 | Update the risk response and obtain owner approval. | E-129 | MEDIUM | 2027-02-01 | 2027-01-29 | COMPLETED | EVID-0396 | Maintenance Planning Enhancement 19
ACT-0397 | P-028 | R-0322 | Complete independent review of the proposed control. | E-060 | MEDIUM | 2026-08-07 | 2026-08-03 | COMPLETED | EVID-0397 | Document Modernization 28
ACT-0398 | P-026 | R-0094 | Run the evaluation set and document failure cases. | E-172 | LOW | 2026-07-09 |  | OPEN |  | Training Digitization 26
ACT-0399 | P-014 | R-0390 | Validate source data and document evidence. | E-014 | LOW | 2027-02-18 | 2027-02-17 | COMPLETED | EVID-0399 | Analytics Enablement 14
ACT-0400 | P-013 | R-0391 | Run the evaluation set and document failure cases. | E-078 | LOW | 2026-09-07 |  | OPEN |  | Document Modernization 13
ACT-0401 | P-022 | R-0045 | Validate source data and document evidence. | E-172 | MEDIUM | 2027-01-01 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0402 | P-003 | R-0420 | Run the evaluation set and document failure cases. | E-192 | LOW | 2027-01-30 |  | IN_PROGRESS |  | Training Digitization 03
ACT-0403 | P-004 | R-0091 | Complete independent review of the proposed control. | E-110 | LOW | 2026-12-10 |  | IN_PROGRESS |  | Knowledge Management 04
ACT-0404 | P-001 | R-0184 | Validate source data and document evidence. | E-199 | LOW | 2026-10-04 | 2026-10-04 | COMPLETED | EVID-0404 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0405 | P-024 | R-0213 | Run the evaluation set and document failure cases. | E-222 | HIGH | 2027-01-04 |  | IN_PROGRESS |  | Knowledge Management 24
ACT-0406 | P-026 | R-0094 | Run the evaluation set and document failure cases. | E-189 | HIGH | 2026-06-13 | 2026-06-05 | COMPLETED | EVID-0406 | Training Digitization 26
ACT-0407 | P-012 | R-0255 | Validate source data and document evidence. | E-074 | HIGH | 2026-10-19 | 2026-10-10 | COMPLETED | EVID-0407 | Document Modernization 12
ACT-0408 | P-014 | R-0071 | Update the risk response and obtain owner approval. | E-154 | MEDIUM | 2026-09-09 | 2026-09-09 | COMPLETED | EVID-0408 | Analytics Enablement 14
ACT-0409 | P-002 | R-0168 | Validate source data and document evidence. | E-076 | HIGH | 2026-08-24 |  | OVERDUE |  | Risk Reporting Automation 02
ACT-0410 | P-023 | R-0034 | Complete independent review of the proposed control. | E-145 | MEDIUM | 2026-08-10 |  | OPEN |  | Supplier Performance Improvement 23
ACT-0411 | P-005 | R-0276 | Update the risk response and obtain owner approval. | E-182 | HIGH | 2026-09-29 | 2026-09-28 | COMPLETED | EVID-0411 | Maintenance Planning Enhancement 05
ACT-0412 | P-028 | R-0317 | Validate source data and document evidence. | E-189 | LOW | 2026-10-10 | 2026-10-03 | COMPLETED | EVID-0412 | Document Modernization 28
ACT-0413 | P-008 | R-0319 | Run the evaluation set and document failure cases. | E-067 | HIGH | 2026-10-27 |  | IN_PROGRESS |  | Data Quality Improvement 08
ACT-0414 | P-025 | R-0138 | Run the evaluation set and document failure cases. | E-034 | LOW | 2027-01-03 |  | OPEN |  | Knowledge Management 25
ACT-0415 | P-013 | R-0072 | Complete independent review of the proposed control. | E-142 | LOW | 2026-08-18 |  | OPEN |  | Document Modernization 13
ACT-0416 | P-025 | R-0337 | Update the risk response and obtain owner approval. | E-109 | HIGH | 2026-08-05 |  | IN_PROGRESS |  | Knowledge Management 25
ACT-0417 | P-012 | R-0149 | Update the risk response and obtain owner approval. | E-224 | HIGH | 2026-06-19 |  | OVERDUE |  | Document Modernization 12
ACT-0418 | P-026 | R-0103 | Update the risk response and obtain owner approval. | E-042 | LOW | 2027-01-20 |  | IN_PROGRESS |  | Training Digitization 26
ACT-0419 | P-013 | R-0378 | Complete independent review of the proposed control. | E-183 | LOW | 2027-01-01 |  | OPEN |  | Document Modernization 13
ACT-0420 | P-026 | R-0177 | Validate source data and document evidence. | E-193 | HIGH | 2026-09-03 | 2026-09-01 | COMPLETED | EVID-0420 | Training Digitization 26
ACT-0421 | P-022 | R-0318 | Run the evaluation set and document failure cases. | E-194 | LOW | 2026-07-16 |  | OPEN |  | Data Quality Improvement 22
ACT-0422 | P-020 | R-0301 | Run the evaluation set and document failure cases. | E-080 | MEDIUM | 2027-01-03 |  | OVERDUE |  | Training Digitization 20
ACT-0423 | P-010 | R-0271 | Validate source data and document evidence. | E-020 | LOW | 2026-08-03 |  | OVERDUE |  | Document Modernization 10
ACT-0424 | P-018 | R-0097 | Complete independent review of the proposed control. | E-167 | HIGH | 2026-11-10 |  | OPEN |  | Document Modernization 18
ACT-0425 | P-017 | R-0352 | Run the evaluation set and document failure cases. | E-012 | HIGH | 2026-07-28 | 2026-07-25 | COMPLETED | EVID-0425 | Analytics Enablement 17
ACT-0426 | P-026 | R-0094 | Update the risk response and obtain owner approval. | E-143 | HIGH | 2027-01-18 | 2027-01-08 | COMPLETED | EVID-0426 | Training Digitization 26
ACT-0427 | P-014 | R-0247 | Update the risk response and obtain owner approval. | E-156 | HIGH | 2027-02-02 | 2027-01-31 | COMPLETED | EVID-0427 | Analytics Enablement 14
ACT-0428 | P-008 | R-0134 | Update the risk response and obtain owner approval. | E-019 | LOW | 2026-06-20 | 2026-06-12 | COMPLETED | EVID-0428 | Data Quality Improvement 08
ACT-0429 | P-018 | R-0209 | Complete independent review of the proposed control. | E-027 | MEDIUM | 2026-06-03 | 2026-05-30 | COMPLETED | EVID-0429 | Document Modernization 18
ACT-0430 | P-026 | R-0208 | Update the risk response and obtain owner approval. | E-129 | LOW | 2026-06-26 |  | IN_PROGRESS |  | Training Digitization 26
ACT-0431 | P-007 | R-0031 | Complete independent review of the proposed control. | E-237 | LOW | 2026-11-09 | 2026-11-05 | COMPLETED | EVID-0431 | Analytics Enablement 07
ACT-0432 | P-024 | R-0259 | Update the risk response and obtain owner approval. | E-161 | HIGH | 2026-09-20 |  | IN_PROGRESS |  | Knowledge Management 24
ACT-0433 | P-004 | R-0150 | Complete independent review of the proposed control. | E-192 | MEDIUM | 2026-06-09 | 2026-06-06 | COMPLETED | EVID-0433 | Knowledge Management 04
ACT-0434 | P-026 | R-0094 | Update the risk response and obtain owner approval. | E-159 | LOW | 2026-11-02 |  | OPEN |  | Training Digitization 26
ACT-0435 | P-025 | R-0337 | Run the evaluation set and document failure cases. | E-082 | MEDIUM | 2026-07-19 | 2026-07-13 | COMPLETED | EVID-0435 | Knowledge Management 25
ACT-0436 | P-010 | R-0132 | Validate source data and document evidence. | E-167 | LOW | 2026-09-05 |  | IN_PROGRESS |  | Document Modernization 10
ACT-0437 | P-027 | R-0373 | Validate source data and document evidence. | E-039 | MEDIUM | 2026-11-06 |  | IN_PROGRESS |  | Supplier Performance Improvement 27
ACT-0438 | P-001 | R-0358 | Update the risk response and obtain owner approval. | E-075 | LOW | 2027-01-07 | 2026-12-28 | COMPLETED | EVID-0438 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0439 | P-024 | R-0017 | Validate source data and document evidence. | E-005 | MEDIUM | 2026-07-20 | 2026-07-15 | COMPLETED | EVID-0439 | Knowledge Management 24
ACT-0440 | P-017 | R-0403 | Validate source data and document evidence. | E-211 | HIGH | 2026-10-27 | 2026-10-23 | COMPLETED | EVID-0440 | Analytics Enablement 17
ACT-0441 | P-013 | R-0078 | Complete independent review of the proposed control. | E-105 | HIGH | 2027-01-23 |  | OPEN |  | Document Modernization 13
ACT-0442 | P-016 | R-0299 | Validate source data and document evidence. | E-111 | HIGH | 2026-10-31 | 2026-10-26 | COMPLETED | EVID-0442 | Data Quality Improvement 16
ACT-0443 | P-020 | R-0198 | Update the risk response and obtain owner approval. | E-081 | MEDIUM | 2027-01-09 |  | OPEN |  | Training Digitization 20
ACT-0444 | P-007 | R-0238 | Complete independent review of the proposed control. | E-167 | HIGH | 2026-07-31 |  | IN_PROGRESS |  | Analytics Enablement 07
ACT-0445 | P-028 | R-0127 | Complete independent review of the proposed control. | E-123 | LOW | 2026-10-26 |  | OPEN |  | Document Modernization 28
ACT-0446 | P-020 | R-0256 | Run the evaluation set and document failure cases. | E-166 | LOW | 2026-10-28 | 2026-10-22 | COMPLETED | EVID-0446 | Training Digitization 20
ACT-0447 | P-003 | R-0417 | Validate source data and document evidence. | E-148 | MEDIUM | 2026-10-07 |  | OPEN |  | Training Digitization 03
ACT-0448 | P-008 | R-0241 | Run the evaluation set and document failure cases. | E-126 | HIGH | 2026-08-31 |  | IN_PROGRESS |  | Data Quality Improvement 08
ACT-0449 | P-023 | R-0009 | Validate source data and document evidence. | E-074 | MEDIUM | 2026-08-15 |  | IN_PROGRESS |  | Supplier Performance Improvement 23
ACT-0450 | P-005 | R-0392 | Run the evaluation set and document failure cases. | E-051 | HIGH | 2027-02-08 | 2027-02-06 | COMPLETED | EVID-0450 | Maintenance Planning Enhancement 05
ACT-0451 | P-001 | R-0148 | Validate source data and document evidence. | E-186 | HIGH | 2026-07-10 | 2026-07-01 | COMPLETED | EVID-0451 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0452 | P-004 | R-0253 | Complete independent review of the proposed control. | E-140 | LOW | 2027-01-23 |  | OPEN |  | Knowledge Management 04
ACT-0453 | P-014 | R-0116 | Run the evaluation set and document failure cases. | E-073 | MEDIUM | 2026-08-22 | 2026-08-18 | COMPLETED | EVID-0453 | Analytics Enablement 14
ACT-0454 | P-028 | R-0225 | Complete independent review of the proposed control. | E-227 | LOW | 2026-09-13 |  | IN_PROGRESS |  | Document Modernization 28
ACT-0455 | P-019 | R-0381 | Validate source data and document evidence. | E-120 | MEDIUM | 2026-11-03 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 19
ACT-0456 | P-022 | R-0411 | Update the risk response and obtain owner approval. | E-026 | HIGH | 2026-10-17 |  | OPEN |  | Data Quality Improvement 22
ACT-0457 | P-020 | R-0100 | Update the risk response and obtain owner approval. | E-115 | HIGH | 2026-06-16 |  | OPEN |  | Training Digitization 20
ACT-0458 | P-014 | R-0390 | Update the risk response and obtain owner approval. | E-041 | LOW | 2026-05-27 | 2026-05-17 | COMPLETED | EVID-0458 | Analytics Enablement 14
ACT-0459 | P-006 | R-0011 | Update the risk response and obtain owner approval. | E-033 | HIGH | 2026-09-01 |  | OPEN |  | Analytics Enablement 06
ACT-0460 | P-026 | R-0216 | Validate source data and document evidence. | E-131 | HIGH | 2026-07-01 |  | IN_PROGRESS |  | Training Digitization 26
ACT-0461 | P-009 | R-0063 | Complete independent review of the proposed control. | E-026 | MEDIUM | 2026-10-24 |  | OPEN |  | Training Digitization 09
ACT-0462 | P-016 | R-0232 | Update the risk response and obtain owner approval. | E-093 | LOW | 2026-06-26 |  | IN_PROGRESS |  | Data Quality Improvement 16
ACT-0463 | P-003 | R-0083 | Validate source data and document evidence. | E-001 | LOW | 2026-09-19 |  | OPEN |  | Training Digitization 03
ACT-0464 | P-004 | R-0331 | Run the evaluation set and document failure cases. | E-067 | HIGH | 2026-10-27 | 2026-10-22 | COMPLETED | EVID-0464 | Knowledge Management 04
ACT-0465 | P-012 | R-0149 | Complete independent review of the proposed control. | E-221 | LOW | 2027-01-19 |  | OPEN |  | Document Modernization 12
ACT-0466 | P-019 | R-0123 | Complete independent review of the proposed control. | E-021 | LOW | 2026-09-30 | 2026-09-22 | COMPLETED | EVID-0466 | Maintenance Planning Enhancement 19
ACT-0467 | P-012 | R-0204 | Update the risk response and obtain owner approval. | E-021 | MEDIUM | 2026-06-04 | 2026-05-25 | COMPLETED | EVID-0467 | Document Modernization 12
ACT-0468 | P-018 | R-0205 | Run the evaluation set and document failure cases. | E-156 | LOW | 2026-07-19 |  | OVERDUE |  | Document Modernization 18
ACT-0469 | P-017 | R-0279 | Validate source data and document evidence. | E-179 | LOW | 2026-07-20 | 2026-07-20 | COMPLETED | EVID-0469 | Analytics Enablement 17
ACT-0470 | P-021 | R-0254 | Run the evaluation set and document failure cases. | E-173 | MEDIUM | 2026-11-20 |  | OPEN |  | Data Quality Improvement 21
ACT-0471 | P-016 | R-0212 | Update the risk response and obtain owner approval. | E-137 | HIGH | 2026-09-23 |  | OVERDUE |  | Data Quality Improvement 16
ACT-0472 | P-002 | R-0356 | Update the risk response and obtain owner approval. | E-225 | MEDIUM | 2026-12-23 | 2026-12-22 | COMPLETED | EVID-0472 | Risk Reporting Automation 02
ACT-0473 | P-003 | R-0231 | Update the risk response and obtain owner approval. | E-217 | LOW | 2026-06-01 |  | IN_PROGRESS |  | Training Digitization 03
ACT-0474 | P-027 | R-0407 | Update the risk response and obtain owner approval. | E-069 | MEDIUM | 2026-07-23 | 2026-07-21 | COMPLETED | EVID-0474 | Supplier Performance Improvement 27
ACT-0475 | P-011 | R-0135 | Validate source data and document evidence. | E-115 | HIGH | 2026-07-18 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 11
ACT-0476 | P-004 | R-0059 | Complete independent review of the proposed control. | E-074 | HIGH | 2026-07-08 | 2026-06-30 | COMPLETED | EVID-0476 | Knowledge Management 04
ACT-0477 | P-026 | R-0183 | Update the risk response and obtain owner approval. | E-115 | MEDIUM | 2026-07-20 | 2026-07-17 | COMPLETED | EVID-0477 | Training Digitization 26
ACT-0478 | P-013 | R-0180 | Run the evaluation set and document failure cases. | E-197 | LOW | 2026-11-29 | 2026-11-19 | COMPLETED | EVID-0478 | Document Modernization 13
ACT-0479 | P-008 | R-0408 | Run the evaluation set and document failure cases. | E-014 | MEDIUM | 2027-01-04 |  | OVERDUE |  | Data Quality Improvement 08
ACT-0480 | P-023 | R-0060 | Run the evaluation set and document failure cases. | E-142 | MEDIUM | 2026-09-06 |  | IN_PROGRESS |  | Supplier Performance Improvement 23
ACT-0481 | P-001 | R-0258 | Complete independent review of the proposed control. | E-194 | LOW | 2026-06-05 | 2026-06-01 | COMPLETED | EVID-0481 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0482 | P-022 | R-0312 | Validate source data and document evidence. | E-060 | MEDIUM | 2026-11-30 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0483 | P-010 | R-0136 | Complete independent review of the proposed control. | E-231 | MEDIUM | 2026-08-22 |  | OPEN |  | Document Modernization 10
ACT-0484 | P-020 | R-0104 | Run the evaluation set and document failure cases. | E-240 | MEDIUM | 2027-01-06 | 2027-01-04 | COMPLETED | EVID-0484 | Training Digitization 20
ACT-0485 | P-021 | R-0254 | Validate source data and document evidence. | E-064 | LOW | 2027-01-24 |  | IN_PROGRESS |  | Data Quality Improvement 21
ACT-0486 | P-014 | R-0200 | Update the risk response and obtain owner approval. | E-225 | LOW | 2026-06-10 | 2026-06-05 | COMPLETED | EVID-0486 | Analytics Enablement 14
ACT-0487 | P-005 | R-0369 | Run the evaluation set and document failure cases. | E-043 | HIGH | 2026-11-25 |  | OPEN |  | Maintenance Planning Enhancement 05
ACT-0488 | P-011 | R-0156 | Validate source data and document evidence. | E-166 | HIGH | 2026-09-22 |  | OPEN |  | Maintenance Planning Enhancement 11
ACT-0489 | P-006 | R-0321 | Run the evaluation set and document failure cases. | E-120 | MEDIUM | 2026-12-28 | 2026-12-28 | COMPLETED | EVID-0489 | Analytics Enablement 06
ACT-0490 | P-020 | R-0098 | Run the evaluation set and document failure cases. | E-019 | MEDIUM | 2026-12-22 | 2026-12-12 | COMPLETED | EVID-0490 | Training Digitization 20
ACT-0491 | P-003 | R-0235 | Run the evaluation set and document failure cases. | E-199 | LOW | 2027-02-17 | 2027-02-14 | COMPLETED | EVID-0491 | Training Digitization 03
ACT-0492 | P-020 | R-0301 | Run the evaluation set and document failure cases. | E-011 | LOW | 2026-12-30 |  | OPEN |  | Training Digitization 20
ACT-0493 | P-025 | R-0053 | Update the risk response and obtain owner approval. | E-042 | HIGH | 2027-02-04 |  | IN_PROGRESS |  | Knowledge Management 25
ACT-0494 | P-020 | R-0257 | Run the evaluation set and document failure cases. | E-185 | MEDIUM | 2026-06-16 | 2026-06-06 | COMPLETED | EVID-0494 | Training Digitization 20
ACT-0495 | P-026 | R-0197 | Run the evaluation set and document failure cases. | E-113 | LOW | 2026-12-02 |  | OVERDUE |  | Training Digitization 26
ACT-0496 | P-028 | R-0007 | Validate source data and document evidence. | E-236 | HIGH | 2026-10-07 |  | OVERDUE |  | Document Modernization 28
ACT-0497 | P-001 | R-0362 | Validate source data and document evidence. | E-026 | MEDIUM | 2026-08-22 | 2026-08-21 | COMPLETED | EVID-0497 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0498 | P-019 | R-0389 | Complete independent review of the proposed control. | E-228 | LOW | 2026-11-20 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 19
ACT-0499 | P-026 | R-0300 | Update the risk response and obtain owner approval. | E-208 | LOW | 2026-09-03 | 2026-09-02 | COMPLETED | EVID-0499 | Training Digitization 26
ACT-0500 | P-011 | R-0135 | Run the evaluation set and document failure cases. | E-059 | LOW | 2026-07-09 |  | OPEN |  | Maintenance Planning Enhancement 11
ACT-0501 | P-021 | R-0345 | Update the risk response and obtain owner approval. | E-164 | HIGH | 2026-05-30 |  | OPEN |  | Data Quality Improvement 21
ACT-0502 | P-021 | R-0020 | Validate source data and document evidence. | E-103 | LOW | 2026-08-23 | 2026-08-18 | COMPLETED | EVID-0502 | Data Quality Improvement 21
ACT-0503 | P-002 | R-0121 | Run the evaluation set and document failure cases. | E-120 | MEDIUM | 2026-10-16 | 2026-10-06 | COMPLETED | EVID-0503 | Risk Reporting Automation 02
ACT-0504 | P-020 | R-0198 | Validate source data and document evidence. | E-215 | LOW | 2027-01-25 |  | IN_PROGRESS |  | Training Digitization 20
ACT-0505 | P-018 | R-0221 | Update the risk response and obtain owner approval. | E-161 | MEDIUM | 2026-07-21 | 2026-07-12 | COMPLETED | EVID-0505 | Document Modernization 18
ACT-0506 | P-020 | R-0092 | Update the risk response and obtain owner approval. | E-187 | HIGH | 2026-12-23 | 2026-12-14 | COMPLETED | EVID-0506 | Training Digitization 20
ACT-0507 | P-007 | R-0126 | Run the evaluation set and document failure cases. | E-167 | LOW | 2026-08-16 |  | OPEN |  | Analytics Enablement 07
ACT-0508 | P-024 | R-0272 | Validate source data and document evidence. | E-135 | MEDIUM | 2026-06-26 | 2026-06-18 | COMPLETED | EVID-0508 | Knowledge Management 24
ACT-0509 | P-015 | R-0306 | Complete independent review of the proposed control. | E-038 | LOW | 2026-11-29 | 2026-11-23 | COMPLETED | EVID-0509 | Document Modernization 15
ACT-0510 | P-027 | R-0320 | Update the risk response and obtain owner approval. | E-238 | LOW | 2026-06-16 |  | OVERDUE |  | Supplier Performance Improvement 27
ACT-0511 | P-025 | R-0290 | Run the evaluation set and document failure cases. | E-066 | HIGH | 2026-12-15 |  | IN_PROGRESS |  | Knowledge Management 25
ACT-0512 | P-006 | R-0067 | Run the evaluation set and document failure cases. | E-187 | MEDIUM | 2027-02-18 | 2027-02-10 | COMPLETED | EVID-0512 | Analytics Enablement 06
ACT-0513 | P-018 | R-0209 | Validate source data and document evidence. | E-215 | HIGH | 2026-12-11 | 2026-12-01 | COMPLETED | EVID-0513 | Document Modernization 18
ACT-0514 | P-026 | R-0065 | Complete independent review of the proposed control. | E-040 | HIGH | 2026-10-15 | 2026-10-05 | COMPLETED | EVID-0514 | Training Digitization 26
ACT-0515 | P-003 | R-0420 | Validate source data and document evidence. | E-096 | HIGH | 2026-10-16 |  | OPEN |  | Training Digitization 03
ACT-0516 | P-028 | R-0007 | Validate source data and document evidence. | E-026 | HIGH | 2026-12-26 |  | OPEN |  | Document Modernization 28
ACT-0517 | P-026 | R-0296 | Run the evaluation set and document failure cases. | E-080 | HIGH | 2026-06-02 |  | OPEN |  | Training Digitization 26
ACT-0518 | P-018 | R-0176 | Update the risk response and obtain owner approval. | E-236 | HIGH | 2027-02-14 |  | IN_PROGRESS |  | Document Modernization 18
ACT-0519 | P-021 | R-0359 | Update the risk response and obtain owner approval. | E-139 | LOW | 2026-12-14 |  | IN_PROGRESS |  | Data Quality Improvement 21
ACT-0520 | P-006 | R-0335 | Update the risk response and obtain owner approval. | E-163 | MEDIUM | 2026-08-09 |  | IN_PROGRESS |  | Analytics Enablement 06
ACT-0521 | P-017 | R-0372 | Validate source data and document evidence. | E-031 | HIGH | 2027-01-11 |  | IN_PROGRESS |  | Analytics Enablement 17
ACT-0522 | P-005 | R-0052 | Update the risk response and obtain owner approval. | E-239 | LOW | 2027-01-09 | 2027-01-04 | COMPLETED | EVID-0522 | Maintenance Planning Enhancement 05
ACT-0523 | P-015 | R-0280 | Complete independent review of the proposed control. | E-055 | MEDIUM | 2026-08-24 |  | OPEN |  | Document Modernization 15
ACT-0524 | P-006 | R-0011 | Complete independent review of the proposed control. | E-089 | MEDIUM | 2026-07-02 | 2026-06-25 | COMPLETED | EVID-0524 | Analytics Enablement 06
ACT-0525 | P-013 | R-0180 | Run the evaluation set and document failure cases. | E-149 | HIGH | 2026-08-23 |  | OPEN |  | Document Modernization 13
ACT-0526 | P-019 | R-0086 | Complete independent review of the proposed control. | E-193 | HIGH | 2026-09-01 | 2026-09-01 | COMPLETED | EVID-0526 | Maintenance Planning Enhancement 19
ACT-0527 | P-021 | R-0269 | Complete independent review of the proposed control. | E-153 | MEDIUM | 2026-10-15 | 2026-10-13 | COMPLETED | EVID-0527 | Data Quality Improvement 21
ACT-0528 | P-018 | R-0281 | Complete independent review of the proposed control. | E-008 | MEDIUM | 2026-09-22 | 2026-09-12 | COMPLETED | EVID-0528 | Document Modernization 18
ACT-0529 | P-022 | R-0155 | Validate source data and document evidence. | E-230 | HIGH | 2026-08-31 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0530 | P-002 | R-0188 | Validate source data and document evidence. | E-189 | LOW | 2026-11-15 |  | OPEN |  | Risk Reporting Automation 02
ACT-0531 | P-018 | R-0221 | Validate source data and document evidence. | E-152 | LOW | 2026-08-08 | 2026-07-31 | COMPLETED | EVID-0531 | Document Modernization 18
ACT-0532 | P-009 | R-0395 | Complete independent review of the proposed control. | E-128 | HIGH | 2026-10-06 | 2026-10-04 | COMPLETED | EVID-0532 | Training Digitization 09
ACT-0533 | P-023 | R-0034 | Validate source data and document evidence. | E-183 | LOW | 2026-11-03 | 2026-11-01 | COMPLETED | EVID-0533 | Supplier Performance Improvement 23
ACT-0534 | P-013 | R-0378 | Run the evaluation set and document failure cases. | E-064 | MEDIUM | 2027-01-06 | 2026-12-28 | COMPLETED | EVID-0534 | Document Modernization 13
ACT-0535 | P-013 | R-0347 | Complete independent review of the proposed control. | E-101 | LOW | 2026-06-13 |  | OPEN |  | Document Modernization 13
ACT-0536 | P-004 | R-0228 | Run the evaluation set and document failure cases. | E-200 | LOW | 2026-07-09 |  | OPEN |  | Knowledge Management 04
ACT-0537 | P-019 | R-0030 | Validate source data and document evidence. | E-135 | LOW | 2026-09-04 | 2026-09-02 | COMPLETED | EVID-0537 | Maintenance Planning Enhancement 19
ACT-0538 | P-009 | R-0080 | Run the evaluation set and document failure cases. | E-207 | LOW | 2027-01-10 | 2026-12-31 | COMPLETED | EVID-0538 | Training Digitization 09
ACT-0539 | P-008 | R-0406 | Update the risk response and obtain owner approval. | E-040 | MEDIUM | 2026-07-29 |  | IN_PROGRESS |  | Data Quality Improvement 08
ACT-0540 | P-021 | R-0409 | Update the risk response and obtain owner approval. | E-207 | MEDIUM | 2026-10-12 |  | OPEN |  | Data Quality Improvement 21
ACT-0541 | P-005 | R-0117 | Run the evaluation set and document failure cases. | E-049 | HIGH | 2027-02-03 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 05
ACT-0542 | P-026 | R-0405 | Run the evaluation set and document failure cases. | E-047 | MEDIUM | 2026-09-18 | 2026-09-14 | COMPLETED | EVID-0542 | Training Digitization 26
ACT-0543 | P-020 | R-0092 | Validate source data and document evidence. | E-099 | LOW | 2026-08-21 |  | OVERDUE |  | Training Digitization 20
ACT-0544 | P-017 | R-0396 | Run the evaluation set and document failure cases. | E-220 | HIGH | 2026-08-11 |  | OPEN |  | Analytics Enablement 17
ACT-0545 | P-017 | R-0242 | Complete independent review of the proposed control. | E-237 | LOW | 2026-07-21 |  | OPEN |  | Analytics Enablement 17
ACT-0546 | P-013 | R-0036 | Complete independent review of the proposed control. | E-043 | HIGH | 2026-07-03 | 2026-06-28 | COMPLETED | EVID-0546 | Document Modernization 13
ACT-0547 | P-011 | R-0233 | Validate source data and document evidence. | E-023 | HIGH | 2026-11-22 |  | OVERDUE |  | Maintenance Planning Enhancement 11
ACT-0548 | P-006 | R-0222 | Update the risk response and obtain owner approval. | E-161 | LOW | 2026-06-12 |  | OPEN |  | Analytics Enablement 06
ACT-0549 | P-004 | R-0041 | Complete independent review of the proposed control. | E-160 | MEDIUM | 2026-10-15 |  | OPEN |  | Knowledge Management 04
ACT-0550 | P-004 | R-0263 | Validate source data and document evidence. | E-136 | HIGH | 2026-05-31 |  | IN_PROGRESS |  | Knowledge Management 04
ACT-0551 | P-006 | R-0222 | Validate source data and document evidence. | E-042 | HIGH | 2026-10-10 |  | IN_PROGRESS |  | Analytics Enablement 06
ACT-0552 | P-004 | R-0059 | Update the risk response and obtain owner approval. | E-116 | LOW | 2026-06-01 | 2026-05-31 | COMPLETED | EVID-0552 | Knowledge Management 04
ACT-0553 | P-021 | R-0269 | Validate source data and document evidence. | E-106 | LOW | 2026-06-26 | 2026-06-24 | COMPLETED | EVID-0553 | Data Quality Improvement 21
ACT-0554 | P-026 | R-0177 | Complete independent review of the proposed control. | E-006 | MEDIUM | 2027-01-21 | 2027-01-19 | COMPLETED | EVID-0554 | Training Digitization 26
ACT-0555 | P-006 | R-0326 | Run the evaluation set and document failure cases. | E-025 | HIGH | 2026-07-12 | 2026-07-05 | COMPLETED | EVID-0555 | Analytics Enablement 06
ACT-0556 | P-017 | R-0234 | Complete independent review of the proposed control. | E-124 | MEDIUM | 2026-07-06 |  | IN_PROGRESS |  | Analytics Enablement 17
ACT-0557 | P-012 | R-0236 | Complete independent review of the proposed control. | E-026 | LOW | 2026-08-07 | 2026-08-03 | COMPLETED | EVID-0557 | Document Modernization 12
ACT-0558 | P-005 | R-0338 | Validate source data and document evidence. | E-109 | LOW | 2026-09-19 |  | OVERDUE |  | Maintenance Planning Enhancement 05
ACT-0559 | P-005 | R-0012 | Update the risk response and obtain owner approval. | E-005 | MEDIUM | 2026-12-25 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 05
ACT-0560 | P-009 | R-0063 | Update the risk response and obtain owner approval. | E-009 | LOW | 2026-08-21 |  | OPEN |  | Training Digitization 09
ACT-0561 | P-006 | R-0220 | Run the evaluation set and document failure cases. | E-170 | LOW | 2026-10-27 |  | IN_PROGRESS |  | Analytics Enablement 06
ACT-0562 | P-021 | R-0020 | Validate source data and document evidence. | E-002 | MEDIUM | 2026-11-01 |  | OVERDUE |  | Data Quality Improvement 21
ACT-0563 | P-016 | R-0400 | Validate source data and document evidence. | E-108 | HIGH | 2027-02-10 |  | OPEN |  | Data Quality Improvement 16
ACT-0564 | P-011 | R-0156 | Complete independent review of the proposed control. | E-036 | LOW | 2026-08-12 |  | OVERDUE |  | Maintenance Planning Enhancement 11
ACT-0565 | P-004 | R-0250 | Complete independent review of the proposed control. | E-110 | LOW | 2026-10-16 | 2026-10-09 | COMPLETED | EVID-0565 | Knowledge Management 04
ACT-0566 | P-010 | R-0169 | Run the evaluation set and document failure cases. | E-050 | LOW | 2026-08-13 | 2026-08-05 | COMPLETED | EVID-0566 | Document Modernization 10
ACT-0567 | P-018 | R-0205 | Run the evaluation set and document failure cases. | E-233 | HIGH | 2026-09-26 |  | OVERDUE |  | Document Modernization 18
ACT-0568 | P-020 | R-0010 | Validate source data and document evidence. | E-188 | LOW | 2026-09-13 |  | OPEN |  | Training Digitization 20
ACT-0569 | P-013 | R-0173 | Run the evaluation set and document failure cases. | E-223 | LOW | 2026-07-11 |  | OPEN |  | Document Modernization 13
ACT-0570 | P-027 | R-0093 | Complete independent review of the proposed control. | E-027 | LOW | 2026-12-19 | 2026-12-14 | COMPLETED | EVID-0570 | Supplier Performance Improvement 27
ACT-0571 | P-019 | R-0414 | Complete independent review of the proposed control. | E-136 | HIGH | 2026-07-06 | 2026-06-27 | COMPLETED | EVID-0571 | Maintenance Planning Enhancement 19
ACT-0572 | P-019 | R-0349 | Update the risk response and obtain owner approval. | E-195 | MEDIUM | 2026-07-19 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 19
ACT-0573 | P-025 | R-0315 | Update the risk response and obtain owner approval. | E-194 | MEDIUM | 2026-07-05 | 2026-07-02 | COMPLETED | EVID-0573 | Knowledge Management 25
ACT-0574 | P-001 | R-0002 | Complete independent review of the proposed control. | E-236 | MEDIUM | 2026-09-30 | 2026-09-26 | COMPLETED | EVID-0574 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0575 | P-020 | R-0198 | Update the risk response and obtain owner approval. | E-124 | MEDIUM | 2027-01-27 | 2027-01-26 | COMPLETED | EVID-0575 | Training Digitization 20
ACT-0576 | P-023 | R-0267 | Run the evaluation set and document failure cases. | E-085 | HIGH | 2026-07-08 |  | IN_PROGRESS |  | Supplier Performance Improvement 23
ACT-0577 | P-016 | R-0366 | Run the evaluation set and document failure cases. | E-114 | MEDIUM | 2026-08-07 |  | IN_PROGRESS |  | Data Quality Improvement 16
ACT-0578 | P-019 | R-0162 | Run the evaluation set and document failure cases. | E-117 | LOW | 2026-06-30 | 2026-06-25 | COMPLETED | EVID-0578 | Maintenance Planning Enhancement 19
ACT-0579 | P-018 | R-0281 | Update the risk response and obtain owner approval. | E-028 | MEDIUM | 2027-01-19 | 2027-01-18 | COMPLETED | EVID-0579 | Document Modernization 18
ACT-0580 | P-001 | R-0161 | Update the risk response and obtain owner approval. | E-029 | LOW | 2026-11-27 | 2026-11-22 | COMPLETED | EVID-0580 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0581 | P-025 | R-0138 | Update the risk response and obtain owner approval. | E-083 | LOW | 2027-02-05 |  | IN_PROGRESS |  | Knowledge Management 25
ACT-0582 | P-018 | R-0209 | Validate source data and document evidence. | E-109 | MEDIUM | 2026-07-22 |  | OPEN |  | Document Modernization 18
ACT-0583 | P-012 | R-0255 | Validate source data and document evidence. | E-006 | MEDIUM | 2026-08-04 | 2026-08-03 | COMPLETED | EVID-0583 | Document Modernization 12
ACT-0584 | P-018 | R-0355 | Update the risk response and obtain owner approval. | E-028 | HIGH | 2026-07-16 | 2026-07-13 | COMPLETED | EVID-0584 | Document Modernization 18
ACT-0585 | P-019 | R-0325 | Run the evaluation set and document failure cases. | E-002 | HIGH | 2026-05-28 | 2026-05-23 | COMPLETED | EVID-0585 | Maintenance Planning Enhancement 19
ACT-0586 | P-021 | R-0077 | Validate source data and document evidence. | E-090 | MEDIUM | 2026-06-12 |  | OVERDUE |  | Data Quality Improvement 21
ACT-0587 | P-003 | R-0417 | Update the risk response and obtain owner approval. | E-164 | LOW | 2026-11-07 | 2026-11-03 | COMPLETED | EVID-0587 | Training Digitization 03
ACT-0588 | P-010 | R-0169 | Complete independent review of the proposed control. | E-075 | LOW | 2026-05-27 | 2026-05-24 | COMPLETED | EVID-0588 | Document Modernization 10
ACT-0589 | P-019 | R-0381 | Update the risk response and obtain owner approval. | E-112 | MEDIUM | 2026-12-14 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 19
ACT-0590 | P-010 | R-0136 | Update the risk response and obtain owner approval. | E-140 | HIGH | 2026-08-28 | 2026-08-25 | COMPLETED | EVID-0590 | Document Modernization 10
ACT-0591 | P-025 | R-0196 | Update the risk response and obtain owner approval. | E-093 | HIGH | 2026-08-03 |  | OPEN |  | Knowledge Management 25
ACT-0592 | P-026 | R-0386 | Validate source data and document evidence. | E-231 | LOW | 2026-09-16 |  | IN_PROGRESS |  | Training Digitization 26
ACT-0593 | P-016 | R-0273 | Validate source data and document evidence. | E-155 | LOW | 2026-07-11 |  | OVERDUE |  | Data Quality Improvement 16
ACT-0594 | P-016 | R-0360 | Complete independent review of the proposed control. | E-096 | MEDIUM | 2027-02-09 |  | IN_PROGRESS |  | Data Quality Improvement 16
ACT-0595 | P-008 | R-0118 | Complete independent review of the proposed control. | E-120 | MEDIUM | 2026-07-18 |  | OVERDUE |  | Data Quality Improvement 08
ACT-0596 | P-004 | R-0228 | Validate source data and document evidence. | E-212 | MEDIUM | 2026-07-30 | 2026-07-25 | COMPLETED | EVID-0596 | Knowledge Management 04
ACT-0597 | P-016 | R-0212 | Run the evaluation set and document failure cases. | E-143 | LOW | 2026-09-01 | 2026-08-23 | COMPLETED | EVID-0597 | Data Quality Improvement 16
ACT-0598 | P-009 | R-0063 | Validate source data and document evidence. | E-194 | MEDIUM | 2026-09-06 |  | IN_PROGRESS |  | Training Digitization 09
ACT-0599 | P-014 | R-0357 | Run the evaluation set and document failure cases. | E-130 | MEDIUM | 2026-12-23 |  | OPEN |  | Analytics Enablement 14
ACT-0600 | P-018 | R-0221 | Validate source data and document evidence. | E-169 | LOW | 2026-07-17 |  | OPEN |  | Document Modernization 18
ACT-0601 | P-005 | R-0369 | Complete independent review of the proposed control. | E-219 | LOW | 2026-12-01 | 2026-11-28 | COMPLETED | EVID-0601 | Maintenance Planning Enhancement 05
ACT-0602 | P-001 | R-0106 | Run the evaluation set and document failure cases. | E-217 | MEDIUM | 2026-07-10 | 2026-07-02 | COMPLETED | EVID-0602 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0603 | P-003 | R-0163 | Validate source data and document evidence. | E-107 | MEDIUM | 2026-10-24 | 2026-10-23 | COMPLETED | EVID-0603 | Training Digitization 03
ACT-0604 | P-006 | R-0277 | Validate source data and document evidence. | E-029 | HIGH | 2026-12-20 | 2026-12-10 | COMPLETED | EVID-0604 | Analytics Enablement 06
ACT-0605 | P-019 | R-0414 | Validate source data and document evidence. | E-183 | MEDIUM | 2027-01-05 | 2026-12-29 | COMPLETED | EVID-0605 | Maintenance Planning Enhancement 19
ACT-0606 | P-022 | R-0316 | Update the risk response and obtain owner approval. | E-023 | MEDIUM | 2026-10-09 |  | OVERDUE |  | Data Quality Improvement 22
ACT-0607 | P-023 | R-0388 | Complete independent review of the proposed control. | E-030 | MEDIUM | 2027-01-03 |  | OPEN |  | Supplier Performance Improvement 23
ACT-0608 | P-007 | R-0238 | Update the risk response and obtain owner approval. | E-179 | LOW | 2026-12-01 |  | OPEN |  | Analytics Enablement 07
ACT-0609 | P-009 | R-0387 | Run the evaluation set and document failure cases. | E-044 | LOW | 2026-09-09 | 2026-09-04 | COMPLETED | EVID-0609 | Training Digitization 09
ACT-0610 | P-013 | R-0378 | Complete independent review of the proposed control. | E-042 | LOW | 2026-12-23 |  | OPEN |  | Document Modernization 13
ACT-0611 | P-016 | R-0328 | Run the evaluation set and document failure cases. | E-126 | LOW | 2027-02-13 |  | OVERDUE |  | Data Quality Improvement 16
ACT-0612 | P-004 | R-0298 | Run the evaluation set and document failure cases. | E-072 | HIGH | 2027-01-23 | 2027-01-13 | COMPLETED | EVID-0612 | Knowledge Management 04
ACT-0613 | P-014 | R-0116 | Update the risk response and obtain owner approval. | E-032 | LOW | 2026-09-24 | 2026-09-16 | COMPLETED | EVID-0613 | Analytics Enablement 14
ACT-0614 | P-017 | R-0330 | Run the evaluation set and document failure cases. | E-054 | MEDIUM | 2026-09-27 |  | OVERDUE |  | Analytics Enablement 17
ACT-0615 | P-015 | R-0240 | Run the evaluation set and document failure cases. | E-218 | HIGH | 2026-09-23 |  | IN_PROGRESS |  | Document Modernization 15
ACT-0616 | P-017 | R-0251 | Update the risk response and obtain owner approval. | E-063 | HIGH | 2026-07-05 |  | OPEN |  | Analytics Enablement 17
ACT-0617 | P-014 | R-0200 | Complete independent review of the proposed control. | E-198 | MEDIUM | 2026-08-13 | 2026-08-07 | COMPLETED | EVID-0617 | Analytics Enablement 14
ACT-0618 | P-002 | R-0382 | Update the risk response and obtain owner approval. | E-042 | LOW | 2027-01-20 | 2027-01-13 | COMPLETED | EVID-0618 | Risk Reporting Automation 02
ACT-0619 | P-013 | R-0391 | Run the evaluation set and document failure cases. | E-215 | MEDIUM | 2027-01-13 | 2027-01-10 | COMPLETED | EVID-0619 | Document Modernization 13
ACT-0620 | P-003 | R-0231 | Run the evaluation set and document failure cases. | E-162 | LOW | 2026-12-21 |  | OPEN |  | Training Digitization 03
ACT-0621 | P-022 | R-0318 | Run the evaluation set and document failure cases. | E-232 | MEDIUM | 2026-12-17 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0622 | P-025 | R-0038 | Validate source data and document evidence. | E-013 | HIGH | 2026-09-24 |  | IN_PROGRESS |  | Knowledge Management 25
ACT-0623 | P-021 | R-0269 | Update the risk response and obtain owner approval. | E-007 | HIGH | 2027-01-29 | 2027-01-27 | COMPLETED | EVID-0623 | Data Quality Improvement 21
ACT-0624 | P-028 | R-0007 | Validate source data and document evidence. | E-199 | HIGH | 2026-11-20 | 2026-11-19 | COMPLETED | EVID-0624 | Document Modernization 28
ACT-0625 | P-028 | R-0339 | Validate source data and document evidence. | E-030 | LOW | 2026-08-30 |  | IN_PROGRESS |  | Document Modernization 28
ACT-0626 | P-028 | R-0227 | Run the evaluation set and document failure cases. | E-021 | LOW | 2026-07-10 |  | OPEN |  | Document Modernization 28
ACT-0627 | P-005 | R-0367 | Update the risk response and obtain owner approval. | E-212 | HIGH | 2027-01-18 |  | OPEN |  | Maintenance Planning Enhancement 05
ACT-0628 | P-003 | R-0417 | Update the risk response and obtain owner approval. | E-077 | HIGH | 2026-08-05 |  | IN_PROGRESS |  | Training Digitization 03
ACT-0629 | P-004 | R-0270 | Update the risk response and obtain owner approval. | E-060 | LOW | 2026-05-30 |  | OPEN |  | Knowledge Management 04
ACT-0630 | P-017 | R-0336 | Complete independent review of the proposed control. | E-209 | MEDIUM | 2026-11-13 | 2026-11-12 | COMPLETED | EVID-0630 | Analytics Enablement 17
ACT-0631 | P-011 | R-0363 | Validate source data and document evidence. | E-186 | LOW | 2026-08-10 |  | OVERDUE |  | Maintenance Planning Enhancement 11
ACT-0632 | P-008 | R-0252 | Complete independent review of the proposed control. | E-159 | LOW | 2027-02-19 |  | OPEN |  | Data Quality Improvement 08
ACT-0633 | P-001 | R-0199 | Update the risk response and obtain owner approval. | E-179 | MEDIUM | 2027-01-22 | 2027-01-13 | COMPLETED | EVID-0633 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0634 | P-015 | R-0306 | Complete independent review of the proposed control. | E-084 | MEDIUM | 2026-09-29 |  | IN_PROGRESS |  | Document Modernization 15
ACT-0635 | P-017 | R-0089 | Complete independent review of the proposed control. | E-104 | HIGH | 2027-02-18 |  | OVERDUE |  | Analytics Enablement 17
ACT-0636 | P-005 | R-0367 | Validate source data and document evidence. | E-119 | LOW | 2026-08-11 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 05
ACT-0637 | P-006 | R-0164 | Update the risk response and obtain owner approval. | E-057 | LOW | 2026-10-19 |  | OPEN |  | Analytics Enablement 06
ACT-0638 | P-018 | R-0085 | Run the evaluation set and document failure cases. | E-030 | MEDIUM | 2027-02-09 |  | OPEN |  | Document Modernization 18
ACT-0639 | P-017 | R-0251 | Complete independent review of the proposed control. | E-138 | MEDIUM | 2026-10-08 |  | OVERDUE |  | Analytics Enablement 17
ACT-0640 | P-027 | R-0042 | Validate source data and document evidence. | E-070 | LOW | 2026-08-05 |  | OPEN |  | Supplier Performance Improvement 27
ACT-0641 | P-006 | R-0113 | Run the evaluation set and document failure cases. | E-206 | HIGH | 2027-01-19 |  | OPEN |  | Analytics Enablement 06
ACT-0642 | P-004 | R-0228 | Run the evaluation set and document failure cases. | E-221 | LOW | 2026-11-15 |  | OVERDUE |  | Knowledge Management 04
ACT-0643 | P-005 | R-0276 | Validate source data and document evidence. | E-135 | LOW | 2027-01-11 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 05
ACT-0644 | P-011 | R-0233 | Complete independent review of the proposed control. | E-127 | HIGH | 2026-10-29 | 2026-10-22 | COMPLETED | EVID-0644 | Maintenance Planning Enhancement 11
ACT-0645 | P-020 | R-0104 | Update the risk response and obtain owner approval. | E-018 | LOW | 2027-01-06 | 2027-01-06 | COMPLETED | EVID-0645 | Training Digitization 20
ACT-0646 | P-001 | R-0002 | Run the evaluation set and document failure cases. | E-190 | LOW | 2026-05-27 |  | IN_PROGRESS |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0647 | P-022 | R-0309 | Complete independent review of the proposed control. | E-224 | HIGH | 2027-01-08 | 2027-01-05 | COMPLETED | EVID-0647 | Data Quality Improvement 22
ACT-0648 | P-016 | R-0328 | Run the evaluation set and document failure cases. | E-073 | LOW | 2026-10-20 | 2026-10-18 | COMPLETED | EVID-0648 | Data Quality Improvement 16
ACT-0649 | P-023 | R-0388 | Validate source data and document evidence. | E-194 | LOW | 2026-10-29 |  | IN_PROGRESS |  | Supplier Performance Improvement 23
ACT-0650 | P-014 | R-0344 | Validate source data and document evidence. | E-201 | HIGH | 2026-07-27 | 2026-07-25 | COMPLETED | EVID-0650 | Analytics Enablement 14
ACT-0651 | P-001 | R-0148 | Update the risk response and obtain owner approval. | E-059 | MEDIUM | 2026-10-10 |  | OPEN |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0652 | P-018 | R-0281 | Update the risk response and obtain owner approval. | E-083 | MEDIUM | 2026-11-18 | 2026-11-08 | COMPLETED | EVID-0652 | Document Modernization 18
ACT-0653 | P-022 | R-0190 | Validate source data and document evidence. | E-185 | LOW | 2026-10-14 |  | OPEN |  | Data Quality Improvement 22
ACT-0654 | P-028 | R-0151 | Run the evaluation set and document failure cases. | E-061 | HIGH | 2027-01-03 |  | IN_PROGRESS |  | Document Modernization 28
ACT-0655 | P-022 | R-0217 | Complete independent review of the proposed control. | E-124 | LOW | 2027-02-09 | 2027-02-05 | COMPLETED | EVID-0655 | Data Quality Improvement 22
ACT-0656 | P-003 | R-0231 | Run the evaluation set and document failure cases. | E-133 | MEDIUM | 2027-01-03 |  | OVERDUE |  | Training Digitization 03
ACT-0657 | P-009 | R-0027 | Complete independent review of the proposed control. | E-086 | MEDIUM | 2026-07-17 |  | IN_PROGRESS |  | Training Digitization 09
ACT-0658 | P-008 | R-0402 | Validate source data and document evidence. | E-143 | MEDIUM | 2026-11-15 | 2026-11-07 | COMPLETED | EVID-0658 | Data Quality Improvement 08
ACT-0659 | P-010 | R-0145 | Validate source data and document evidence. | E-159 | MEDIUM | 2026-07-05 | 2026-06-29 | COMPLETED | EVID-0659 | Document Modernization 10
ACT-0660 | P-006 | R-0124 | Update the risk response and obtain owner approval. | E-095 | LOW | 2026-07-23 |  | OVERDUE |  | Analytics Enablement 06
ACT-0661 | P-020 | R-0275 | Run the evaluation set and document failure cases. | E-091 | LOW | 2026-07-19 |  | OPEN |  | Training Digitization 20
ACT-0662 | P-022 | R-0155 | Run the evaluation set and document failure cases. | E-030 | HIGH | 2026-12-25 | 2026-12-18 | COMPLETED | EVID-0662 | Data Quality Improvement 22
ACT-0663 | P-028 | R-0322 | Complete independent review of the proposed control. | E-128 | MEDIUM | 2026-07-09 |  | IN_PROGRESS |  | Document Modernization 28
ACT-0664 | P-009 | R-0137 | Update the risk response and obtain owner approval. | E-193 | HIGH | 2026-11-04 | 2026-11-03 | COMPLETED | EVID-0664 | Training Digitization 09
ACT-0665 | P-024 | R-0051 | Complete independent review of the proposed control. | E-078 | MEDIUM | 2026-08-09 | 2026-08-03 | COMPLETED | EVID-0665 | Knowledge Management 24
ACT-0666 | P-025 | R-0243 | Run the evaluation set and document failure cases. | E-176 | LOW | 2026-11-25 | 2026-11-25 | COMPLETED | EVID-0666 | Knowledge Management 25
ACT-0667 | P-004 | R-0150 | Validate source data and document evidence. | E-145 | LOW | 2026-10-22 | 2026-10-14 | COMPLETED | EVID-0667 | Knowledge Management 04
ACT-0668 | P-022 | R-0312 | Complete independent review of the proposed control. | E-185 | MEDIUM | 2026-08-03 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0669 | P-002 | R-0224 | Validate source data and document evidence. | E-043 | MEDIUM | 2026-09-23 |  | OVERDUE |  | Risk Reporting Automation 02
ACT-0670 | P-019 | R-0123 | Run the evaluation set and document failure cases. | E-233 | LOW | 2026-07-07 | 2026-06-28 | COMPLETED | EVID-0670 | Maintenance Planning Enhancement 19
ACT-0671 | P-001 | R-0258 | Update the risk response and obtain owner approval. | E-050 | LOW | 2026-06-09 |  | OPEN |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0672 | P-007 | R-0031 | Complete independent review of the proposed control. | E-112 | LOW | 2026-10-19 |  | IN_PROGRESS |  | Analytics Enablement 07
ACT-0673 | P-013 | R-0130 | Update the risk response and obtain owner approval. | E-081 | HIGH | 2026-09-27 |  | IN_PROGRESS |  | Document Modernization 13
ACT-0674 | P-010 | R-0109 | Update the risk response and obtain owner approval. | E-212 | MEDIUM | 2026-07-23 |  | OVERDUE |  | Document Modernization 10
ACT-0675 | P-004 | R-0211 | Complete independent review of the proposed control. | E-017 | HIGH | 2026-11-05 | 2026-10-26 | COMPLETED | EVID-0675 | Knowledge Management 04
ACT-0676 | P-001 | R-0258 | Update the risk response and obtain owner approval. | E-025 | MEDIUM | 2026-09-21 |  | OPEN |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0677 | P-001 | R-0393 | Complete independent review of the proposed control. | E-212 | MEDIUM | 2026-08-03 |  | IN_PROGRESS |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0678 | P-001 | R-0362 | Run the evaluation set and document failure cases. | E-189 | HIGH | 2026-09-22 |  | OVERDUE |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0679 | P-018 | R-0355 | Complete independent review of the proposed control. | E-237 | MEDIUM | 2026-06-08 | 2026-05-29 | COMPLETED | EVID-0679 | Document Modernization 18
ACT-0680 | P-004 | R-0040 | Update the risk response and obtain owner approval. | E-042 | MEDIUM | 2027-02-20 |  | IN_PROGRESS |  | Knowledge Management 04
ACT-0681 | P-013 | R-0178 | Update the risk response and obtain owner approval. | E-085 | HIGH | 2026-11-06 |  | IN_PROGRESS |  | Document Modernization 13
ACT-0682 | P-021 | R-0166 | Complete independent review of the proposed control. | E-041 | LOW | 2026-08-24 | 2026-08-14 | COMPLETED | EVID-0682 | Data Quality Improvement 21
ACT-0683 | P-028 | R-0005 | Complete independent review of the proposed control. | E-007 | LOW | 2026-08-19 |  | OPEN |  | Document Modernization 28
ACT-0684 | P-010 | R-0194 | Run the evaluation set and document failure cases. | E-052 | LOW | 2026-12-13 |  | IN_PROGRESS |  | Document Modernization 10
ACT-0685 | P-025 | R-0196 | Validate source data and document evidence. | E-037 | HIGH | 2027-01-13 |  | IN_PROGRESS |  | Knowledge Management 25
ACT-0686 | P-023 | R-0388 | Update the risk response and obtain owner approval. | E-058 | MEDIUM | 2026-07-17 | 2026-07-12 | COMPLETED | EVID-0686 | Supplier Performance Improvement 23
ACT-0687 | P-013 | R-0311 | Complete independent review of the proposed control. | E-102 | LOW | 2026-12-09 | 2026-11-30 | COMPLETED | EVID-0687 | Document Modernization 13
ACT-0688 | P-026 | R-0197 | Complete independent review of the proposed control. | E-193 | LOW | 2026-12-12 |  | OVERDUE |  | Training Digitization 26
ACT-0689 | P-006 | R-0011 | Validate source data and document evidence. | E-146 | MEDIUM | 2026-06-05 |  | IN_PROGRESS |  | Analytics Enablement 06
ACT-0690 | P-009 | R-0063 | Run the evaluation set and document failure cases. | E-233 | HIGH | 2026-06-18 |  | IN_PROGRESS |  | Training Digitization 09
ACT-0691 | P-018 | R-0046 | Validate source data and document evidence. | E-113 | LOW | 2026-08-11 |  | OVERDUE |  | Document Modernization 18
ACT-0692 | P-009 | R-0375 | Run the evaluation set and document failure cases. | E-012 | LOW | 2027-02-01 | 2027-02-01 | COMPLETED | EVID-0692 | Training Digitization 09
ACT-0693 | P-020 | R-0010 | Update the risk response and obtain owner approval. | E-068 | HIGH | 2026-09-26 |  | IN_PROGRESS |  | Training Digitization 20
ACT-0694 | P-003 | R-0401 | Run the evaluation set and document failure cases. | E-001 | LOW | 2027-02-10 |  | OPEN |  | Training Digitization 03
ACT-0695 | P-018 | R-0281 | Validate source data and document evidence. | E-240 | MEDIUM | 2026-10-15 | 2026-10-07 | COMPLETED | EVID-0695 | Document Modernization 18
ACT-0696 | P-018 | R-0085 | Run the evaluation set and document failure cases. | E-056 | MEDIUM | 2026-06-25 |  | IN_PROGRESS |  | Document Modernization 18
ACT-0697 | P-010 | R-0194 | Update the risk response and obtain owner approval. | E-054 | HIGH | 2026-11-20 | 2026-11-12 | COMPLETED | EVID-0697 | Document Modernization 10
ACT-0698 | P-016 | R-0191 | Run the evaluation set and document failure cases. | E-183 | LOW | 2026-07-30 | 2026-07-23 | COMPLETED | EVID-0698 | Data Quality Improvement 16
ACT-0699 | P-026 | R-0087 | Validate source data and document evidence. | E-042 | HIGH | 2026-09-12 | 2026-09-10 | COMPLETED | EVID-0699 | Training Digitization 26
ACT-0700 | P-028 | R-0332 | Update the risk response and obtain owner approval. | E-228 | LOW | 2026-08-05 | 2026-08-04 | COMPLETED | EVID-0700 | Document Modernization 28
ACT-0701 | P-006 | R-0164 | Run the evaluation set and document failure cases. | E-232 | MEDIUM | 2027-02-08 |  | OPEN |  | Analytics Enablement 06
ACT-0702 | P-016 | R-0191 | Run the evaluation set and document failure cases. | E-211 | LOW | 2027-01-25 |  | IN_PROGRESS |  | Data Quality Improvement 16
ACT-0703 | P-009 | R-0375 | Validate source data and document evidence. | E-179 | HIGH | 2027-01-22 | 2027-01-22 | COMPLETED | EVID-0703 | Training Digitization 09
ACT-0704 | P-026 | R-0141 | Update the risk response and obtain owner approval. | E-098 | LOW | 2026-08-11 |  | IN_PROGRESS |  | Training Digitization 26
ACT-0705 | P-003 | R-0420 | Run the evaluation set and document failure cases. | E-119 | HIGH | 2026-09-22 |  | IN_PROGRESS |  | Training Digitization 03
ACT-0706 | P-009 | R-0375 | Update the risk response and obtain owner approval. | E-043 | LOW | 2026-11-29 |  | IN_PROGRESS |  | Training Digitization 09
ACT-0707 | P-014 | R-0116 | Complete independent review of the proposed control. | E-052 | HIGH | 2026-12-02 | 2026-11-24 | COMPLETED | EVID-0707 | Analytics Enablement 14
ACT-0708 | P-019 | R-0028 | Validate source data and document evidence. | E-240 | MEDIUM | 2027-01-31 | 2027-01-28 | COMPLETED | EVID-0708 | Maintenance Planning Enhancement 19
ACT-0709 | P-012 | R-0255 | Complete independent review of the proposed control. | E-013 | HIGH | 2026-10-25 |  | OVERDUE |  | Document Modernization 12
ACT-0710 | P-013 | R-0178 | Run the evaluation set and document failure cases. | E-115 | MEDIUM | 2026-09-30 | 2026-09-20 | COMPLETED | EVID-0710 | Document Modernization 13
ACT-0711 | P-012 | R-0149 | Complete independent review of the proposed control. | E-116 | MEDIUM | 2026-08-18 | 2026-08-08 | COMPLETED | EVID-0711 | Document Modernization 12
ACT-0712 | P-025 | R-0243 | Validate source data and document evidence. | E-134 | HIGH | 2026-11-30 | 2026-11-22 | COMPLETED | EVID-0712 | Knowledge Management 25
ACT-0713 | P-013 | R-0378 | Validate source data and document evidence. | E-038 | HIGH | 2027-02-10 |  | OPEN |  | Document Modernization 13
ACT-0714 | P-005 | R-0369 | Run the evaluation set and document failure cases. | E-004 | LOW | 2026-09-04 | 2026-09-01 | COMPLETED | EVID-0714 | Maintenance Planning Enhancement 05
ACT-0715 | P-004 | R-0331 | Update the risk response and obtain owner approval. | E-102 | MEDIUM | 2026-06-26 |  | OPEN |  | Knowledge Management 04
ACT-0716 | P-007 | R-0245 | Update the risk response and obtain owner approval. | E-046 | MEDIUM | 2026-07-21 |  | IN_PROGRESS |  | Analytics Enablement 07
ACT-0717 | P-022 | R-0309 | Validate source data and document evidence. | E-019 | LOW | 2026-12-07 |  | IN_PROGRESS |  | Data Quality Improvement 22
ACT-0718 | P-025 | R-0397 | Run the evaluation set and document failure cases. | E-131 | LOW | 2027-02-17 | 2027-02-07 | COMPLETED | EVID-0718 | Knowledge Management 25
ACT-0719 | P-023 | R-0370 | Update the risk response and obtain owner approval. | E-023 | LOW | 2026-11-18 |  | OPEN |  | Supplier Performance Improvement 23
ACT-0720 | P-022 | R-0371 | Run the evaluation set and document failure cases. | E-225 | HIGH | 2026-08-28 | 2026-08-24 | COMPLETED | EVID-0720 | Data Quality Improvement 22
ACT-0721 | P-016 | R-0360 | Validate source data and document evidence. | E-191 | HIGH | 2026-06-03 |  | OVERDUE |  | Data Quality Improvement 16
ACT-0722 | P-025 | R-0315 | Validate source data and document evidence. | E-230 | LOW | 2026-10-10 | 2026-10-03 | COMPLETED | EVID-0722 | Knowledge Management 25
ACT-0723 | P-017 | R-0372 | Validate source data and document evidence. | E-215 | HIGH | 2026-11-20 |  | OVERDUE |  | Analytics Enablement 17
ACT-0724 | P-021 | R-0020 | Update the risk response and obtain owner approval. | E-237 | MEDIUM | 2026-10-29 |  | OPEN |  | Data Quality Improvement 21
ACT-0725 | P-024 | R-0262 | Run the evaluation set and document failure cases. | E-124 | LOW | 2026-10-01 |  | OPEN |  | Knowledge Management 24
ACT-0726 | P-009 | R-0063 | Run the evaluation set and document failure cases. | E-205 | MEDIUM | 2027-01-11 | 2027-01-06 | COMPLETED | EVID-0726 | Training Digitization 09
ACT-0727 | P-013 | R-0072 | Run the evaluation set and document failure cases. | E-129 | LOW | 2026-12-13 |  | IN_PROGRESS |  | Document Modernization 13
ACT-0728 | P-001 | R-0199 | Update the risk response and obtain owner approval. | E-232 | LOW | 2026-10-12 |  | OPEN |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0729 | P-026 | R-0141 | Validate source data and document evidence. | E-159 | LOW | 2027-01-17 | 2027-01-12 | COMPLETED | EVID-0729 | Training Digitization 26
ACT-0730 | P-013 | R-0130 | Validate source data and document evidence. | E-152 | HIGH | 2026-11-03 |  | IN_PROGRESS |  | Document Modernization 13
ACT-0731 | P-021 | R-0409 | Validate source data and document evidence. | E-116 | LOW | 2026-12-02 | 2026-11-28 | COMPLETED | EVID-0731 | Data Quality Improvement 21
ACT-0732 | P-010 | R-0323 | Update the risk response and obtain owner approval. | E-174 | MEDIUM | 2026-12-28 |  | OPEN |  | Document Modernization 10
ACT-0733 | P-028 | R-0115 | Run the evaluation set and document failure cases. | E-003 | LOW | 2026-06-22 |  | OVERDUE |  | Document Modernization 28
ACT-0734 | P-027 | R-0398 | Update the risk response and obtain owner approval. | E-056 | HIGH | 2026-09-04 |  | OPEN |  | Supplier Performance Improvement 27
ACT-0735 | P-027 | R-0320 | Run the evaluation set and document failure cases. | E-176 | HIGH | 2026-09-07 | 2026-08-30 | COMPLETED | EVID-0735 | Supplier Performance Improvement 27
ACT-0736 | P-006 | R-0419 | Validate source data and document evidence. | E-083 | LOW | 2027-02-18 |  | OVERDUE |  | Analytics Enablement 06
ACT-0737 | P-005 | R-0415 | Validate source data and document evidence. | E-034 | HIGH | 2026-07-14 |  | OPEN |  | Maintenance Planning Enhancement 05
ACT-0738 | P-020 | R-0092 | Run the evaluation set and document failure cases. | E-057 | HIGH | 2026-12-18 |  | IN_PROGRESS |  | Training Digitization 20
ACT-0739 | P-024 | R-0248 | Complete independent review of the proposed control. | E-112 | LOW | 2026-08-06 |  | OVERDUE |  | Knowledge Management 24
ACT-0740 | P-007 | R-0374 | Complete independent review of the proposed control. | E-025 | LOW | 2026-12-10 | 2026-12-03 | COMPLETED | EVID-0740 | Analytics Enablement 07
ACT-0741 | P-003 | R-0417 | Run the evaluation set and document failure cases. | E-053 | MEDIUM | 2026-12-10 |  | IN_PROGRESS |  | Training Digitization 03
ACT-0742 | P-003 | R-0083 | Run the evaluation set and document failure cases. | E-228 | LOW | 2026-11-02 |  | OPEN |  | Training Digitization 03
ACT-0743 | P-015 | R-0214 | Complete independent review of the proposed control. | E-192 | MEDIUM | 2026-12-28 | 2026-12-24 | COMPLETED | EVID-0743 | Document Modernization 15
ACT-0744 | P-028 | R-0008 | Update the risk response and obtain owner approval. | E-131 | LOW | 2026-10-19 | 2026-10-15 | COMPLETED | EVID-0744 | Document Modernization 28
ACT-0745 | P-007 | R-0384 | Validate source data and document evidence. | E-160 | LOW | 2026-12-14 |  | OPEN |  | Analytics Enablement 07
ACT-0746 | P-011 | R-0308 | Update the risk response and obtain owner approval. | E-101 | HIGH | 2026-10-09 | 2026-10-08 | COMPLETED | EVID-0746 | Maintenance Planning Enhancement 11
ACT-0747 | P-002 | R-0356 | Run the evaluation set and document failure cases. | E-160 | LOW | 2026-10-29 | 2026-10-23 | COMPLETED | EVID-0747 | Risk Reporting Automation 02
ACT-0748 | P-024 | R-0017 | Update the risk response and obtain owner approval. | E-070 | LOW | 2026-07-01 | 2026-06-25 | COMPLETED | EVID-0748 | Knowledge Management 24
ACT-0749 | P-003 | R-0083 | Validate source data and document evidence. | E-084 | LOW | 2027-01-18 |  | IN_PROGRESS |  | Training Digitization 03
ACT-0750 | P-027 | R-0373 | Update the risk response and obtain owner approval. | E-096 | MEDIUM | 2026-09-02 |  | IN_PROGRESS |  | Supplier Performance Improvement 27
ACT-0751 | P-019 | R-0189 | Update the risk response and obtain owner approval. | E-043 | MEDIUM | 2026-11-11 |  | OPEN |  | Maintenance Planning Enhancement 19
ACT-0752 | P-007 | R-0182 | Complete independent review of the proposed control. | E-114 | MEDIUM | 2026-08-02 |  | IN_PROGRESS |  | Analytics Enablement 07
ACT-0753 | P-017 | R-0234 | Update the risk response and obtain owner approval. | E-051 | LOW | 2026-06-24 |  | OVERDUE |  | Analytics Enablement 17
ACT-0754 | P-023 | R-0304 | Complete independent review of the proposed control. | E-091 | LOW | 2026-07-14 |  | IN_PROGRESS |  | Supplier Performance Improvement 23
ACT-0755 | P-013 | R-0072 | Update the risk response and obtain owner approval. | E-088 | HIGH | 2026-09-10 |  | IN_PROGRESS |  | Document Modernization 13
ACT-0756 | P-025 | R-0138 | Complete independent review of the proposed control. | E-219 | HIGH | 2026-10-26 | 2026-10-19 | COMPLETED | EVID-0756 | Knowledge Management 25
ACT-0757 | P-003 | R-0231 | Validate source data and document evidence. | E-123 | MEDIUM | 2026-12-02 |  | IN_PROGRESS |  | Training Digitization 03
ACT-0758 | P-007 | R-0374 | Update the risk response and obtain owner approval. | E-067 | HIGH | 2026-07-01 |  | OPEN |  | Analytics Enablement 07
ACT-0759 | P-009 | R-0027 | Update the risk response and obtain owner approval. | E-108 | MEDIUM | 2026-09-22 |  | IN_PROGRESS |  | Training Digitization 09
ACT-0760 | P-001 | R-0001 | Update the risk response and obtain owner approval. | E-044 | MEDIUM | 2026-11-23 | 2026-11-21 | COMPLETED | EVID-0760 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0761 | P-028 | R-0404 | Update the risk response and obtain owner approval. | E-182 | HIGH | 2026-05-28 | 2026-05-23 | COMPLETED | EVID-0761 | Document Modernization 28
ACT-0762 | P-018 | R-0119 | Update the risk response and obtain owner approval. | E-011 | MEDIUM | 2026-06-08 |  | OPEN |  | Document Modernization 18
ACT-0763 | P-017 | R-0251 | Validate source data and document evidence. | E-209 | MEDIUM | 2027-01-02 | 2027-01-01 | COMPLETED | EVID-0763 | Analytics Enablement 17
ACT-0764 | P-021 | R-0359 | Validate source data and document evidence. | E-185 | MEDIUM | 2027-01-31 |  | OPEN |  | Data Quality Improvement 21
ACT-0765 | P-006 | R-0164 | Complete independent review of the proposed control. | E-216 | MEDIUM | 2026-11-29 |  | OPEN |  | Analytics Enablement 06
ACT-0766 | P-016 | R-0191 | Run the evaluation set and document failure cases. | E-240 | HIGH | 2026-10-28 |  | IN_PROGRESS |  | Data Quality Improvement 16
ACT-0767 | P-019 | R-0030 | Validate source data and document evidence. | E-170 | MEDIUM | 2026-12-12 |  | IN_PROGRESS |  | Maintenance Planning Enhancement 19
ACT-0768 | P-001 | R-0283 | Complete independent review of the proposed control. | E-175 | MEDIUM | 2026-10-17 | 2026-10-10 | COMPLETED | EVID-0768 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0769 | P-021 | R-0254 | Update the risk response and obtain owner approval. | E-037 | LOW | 2027-01-23 |  | OVERDUE |  | Data Quality Improvement 21
ACT-0770 | P-006 | R-0419 | Validate source data and document evidence. | E-210 | LOW | 2026-08-07 |  | OVERDUE |  | Analytics Enablement 06
ACT-0771 | P-026 | R-0268 | Validate source data and document evidence. | E-057 | MEDIUM | 2027-02-10 |  | IN_PROGRESS |  | Training Digitization 26
ACT-0772 | P-006 | R-0222 | Validate source data and document evidence. | E-191 | MEDIUM | 2026-12-15 |  | OPEN |  | Analytics Enablement 06
ACT-0773 | P-013 | R-0215 | Validate source data and document evidence. | E-207 | HIGH | 2026-10-19 |  | OVERDUE |  | Document Modernization 13
ACT-0774 | P-028 | R-0007 | Update the risk response and obtain owner approval. | E-196 | MEDIUM | 2026-12-27 |  | IN_PROGRESS |  | Document Modernization 28
ACT-0775 | P-011 | R-0233 | Update the risk response and obtain owner approval. | E-138 | MEDIUM | 2027-02-03 | 2027-01-28 | COMPLETED | EVID-0775 | Maintenance Planning Enhancement 11
ACT-0776 | P-017 | R-0403 | Validate source data and document evidence. | E-016 | MEDIUM | 2026-06-05 | 2026-06-03 | COMPLETED | EVID-0776 | Analytics Enablement 17
ACT-0777 | P-002 | R-0249 | Validate source data and document evidence. | E-223 | HIGH | 2026-07-18 |  | OPEN |  | Risk Reporting Automation 02
ACT-0778 | P-023 | R-0304 | Validate source data and document evidence. | E-065 | MEDIUM | 2026-10-14 |  | OVERDUE |  | Supplier Performance Improvement 23
ACT-0779 | P-013 | R-0347 | Complete independent review of the proposed control. | E-052 | LOW | 2026-08-21 | 2026-08-18 | COMPLETED | EVID-0779 | Document Modernization 13
ACT-0780 | P-014 | R-0291 | Complete independent review of the proposed control. | E-128 | MEDIUM | 2026-08-17 |  | OPEN |  | Analytics Enablement 14
ACT-0781 | P-028 | R-0018 | Update the risk response and obtain owner approval. | E-146 | LOW | 2026-10-17 |  | OPEN |  | Document Modernization 28
ACT-0782 | P-015 | R-0324 | Run the evaluation set and document failure cases. | E-141 | HIGH | 2027-01-06 | 2027-01-01 | COMPLETED | EVID-0782 | Document Modernization 15
ACT-0783 | P-019 | R-0325 | Complete independent review of the proposed control. | E-216 | HIGH | 2026-12-07 |  | OPEN |  | Maintenance Planning Enhancement 19
ACT-0784 | P-013 | R-0173 | Complete independent review of the proposed control. | E-128 | HIGH | 2027-01-18 | 2027-01-17 | COMPLETED | EVID-0784 | Document Modernization 13
ACT-0785 | P-014 | R-0344 | Complete independent review of the proposed control. | E-141 | LOW | 2026-07-16 |  | OVERDUE |  | Analytics Enablement 14
ACT-0786 | P-016 | R-0366 | Validate source data and document evidence. | E-164 | HIGH | 2026-11-22 |  | IN_PROGRESS |  | Data Quality Improvement 16
ACT-0787 | P-018 | R-0068 | Run the evaluation set and document failure cases. | E-109 | MEDIUM | 2026-08-20 |  | IN_PROGRESS |  | Document Modernization 18
ACT-0788 | P-026 | R-0405 | Run the evaluation set and document failure cases. | E-184 | HIGH | 2026-06-13 | 2026-06-04 | COMPLETED | EVID-0788 | Training Digitization 26
ACT-0789 | P-015 | R-0081 | Complete independent review of the proposed control. | E-195 | MEDIUM | 2026-09-25 | 2026-09-15 | COMPLETED | EVID-0789 | Document Modernization 15
ACT-0790 | P-024 | R-0213 | Complete independent review of the proposed control. | E-080 | LOW | 2026-12-23 |  | OVERDUE |  | Knowledge Management 24
ACT-0791 | P-021 | R-0413 | Complete independent review of the proposed control. | E-068 | MEDIUM | 2026-06-02 | 2026-05-24 | COMPLETED | EVID-0791 | Data Quality Improvement 21
ACT-0792 | P-021 | R-0107 | Validate source data and document evidence. | E-155 | MEDIUM | 2026-10-19 |  | OPEN |  | Data Quality Improvement 21
ACT-0793 | P-015 | R-0306 | Run the evaluation set and document failure cases. | E-147 | HIGH | 2026-11-09 | 2026-10-30 | COMPLETED | EVID-0793 | Document Modernization 15
ACT-0794 | P-006 | R-0192 | Update the risk response and obtain owner approval. | E-110 | MEDIUM | 2026-07-11 |  | OPEN |  | Analytics Enablement 06
ACT-0795 | P-025 | R-0226 | Run the evaluation set and document failure cases. | E-076 | MEDIUM | 2026-06-17 |  | OVERDUE |  | Knowledge Management 25
ACT-0796 | P-023 | R-0048 | Update the risk response and obtain owner approval. | E-157 | LOW | 2026-06-08 | 2026-05-31 | COMPLETED | EVID-0796 | Supplier Performance Improvement 23
ACT-0797 | P-001 | R-0258 | Run the evaluation set and document failure cases. | E-161 | HIGH | 2026-09-25 | 2026-09-22 | COMPLETED | EVID-0797 | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0798 | P-025 | R-0315 | Validate source data and document evidence. | E-041 | HIGH | 2026-11-22 |  | OPEN |  | Knowledge Management 25
ACT-0799 | P-001 | R-0393 | Validate source data and document evidence. | E-135 | MEDIUM | 2026-06-03 |  | OPEN |  | Enterprise Knowledge and Risk Intelligence Pilot
ACT-0800 | P-028 | R-0127 | Update the risk response and obtain owner approval. | E-025 | MEDIUM | 2026-06-28 |  | IN_PROGRESS |  | Document Modernization 28
ACT-0801 | P-029 | R-0421 | Validate the A-001 vibration source and define the temporary monitoring frequency using the approved inspection procedure. | E-001 | HIGH | 2026-08-27 |  | IN_PROGRESS | WO-00001; INSP-0001; DOC-PROC-001-V2 | A-001 Cooling Water Pump Reliability Improvement
ACT-0802 | P-029 | R-0422 | Reconcile all A-001 open/deferred/not-yet-completed work orders and identify which ones are relevant to the reliability issue. | E-075 | HIGH | 2026-09-04 |  | OPEN | A-001 work-order register as of 2026-08-25 | A-001 Cooling Water Pump Reliability Improvement
ACT-0803 | P-029 | R-0423 | Confirm DOC-PROC-001-V2 as the execution reference and mark V1 as superseded and V3 as draft-only in the project evidence pack. | E-041 | MEDIUM | 2026-08-30 |  | IN_PROGRESS | DOC-PROC-001-V1; DOC-PROC-001-V2; DOC-PROC-001-V3D | A-001 Cooling Water Pump Reliability Improvement
ACT-0804 | P-029 | R-0421 | Build a seven-day A-001 forecast baseline from the one-minute sensor history using hourly aggregation; compare forecasted vibration and temperature against the observed degradation trend. | E-137 | MEDIUM | 2026-09-01 |  | OPEN | sensor_readings_a001_1min; a001_sensor_hourly; recommended horizon = 168 hourly steps | A-001 Cooling Water Pump Reliability Improvement
ACT-0805 | P-029 | R-0421 | Train and back-test a baseline hourly forecasting model using the preceding 12 months of A-001 data; record MAE/RMSE for vibration and temperature. | E-137 | MEDIUM | 2026-09-02 |  | OPEN | sensor_readings_a001_1min; a001_sensor_hourly | A-001 Cooling Water Pump Reliability Improvement
ACT-0806 | P-029 | R-0421 | Generate a seven-day hourly forecast with prediction intervals and flag forecast hours where vibration is expected to cross 5.0 mm/s. | E-137 | HIGH | 2026-09-04 |  | OPEN | a001_sensor_hourly; threshold rule vibration >= 5.0 mm/s | A-001 Cooling Water Pump Reliability Improvement
ACT-0807 | P-029 | R-0421 | Use the forecast together with inspection INSP-0001 and work order WO-00001 to prepare a human-reviewed maintenance recommendation; no automatic intervention. | E-001 | HIGH | 2026-09-05 |  | OPEN | INSP-0001; WO-00001; DOC-PROC-001-V2 | A-001 Cooling Water Pump Reliability Improvement

## project_asset_links
project_asset_id | project_id | asset_id | relationship_type | scope_description | start_date | end_date | status | project_name | asset_name
PA-0002 | P-021 | A-001 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Pump 001
PA-0003 | P-021 | A-002 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Motor 002
PA-0004 | P-021 | A-003 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Valve 003
PA-0005 | P-021 | A-004 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Heat Exchanger 004
PA-0006 | P-021 | A-005 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Fan 005
PA-0007 | P-021 | A-006 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Compressor 006
PA-0008 | P-021 | A-007 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Transformer 007
PA-0009 | P-021 | A-008 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Filter 008
PA-0010 | P-021 | A-033 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Pump 033
PA-0011 | P-021 | A-034 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Motor 034
PA-0012 | P-021 | A-035 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Valve 035
PA-0013 | P-021 | A-036 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Heat Exchanger 036
PA-0014 | P-021 | A-037 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Fan 037
PA-0015 | P-021 | A-038 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Compressor 038
PA-0016 | P-021 | A-039 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Transformer 039
PA-0017 | P-021 | A-040 | DATA_VALIDATION_SCOPE | Cooling Water asset included in the Engineering data-quality validation scope for Training Units A and B. Relationship is rule-based from system membership, not randomly assigned. | 2025-11-18 | 2027-04-27 | ACTIVE | Data Quality Improvement 21 | Filter 040
PA-0018 | P-027 | A-001 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Pump 001
PA-0019 | P-027 | A-002 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Motor 002
PA-0020 | P-027 | A-007 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Transformer 007
PA-0021 | P-027 | A-011 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Valve 011
PA-0022 | P-027 | A-012 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Heat Exchanger 012
PA-0023 | P-027 | A-037 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Fan 037
PA-0024 | P-027 | A-043 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Valve 043
PA-0025 | P-027 | A-066 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Motor 066
PA-0026 | P-027 | A-071 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Transformer 071
PA-0027 | P-027 | A-099 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Valve 099
PA-0028 | P-027 | A-107 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Valve 107
PA-0029 | P-027 | A-108 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Heat Exchanger 108
PA-0030 | P-027 | A-111 | SUPPLIER_PERFORMANCE_SCOPE | Engineering asset included in the Fictional Dynamics supplier-performance cohort based on manufacturer and responsible department. | 2026-03-19 | 2027-05-30 | ACTIVE | Supplier Performance Improvement 27 | Transformer 111
PA-0001 | P-029 | A-001 | PRIMARY_SCOPE | Reliability improvement project created from the sustained vibration trend, declining health score, urgent inspection work order, and high-severity condition inspection. | 2026-08-20 | 2026-11-18 | ACTIVE | A-001 Cooling Water Pump Reliability Improvement | Pump 001